# EOS S06B Experience and Operating Workflows

Canonical frontend journeys task orchestration and human operations

Maison Doclar Event OS

| Control code | EOS-S06B-03 |
| --- | --- |
| Status | CEO RATIFICATION DRAFT |
| Programme position | After EOS S06A and before EOS S07 |
| Production effect | None until separately authorised |

# Primary navigation

| Surface | Purpose |
| --- | --- |
| VIP Command | Event-wide status, conflicts, capacity, deadlines and readiness. |
| People requiring attention | VIP and accessibility work queue prioritised by consequence and deadline. |
| Guest intelligence brief | Individual categories, needs, unknowns, decisions, tasks and handoffs. |
| Accessibility Command | Standalone view for all guests with support needs and readiness. |
| Protocol and precedence | Titles, ordering, recognition, arrival and ceremonial dependencies. |
| Entourage and arrivals | Parties, vehicles, escorts, entrances, holding and departure. |
| Decisions and approvals | Maker-checker queue and durable result truth. |
| Tasks and handoffs | Owners, deadlines, dependencies, deep links and completion evidence. |
| Audit and changes | Actor, target, reason, before-after, result and staleness. |

# VIP flag to plan journey

Flag the guest as requiring VIP review and record who requested it and why.

Select one or more event-specific significance categories.

Run applicable question sets; preserve unknown, declined and not-applicable answers.

Create domain handoffs for Protocol, Accessibility, Culture, Religion, Security, Hospitality, Seating or Communications.

Generate a grounded draft brief with sources and uncertainty.

Review contradictions, dependencies, capacity effects and sensitive visibility.

Assign tasks, owners and deadlines.

Submit protected decisions for independent approval.

Publish the current approved operational brief and event impact snapshot.

Monitor changes and mark affected outputs stale.

Close obligations after the event with audit and limited learning data.

# Accessibility journey

Allow any guest—not only a VIP—to be referred or self-identify a support need.

Ask functional, respectful questions and permit the guest to decline optional detail.

Translate answers into minimum-necessary operational instructions.

Confirm companion or carer relationships and entitlements separately.

Check venue routes, seating, toilets, transport, waiting, evacuation and programme conditions.

Assign an Accessibility Lead and accountable delivery owners.

Surface unresolved needs and deadline risk in Accessibility Command and event-wide impact.

Share only the instruction required by each team.

Reconfirm after material venue, seating, timing or transport change.

Record delivery, exceptions and post-event closure without broadcasting diagnosis.

# Category driven question families

| Question family | Required coverage |
| --- | --- |
| Universal | Why is the guest significant for this event? Who confirmed it? What remains unknown? What decisions or deadlines depend on it? |
| Protocol | Correct title, precedence, greeting, announcement, receiving party, ceremony, stage, gifts and liaison? |
| Accessibility | Functional access, route, distance, seating, communication, companion, environment, transport, evacuation and preferred assistance? |
| Culture | Customary greeting, naming, dress, symbols, gender or family practice confirmed by the guest or authorised source? |
| Religion | Confirmed observance, food, prayer, timing, alcohol, photography, greeting or seating consideration? |
| Security privacy | Protection liaison, arrival privacy, photography, media, vehicle, holding and disclosure restrictions? |
| Hospitality | Travel, hotel, transport, refreshments, lounge, gifts, itinerary, departure and follow-up? |
| Entourage | Who accompanies the guest, in what role, with what access, seat, credential, transport and care dependency? |
| Programme | Speech, performance, honour, presentation, officiation, stage movement and timing? |
| Seating | Precedence, table companions, accessibility, security, line of sight, stage movement and separation constraints? |

# Event-level conflict patterns

Two guests expect precedence or the same ceremonial position

Several protected arrivals require the same entrance and receiving party

Entourage totals exceed seating, transport, credential or holding capacity

Accessibility routes or companion seating conflict with protocol placements

Religious or cultural timing conflicts with programme commitments

Photography or media restrictions conflict with public recognition plans

Security separation conflicts with family, stage or table requirements

A title, announcement or gift remains unapproved near production deadline

A changed venue, layout or programme makes an approved brief stale

# Required interface states

Loading and progressive disclosure

Empty with guided first action

Unknown and confirmation required

Declined and privacy-respecting

Contradicted with sources side by side

Blocked with owner and next step

Stale with changed dependency and affected outputs

Partial with completed and outstanding obligations

Denied without leaking restricted existence

Success with durable action result and correlation

Offline or connection loss without false success

Concurrent update and safe recovery

# Premium usability standards

Command Atelier visual language with calm hierarchy and restrained colour

Human labels before technical identifiers

Pointer cursor on clickable controls

No auditor-facing live mutation affordances

Consequential actions state effect, authority and reversibility before confirmation

Search and filter across name, category, readiness, owner, deadline and unresolved need

Mobile operational triage at 360px; tablet and desktop command views

Keyboard, screen-reader semantics, zoom, reflow and non-colour status cues

No dense dashboard that hides the individual human behind aggregate counts

# Operational outputs

| Output | Minimum content |
| --- | --- |
| Individual brief | Verified identity, categories, needs, unknowns, instructions, tasks, decisions and sources. |
| Event impact snapshot | Counts, conflicts, capacity, deadlines, owners and readiness. |
| Accessibility readiness register | Guest-safe instructions, route/service readiness, ownership and unresolved risks. |
| Protocol run sheet | Precedence, greetings, announcements, ceremonial actions and owners. |
| Arrival movement plan | Windows, entrances, vehicles, escorts, holding and departure. |
| Entourage register | Members or counts, roles, entitlements and dependencies. |
| Decision record | Maker, checker, authority, reason, evidence, effect and expiry. |
| Task bank work plan | Canonical task, owner, due date, dependencies, deep link and settlement. |