MAISON DOCLAR

Canonical Academy Blueprint

Architecture, curriculum, assessment, certification, frontend, integration and production delivery

CANONICAL PURPOSE Convert the Maison Doclar Intelligence Specification into governed human competence, verified certification and event-level operational readiness.

Version 1.0

3 September 2026

Status: Draft for CEO ratification

Maison Doclar | Internal and restricted

# Document control and ratification

| Field | Canonical value |
| --- | --- |
| Document | Maison Doclar Academy Canonical Blueprint |
| Version | 1.0 |
| Owner | CEO, Maison Doclar |
| System | Maison Doclar Academy |
| Primary source | Maison Doclar Intelligence Specification v1.0 Final Draft |
| Related system | Maison Doclar Event Operating System (MD-EOS) |
| Decision status | Proposed for CEO ratification |
| Change rule | Material architecture, assessment, certification or authority changes require a recorded decision and new version. |

## Ratification effect

Once ratified, this blueprint governs the Academy build. Implementation specifications may add detail but may not weaken or contradict its laws. A contradiction must stop the affected build slice until the blueprint is formally amended.

## How to use this blueprint

Product and engineering use it to define system boundaries and implementation contracts.

Curriculum authors use it to convert the 30 modules into versioned learning content.

Assessment authors use it to produce difficult, traceable and defensible evaluations.

Operations use it to determine whether a person may be assigned to a particular event role.

Independent reviewers use it as the acceptance baseline.

The CEO uses it to approve material policy, risk and production decisions.

# Contents

| Part I | Part II |
| --- | --- |
| 1. Executive system definition | 13. Complete frontend architecture |
| 2. Outcomes, scope and exclusions | 14. Intelligence, reporting and alerts |
| 3. Canonical laws | 15. Content governance and versioning |
| 4. System architecture and repository boundaries | 16. Security, privacy and assessment integrity |
| 5. Users, roles and authority | 17. Reliability and operations |
| 6. Curriculum and knowledge architecture | 18. Technical stack and repository structure |
| 7. Competency and learning-path architecture | 19. Production build sequence |
| 8. Assessment architecture | 20. Acceptance and release gates |
| 9. Certification and operational authorisation | Appendix A. Canonical status models |
| 10. Event-specific training | Appendix B. Core API contracts |
| 11. OS-Academy integration | Appendix C. Traceability and definition of done |
| 12. Canonical data model |  |

# 1. Executive system definition

SYSTEM DEFINITION Maison Doclar Academy is a production competency system that teaches the Maison Doclar operating standard, tests applied judgment, certifies role competence and returns event-readiness evidence to MD-EOS.

It is not a document library, a generic learning-management system or a substitute for supervised performance. Its job is to make the Maison Doclar standard learnable, assessable, deployable and auditable across permanent staff, temporary teams, vendors and leadership.

## 1.1 The competence chain

| Stage | Meaning | System evidence |
| --- | --- | --- |
| Know | The learner understands the rule and its rationale. | Completed learning activities and knowledge checks |
| Judge | The learner selects the right action in realistic ambiguity. | Scenario and branching-assessment results |
| Demonstrate | The learner performs the responsibility under observation. | Practical assessment and assessor rubric |
| Certify | Maison Doclar confirms role competence for a defined period. | Versioned certificate with scope and expiry |
| Authorise | The person may perform a defined role for a specific event. | Event-readiness decision returned to MD-EOS |
| Learn | Performance and incidents improve future training. | Approved curriculum change and reassignment record |

## 1.2 Success measures

No controlled event role is staffed without valid competence and event readiness.

Every curriculum claim and assessment answer traces to approved knowledge.

Learners can complete assigned work effectively on a mobile phone.

Managers see readiness gaps early enough to correct staffing or training.

Material operational lessons become governed curriculum improvements.

The Academy does not expose guest or event information beyond genuine training need.

# 2. Outcomes, scope and exclusions

## 2.1 Included

Staff identity and Academy profile

Roles, departments and competence profiles

Thirty-module canonical knowledge base

Courses, lessons, scenarios and learning activities

Role learning paths and prerequisites

Question banks and assessment assemblies

Automated and manual marking

Unlimited governed retakes

Practical observation and sign-off

Certificates, renewal, suspension and revocation

Event-specific training and acknowledgements

OS integration and readiness return

Manager, assessor, author, administrator and CEO workspaces

Notifications, audit, reporting and learning intelligence

## 2.2 Explicit exclusions

The Academy does not become the master staff-employment or payroll system.

It does not own event plans, guest records, seating, credentials or live-event command.

It does not automatically publish draft OS information into training.

It does not certify a person solely because content was opened or a video was played.

It does not allow AI to invent doctrine, mark subjective judgment without review, or issue certificates.

It does not treat a job-title change as proof of competence.

## 2.3 Production-fidelity principle

The build is not an MVP. Every released slice must include its complete user journey, permissions, error states, responsive frontend, accessibility, audit trail, tests and operational controls. Scope economy comes from eliminating duplication and keeping bounded modules, not from deferring essential quality.

# 3. Canonical laws

| Law | Binding meaning |
| --- | --- |
| Knowledge provenance | Every teachable rule and every scored answer must trace to an approved source item and version. |
| Competence is not attendance | Completion, assessment, certification and authorisation are different states. |
| Least necessary learning data | Learners receive only the event and guest information needed for their role. |
| Critical knowledge cannot average out | Failure of a designated critical competency prevents certification even where the total score is 80% or more. |
| Role change creates a gap analysis | Vertical or horizontal movement reuses valid competence and assigns only missing requirements. |
| Event readiness is event-scoped | A general certificate does not by itself authorise event deployment. |
| Published versions are immutable | Approved content and assessment versions are superseded, never silently rewritten. |
| Author and approver are separated | A person cannot solely approve their own high-risk content, question bank, practical result or exception. |
| Retakes remain possible | Learners may retake when ready, while every attempt remains auditable and fresh forms protect integrity. |
| Sensitive capabilities require explicit competence | AI, FaceGate, biometrics, privacy, child safeguarding and high-risk command duties require separate, current authority. |
| OS and Academy remain independently operable | Integration failure does not corrupt either system; reconciliation restores truth. |
| Frontend is operational infrastructure | Mobile usability, clarity, accessibility and safe recovery are release requirements, not decoration. |

# 4. System architecture and repository boundaries

## 4.1 Recommended deployment model

Build the Academy in a separate repository and deploy it independently. Use the same identity provider and organisation model as MD-EOS where practicable, but give the Academy its own database, release cycle and operational ownership.

| System | Owns | Must not own |
| --- | --- | --- |
| MD-EOS | Events, assignments, approved event plans, guests, operational permissions, live readiness and event decisions | Curriculum, assessment attempts or certificates |
| Academy | Learning content, competencies, enrolments, attempts, practical evidence, certificates and training readiness | Canonical event plans, guest master data or final event staffing authority |
| Identity service | Authentication, organisation membership and durable person identity | Business-specific competence or event data |
| Integration layer | Versioned package delivery, status return, retries and reconciliation | Independent business truth |

## 4.2 Logical components

Learner application: mobile-first learning, assessment, certificates and event briefings.

Management application: enrolment, readiness, interventions and team analysis.

Authoring studio: structured knowledge, courses, question banks and approval workflow.

Assessment service: secure assembly, attempt control, marking and result calculation.

Certification service: issue, renew, suspend, revoke and verify certificates.

Event-training service: ingest approved packages, assign deltas and publish readiness.

Intelligence service: deterministic alerts and governed analytics; AI only assists bounded drafting or analysis.

Audit and evidence service: immutable business events and durable supporting artefacts.

## 4.3 Separation test

BOUNDARY TEST If MD-EOS is unavailable, existing Academy learning and certificates remain usable. If the Academy is unavailable, MD-EOS retains its event truth and fails closed for assignments requiring current training verification.

# 5. Users, roles and authority

| Role | Primary authority | Key prohibition |
| --- | --- | --- |
| Learner | Complete assigned learning, attempts and acknowledgements | Cannot change results or requirements |
| Line Manager | View team readiness, assign permitted learning, request intervention | Cannot mark their own high-risk practical evidence without policy permission |
| Assessor | Conduct and score practical or written assessments | Cannot alter source doctrine |
| Curriculum Author | Draft structured knowledge, lessons and questions | Cannot publish alone |
| Curriculum Reviewer | Review accuracy, pedagogy and source traceability | Cannot silently edit published content |
| Certification Authority | Approve controlled certifications, suspensions and revocations | Cannot bypass missing critical competence |
| Event Director | Own event-training completion and operational recommendation | Cannot grant corporate certification |
| Academy Administrator | Manage configuration, enrolments and support | Administrative access is not academic approval |
| Security / Privacy Reviewer | Approve restricted content and sensitive-capability training | Cannot approve unrelated operational competence |
| CEO | Ratify standards, reserved curricula, exceptions and production release | Cannot self-verify technical or academic evidence |
| System Integration Principal | Authenticated service account for bounded data exchange | No interactive learner or approver authority |

## 5.1 Permission model

Authorisation uses organisation, role, resource, action, scope and context. Context includes event, department, confidentiality, content state, learner relationship and separation-of-duty rules. UI hiding is never the enforcement layer; every server action repeats the permission decision.

# 6. Curriculum and knowledge architecture

## 6.1 Canonical source model

The Intelligence Specification is imported by controlled editorial work, not copied as undifferentiated prose. Each rule becomes a structured Knowledge Item. The first production knowledge base must cover all 30 modules and retain Lagos-specific context alongside globally reusable doctrine.

| Knowledge Item field | Purpose |
| --- | --- |
| Knowledge ID | Stable identifier |
| Module and source locator | Exact provenance |
| Title and statement | What is taught |
| Knowledge type | Doctrine, standard, rule, procedure, checklist, example, warning or judgment pattern |
| Applicability | Role, geography, event type, lifecycle stage and capability |
| Criticality | Normal, important, critical or stop-authority |
| Decision / action | Expected application |
| Exceptions and escalation | When the normal rule is insufficient |
| Version and state | Draft, review, approved, published, superseded or retired |
| Owner and approver | Accountability |
| Assessment links | Questions and practical criteria that test it |

## 6.2 Learning content hierarchy

| Level | Meaning |
| --- | --- |
| Academy | Organisation-wide learning environment |
| Programme | A coherent professional pathway, such as Event Leadership |
| Course | Certifiable body of competence |
| Module | Major subject mapped to source knowledge |
| Lesson | Short instructional unit with objectives |
| Activity | Reading, video, demonstration, scenario, reflection or practice |
| Knowledge check | Low-stakes formative check |
| Assessment | Controlled evidence used for a certification decision |

## 6.3 Content requirements

Learning objectives written as observable capability

Plain-English instruction without weakening operational precision

Relevant examples and counterexamples

Common failure modes and escalation triggers

Lagos context clearly labelled, not treated as universal fact

Role variants where actions or visibility differ

Source and version metadata invisible to casual reading but available for audit

Accessibility alternatives for audiovisual content

# 7. Competency and learning-path architecture

## 7.1 Competency model

| Dimension | Evidence |
| --- | --- |
| Knowledge | Objective and constructed-response assessment |
| Judgment | Scenario, branching and best/worst-response performance |
| Procedure | Sequencing, simulation or observed execution |
| Behaviour | Supervisor or assessor observation against anchored rubric |
| Leadership | Decision quality, delegation, escalation and debrief evidence |
| Currency | Valid version, time period and required refresher completion |

## 7.2 Initial learning paths

| Path | Default scope |
| --- | --- |
| CEO | All 30 modules; governance, commercial judgment, crisis, privacy, AI and release authority |
| Event Director | Full operational command, standards, teams, vendors, guest journey, risk and recovery |
| Department Lead | Core standard plus complete departmental, supervisory and escalation competence |
| Concierge / Protocol Lead | Guest intelligence, culture, protocol, communication, discretion and recovery |
| Concierge / Host | Guest recognition, service language, assistance, recovery and escalation |
| Usher | Arrival, access, seating, wayfinding, conduct, safeguarding and escalation |
| Check-in / Access | Identity verification, credentials, exception handling, privacy and device workflow |
| Vendor / Temporary Staff | Essential conduct, safety, confidentiality and task-specific responsibilities |
| Academy / System Administrator | Administration, security and support without automatic academic authority |

## 7.3 Vertical and horizontal changes

A role change triggers a deterministic gap analysis. The system compares the learner's current, unexpired competency evidence with the target role profile, credits true equivalence and enrols the learner only into missing or superseded requirements. The new role remains provisional until all required knowledge, practical and event-specific conditions are satisfied.

NO WASTE, NO ASSUMPTION Valid shared competence is reused; a new title never grants competence automatically.

# 8. Assessment architecture

## 8.1 Scoring law

| Outcome | Score | Additional condition |
| --- | --- | --- |
| Pass with distinction | 90–100% | Every critical competency passed |
| Pass | 80–89% | Every critical competency passed |
| Retake required | Below 80% | New attempt permitted when learner is ready |
| Critical fail | Any total | One or more mandatory critical conditions failed |

## 8.2 Supported question formats

Single-answer multiple choice

Multiple selection with partial-credit policy defined per item

True/false with required reasoning

Matching

Ordering and sequencing

Identify-the-error

Best-response and worst-response

Scenario and branching decision

Short constructed response

Operational calculation

File or evidence submission

Observed practical task with rubric

## 8.3 Question contract

| Field group | Required content |
| --- | --- |
| Identity | Question ID, bank, version, language and status |
| Traceability | Knowledge IDs, competencies, module and learning objective |
| Delivery | Format, stem, media, options, randomisation and time expectation |
| Scoring | Correct response, points, partial credit, critical flag and negative-scoring rule |
| Pedagogy | Difficulty, cognitive level, rationale and distractor explanations |
| Governance | Author, reviewers, approval, use history and retirement reason |
| Integrity | Exposure controls, similarity group and permitted feedback timing |

## 8.4 Assembly and retake rules

Every assessment blueprint sets minimum coverage by competency, criticality, format and difficulty.

Questions and answer order are randomised where appropriate.

Equivalent forms draw from a bank materially larger than one examination.

A retake creates a fresh immutable Attempt and normally avoids recently seen items.

Unlimited retakes are allowed, but policy may require a study interval or targeted remediation.

Written and practical responses enter a blinded or separated review workflow where feasible.

Result calculation is deterministic and reproducible from the saved assessment snapshot.

## 8.5 Difficulty standard

High difficulty means applied judgment under realistic constraints, not obscure wording. CEO and leadership assessments must test conflicting priorities, incomplete information, authority boundaries, escalation, reputational risk and the difference between advice and decision authority.

# 9. Certification and operational authorisation

## 9.1 Separate records

| Record | Question answered |
| --- | --- |
| Employment / organisational role | What position does the person hold? |
| Enrolment | What learning must they complete? |
| Competency evidence | What can they demonstrably do? |
| Certificate | For which role and period has Maison Doclar certified them? |
| Event assignment | What are they scheduled to do? |
| Operational authorisation | May they perform that duty at this event now? |

## 9.2 Default recertification policy

| Requirement | Default cycle |
| --- | --- |
| Core Maison Doclar standard | 12 months |
| Role-specific operations | 12 months |
| CEO / Event Director | 12 months |
| Privacy, security and confidentiality | 12 months |
| Access control and credentials | 12 months |
| Emergency and incident procedures | 6 months |
| FaceGate / biometric handling | 6 months |
| High-risk safety or technical duties | 6 months |
| Event-specific readiness | Before every assigned event |
| Materially changed knowledge | Targeted reassessment after publication |

Cycles are policy-controlled by jurisdiction, client, capability and risk. The shortest applicable cycle wins.

## 9.3 Monitoring and intervention

Reminder at 60, 30, 14 and 7 days before expiry

Notification on expiry

Manager escalation while an expired person remains assigned

Immediate readiness recalculation after failure, suspension or material content change

Targeted retraining after incidents or demonstrated performance gaps

Certificate verification by stable public-safe reference without exposing private results

# 10. Event-specific training

## 10.1 Event Training Package

MD-EOS publishes an approved, immutable Event Training Package version. The Academy creates an event learning space, calculates role-specific assignments and returns readiness. Draft OS data is never automatically teachable.

| Package domain | Examples |
| --- | --- |
| Identity | Event ID, client-safe title, date, timezone and venue |
| Operating intent | Experience promise, event objectives and applicable standards |
| People and responsibility | Team structure, assignments, escalation routes and role cards |
| Execution | Approved run of show, arrival, access, seating, wayfinding and communication procedures |
| Risk | Known hazards, contingency actions, emergency and incident procedures |
| Learning controls | Required acknowledgements, assessment rules, deadlines and affected roles |
| Governance | Package version, approval, publication time, sensitivity and supersession |

## 10.2 Data minimisation

The package normally contains categories, procedures and anonymised scenarios rather than the guest database. Named guest data is included only for authorised roles with genuine operational need. Biometrics, confidential notes and unrestricted guest intelligence remain in MD-EOS.

## 10.3 Material event changes

MD-EOS approves and publishes a new package version.

The Academy compares versions and identifies affected roles, lessons and people.

Affected readiness changes to Pending; unaffected competence remains valid.

The Academy assigns a change briefing, acknowledgement or reassessment according to impact.

Completion restores readiness and is returned to MD-EOS.

Both versions and all acknowledgements remain auditable.

# 11. OS–Academy integration

## 11.1 Integration principles

Versioned contracts

Authenticated service principals

Idempotent commands

At-least-once delivery with duplicate safety

Durable outbox and inbox records

Correlation and causation IDs

Retry with dead-letter handling

Periodic reconciliation

Minimum necessary payloads

No shared database

## 11.2 Canonical flows

| Flow | System of record | Result |
| --- | --- | --- |
| Person / organisation synchronisation | Identity / MD-EOS | Durable learner identity and membership |
| Role and event assignment | MD-EOS | Role-gap analysis and enrolment update |
| Event Training Package publication | MD-EOS | Versioned event learning space |
| Readiness status return | Academy | MD-EOS assignment warning or block |
| Certificate status return | Academy | Current general competence visibility |
| Event change notification | MD-EOS | Impact analysis and targeted reassignment |
| Incident learning referral | MD-EOS | Draft curriculum-change candidate, never auto-publication |

## 11.3 Failure behaviour

FAIL SAFELY If current readiness cannot be verified for a controlled duty, MD-EOS shows Verification unavailable and applies the configured warning or assignment block. It must not silently treat an old success as current.

A reconciliation job compares identities, assignments, package versions, certificate summaries and readiness responses. Differences become visible operational exceptions with owners and retry controls.

# 12. Canonical data model

## 12.1 Principal entities

| Domain | Entities |
| --- | --- |
| Identity | Organisation, Person, Membership, Department, Role, Permission Grant |
| Knowledge | Source Document, Source Version, Knowledge Item, Applicability Rule, Knowledge Relationship |
| Curriculum | Programme, Course, Module, Lesson, Activity, Learning Objective, Prerequisite |
| Competence | Competency, Competency Requirement, Role Profile, Equivalence Rule |
| Learning | Learning Path, Path Version, Enrolment, Assignment, Progress Event, Remediation Plan |
| Assessment | Question Bank, Question Version, Option, Rubric, Assessment Blueprint, Form, Attempt, Response, Mark, Review |
| Certification | Certificate, Certificate Scope, Renewal Requirement, Suspension, Revocation |
| Events | External Event Reference, Event Training Package, Package Version, Event Learning Space, Briefing, Acknowledgement, Event Readiness |
| Governance | Approval, Decision, Exception, Evidence, Audit Event, Notification, Integration Message |

## 12.2 Common record contract

UUID primary key and human-readable stable code where useful

Organisation scope on every tenant-owned record

Created, updated and effective timestamps in UTC

Created by and updated by actor

Version and lifecycle state

Classification and retention class

Source / correlation metadata

Soft retirement or supersession for governed records

Optimistic concurrency token

Audit event for material changes

## 12.3 Attempt immutability

An assessment attempt stores a snapshot of the assessment form, question versions, option order, scoring policy, timing, learner context and applicable critical rules. Later edits to a bank cannot change an existing result.

## 12.4 Multi-role readiness

Readiness is calculated separately for each person, event, assigned role and package version. A person can be Certified as Concierge, Renewal Due as Protocol Lead and Not Authorised as Event Director simultaneously.

# 13. Complete frontend architecture

## 13.1 Product surfaces

| Surface | Primary users | Purpose |
| --- | --- | --- |
| Learner Home | All learners | Next action, progress, deadlines, certificates and event readiness |
| Learning Player | Learners | Focused, resumable lesson and practice experience |
| Assessment Runner | Learners | Secure, accessible, interruption-safe controlled attempt |
| Event Briefing | Assigned teams | Role-specific event facts, changes, acknowledgement and readiness |
| Manager Workspace | Managers / leads | Team readiness, gaps, assignment and intervention |
| Assessor Workspace | Assessors | Schedules, rubrics, evidence capture, moderation and sign-off |
| Authoring Studio | Authors / reviewers | Knowledge, course and question production with traceability |
| Certification Console | Authorities | Issue, renew, suspend, revoke and audit |
| CEO Academy | CEO | Enterprise readiness, weak areas, reserved approvals and governance |
| Administration | Administrators | Configuration, users, integrations, support and audit |

## 13.2 Learner Home

One dominant Continue learning action

Required learning grouped by urgency and purpose

Event assignments clearly separated from permanent certification

Exact progress and estimated remaining effort

Certificate scope, validity and renewal date

Plain-language blocked state with the action needed

Recent feedback and remediation without exposing correct answers prematurely

Offline / poor-connection status where supported

## 13.3 Learning Player

Use short sections, persistent progress, visible objectives, transcripts, captions, adjustable playback, keyboard support and a mobile reading width. Navigation must preserve location and never lose completed work after connection interruption. Formative checks explain reasoning after submission.

## 13.4 Assessment Runner

Pre-flight screen showing rules, time, connectivity and accommodations

Server-authoritative attempt start and expiry

Autosave each response with visible saved state

Question navigator showing answered, flagged and incomplete items without revealing correctness

Graceful reconnect and resumable policy

Explicit submit review

Accessible keyboard and screen-reader behaviour

No accidental navigation loss

Results page showing outcome, competency feedback and next step

## 13.5 Event Briefing

The mobile event view prioritises what changed, what this person must do, who owns escalation and what must be acknowledged. It does not present the full OS. Sensitive content is redacted by role and cannot be inferred from counts or labels.

## 13.6 Manager Workspace

Readiness by event, role, department and person

People blocking coverage and the exact missing requirement

Role-change gap analysis and proposed enrolment

Expiry horizon and staffing exposure

Targeted reminders and interventions

No access to private assessment content beyond legitimate management need

## 13.7 Authoring Studio

Authors work in structured fields with source traceability beside the content. The interface must support draft preview by learner role, compare versions, show downstream impact, run coverage checks and route content through review without requiring code changes.

## 13.8 CEO Academy

Organisation-wide certification coverage

Event readiness and uncovered controlled roles

Critical competency weakness

Repeated assessment failure by topic, not public learner shaming

Content changes awaiting reserved approval

High-risk exceptions and expiring waivers

Incidents linked to possible training gaps

Academy production and integration health

## 13.9 Shared UX laws

Mobile-first for learner and event-day surfaces

Desktop-optimised but responsive authoring and analytics

WCAG 2.2 AA target

Inter or equivalent modern sans serif

Maison Doclar obsidian, ivory and restrained gold visual system

No colour-only status meaning

Every action has loading, empty, error, stale, denied and success states

Destructive or authority-bearing actions require clear confirmation and consequence

# 14. Intelligence, reporting and alerts

## 14.1 Deterministic intelligence first

| Signal | Example |
| --- | --- |
| Coverage gap | No event-assigned Check-in Lead has current access-control certification |
| Expiry exposure | Three staff certificates expire before the event date |
| Competency weakness | Protocol conflict questions fail materially above the bank baseline |
| Content quality | A question produces abnormal option selection or assessor disagreement |
| Operational correlation | Repeated service-recovery incidents involve the same unmastered competency |
| Integration exception | MD-EOS assignment version exceeds the Academy package version |
| Governance exception | Published module has superseded critical knowledge without reassignment |

## 14.2 AI boundary

AI may help draft summaries, suggest questions, cluster free-text feedback and identify possible gaps. Every output is labelled, grounded in approved content, reviewed by an authorised human and excluded from certificate issuance unless converted into an approved deterministic rule or human decision. AI does not invent answers, determine subjective practical competence or override critical failures.

## 14.3 Reporting safeguards

Minimum cohort thresholds before comparative reporting

No unnecessary ranking of individual learners

Confidence and sample-size display

Separate learning difficulty from bad question quality

Role and opportunity context before performance conclusions

Restricted access to written responses and assessor notes

# 15. Content governance and versioning

## 15.1 Lifecycle

| State | Permitted meaning |
| --- | --- |
| Draft | Editable working content; never assignable |
| In review | Locked for review; findings recorded |
| Approved | Approved but not yet effective |
| Published | Effective and assignable |
| Superseded | Historic; replaced by a newer version |
| Retired | No longer used; retained for audit |

## 15.2 Material change test

A change is material when it alters required behaviour, authority, safety, privacy, scoring, correct answers, certification validity or event-readiness logic. Material changes require impact analysis, fresh approval, a new version and a reassignment decision.

## 15.3 Publication gate

Source traceability complete

Learning objectives covered

Role and geographic applicability confirmed

Criticality reviewed

Accessibility checks passed

Assessment coverage sufficient

Answers and rubrics independently reviewed

Privacy classification complete

Impact and reassignment decision recorded

Author and approver separation satisfied

# 16. Security, privacy and assessment integrity

## 16.1 Data classification

| Class | Examples | Default handling |
| --- | --- | --- |
| Internal | General doctrine and ordinary course material | Authenticated organisation access |
| Restricted | Assessment banks, learner results and event briefings | Role-scoped access, audit and protected export |
| Highly restricted | Biometric training, safeguarding records, high-status guest procedures | Explicit grant, minimal display, strong audit and short retention where lawful |

## 16.2 Security controls

Single sign-on and MFA for privileged roles

Server-side tenant and resource authorisation

Encryption in transit and at rest

Secret management outside source control

Rate limiting and bot protection

Immutable audit trail for results and approvals

Secure file scanning and signed download access

Session revocation and device-aware controls

Backups with tested restoration

Dependency and vulnerability management

## 16.3 Assessment integrity

Bank access separate from ordinary administration

No correct-answer payload before permitted feedback

Attempt-specific form snapshots

Randomisation and exposure monitoring

Time and submission controlled on the server

Suspicious-event logging with human review

No automatic allegation or punishment from telemetry alone

Accommodation support without weakening learning outcomes

## 16.4 Privacy rules

Collect only data needed for learning, competence and governance. Define retention by record class and jurisdiction. Subject-access, correction and deletion workflows must preserve legally necessary audit records while removing unnecessary personal content. Staff analytics must not become covert surveillance.

# 17. Reliability and operations

## 17.1 Service objectives

| Capability | Production expectation |
| --- | --- |
| Learning and progress | No acknowledged completion lost |
| Assessment | Every saved response durable; result reproducible |
| Certificate verification | Available during staffing and event-readiness decisions |
| Event package ingestion | Retryable, idempotent and reconcilable |
| Readiness return | Freshness visible; stale status never presented as current |
| Audit | Material action captured with actor, time, scope and correlation |

## 17.2 Observability

Structured logs with correlation IDs

Metrics for latency, failure, queue depth and stale integrations

Traces across API, job and message processing

Business-control metrics for enrolment, attempt and certificate transitions

Privacy-safe alert payloads

Runbooks for assessment outage, package failure, certificate mismatch and data restoration

## 17.3 Offline and low-connectivity posture

Learning content may support controlled offline caching where security permits. High-stakes assessment requires a policy-defined connection mode; interrupted attempts preserve server-confirmed answers and provide explicit recovery. Event briefings should support a safe pre-cached role view without exposing newly revoked content indefinitely.

# 18. Technical stack and repository structure

## 18.1 Recommended stack

| Layer | Recommendation |
| --- | --- |
| Web application | Next.js App Router with TypeScript |
| Design system | Tailwind CSS plus accessible headless components and Maison Doclar tokens |
| Application API | Typed server modules with versioned REST contracts for external integration |
| Database | PostgreSQL with migrations and row-aware tenant enforcement |
| Background work | Durable job queue for packages, notifications, exports and reconciliation |
| Object storage | Cloudflare R2 or equivalent for protected learning and evidence artefacts |
| Authentication | Shared identity provider with MFA and service principals |
| Observability | Structured logs, metrics, tracing and error monitoring |
| Testing | Unit, contract, integration, accessibility, visual and browser end-to-end tests |
| Deployment | Independent staging and production pipelines with controlled migrations and rollback |

## 18.2 Repository shape

| Path | Responsibility |
| --- | --- |
| apps/academy-web | Learner, manager, author, assessor and CEO interfaces |
| packages/domain | Entities, policies, state machines and scoring rules |
| packages/ui | Design tokens and accessible shared components |
| packages/contracts | External API and event schemas |
| packages/content | Versioned seed knowledge and curriculum manifests |
| packages/testing | Factories, reference events and acceptance helpers |
| workers | Notifications, integration, reconciliation and reporting jobs |
| db | Schema, migrations, policies and seed controls |
| docs | Architecture decisions, runbooks and generated contract references |

## 18.3 Hardcoded versus managed content

Only constitutional system laws, state machines, permission vocabulary, contract schemas and safe defaults belong in code. The 30-module knowledge base, learning paths, questions, thresholds that policy may change, notification schedules and event training content are versioned managed data with controlled seed packages—not scattered conditionals.

# 19. Production build sequence

The Academy should be built in complete vertical slices. Each slice includes backend, frontend, permissions, audit, automated tests, browser validation and evidence.

| Slice | Production outcome |
| --- | --- |
| 1. Platform foundation | Repository, identity, organisation, roles, permissions, audit, design system and deployment |
| 2. Knowledge foundation | Source documents, Knowledge Items, module structure, search and governance states |
| 3. Curriculum delivery | Courses, lessons, activities, prerequisites, learner home and learning player |
| 4. Competencies and paths | Role profiles, learning paths, enrolment, gap analysis and manager assignment |
| 5. Question-bank studio | Question types, answers, rubrics, traceability, review and exposure controls |
| 6. Assessment engine | Blueprints, forms, attempts, autosave, marking, feedback and retakes |
| 7. Practical assessment | Schedules, evidence, rubrics, moderation and competence decisions |
| 8. Certification | Issuance, scope, renewal, expiry, suspension, revocation and verification |
| 9. OS integration | Identity, assignments, Event Training Packages, readiness return and reconciliation |
| 10. Event-specific Academy | Event spaces, change briefings, acknowledgements and event assessments |
| 11. Intelligence and governance | CEO/manager dashboards, alerts, analytics, content impact and incident learning |
| 12. Whole-system release | Full knowledge and question-bank load, security, performance, accessibility, recovery and production gates |

## 19.1 Slice completion rule

NO PARTIAL ACCEPTANCE A slice is complete only when its full user journeys work responsively, access is enforced server-side, data persists, audit is present, tests pass, browser evidence exists and no unrecorded blocker remains.

# 20. Acceptance and release gates

| Gate | Required proof |
| --- | --- |
| G0 — Blueprint | CEO ratification, settled decisions and traceability |
| G1 — Architecture | Boundaries, tenancy, state machines, integration and migration review |
| G2 — Content | Thirty-module coverage, provenance, accuracy and publication governance |
| G3 — Assessment | Coverage, difficulty, scoring, critical rules, reliability and integrity |
| G4 — Experience | Mobile, desktop, accessibility, interruption and role-based usability |
| G5 — Operations | Security, privacy, observability, backup, restore, support and incident readiness |
| G6 — Production | Exact candidate reconciled, evidence accepted, blockers closed and CEO authorisation recorded |

## 20.1 Minimum whole-system scenarios

CEO completes the entire path, passes a difficult assessment and receives a correctly scoped certificate.

A learner scores above 80% but fails a critical privacy question and is correctly denied certification.

A Concierge is promoted to Lead; valid competence is credited and only the leadership gap is assigned.

An Usher moves to Check-in; shared competence is retained and access-control learning is assigned.

MD-EOS publishes an event package; assigned staff receive role-specific training and readiness returns.

A material run-of-show change reopens only affected readiness and preserves the audit trail.

An expired certificate blocks a controlled event assignment.

An integration outage fails safely and reconciliation restores consistent state.

A curriculum rule changes; affected questions, paths, certificates and learners are identified before publication.

A production incident produces a governed learning candidate but cannot auto-edit published doctrine.

## 20.2 Definition of done

Production release requires accepted evidence for every gate, no open critical defect, no unresolved high-risk authority conflict, tested rollback, operational ownership, accurate documentation and a CEO decision bound to the exact release candidate and scope.

# Appendix A — Canonical status models

## A1. Enrolment and certification

Not enrolled → Enrolled → Learning in progress → Assessment eligible → Assessment in progress → Retake required or Knowledge passed → Practical pending → Certified → Renewal due → Expired. Suspension, revocation and supersession may occur from governed states.

## A2. Content

Draft → In review → Approved → Published → Superseded or Retired. Rejection returns a new draft revision; it does not mutate reviewed evidence.

## A3. Event readiness

Not required → Assigned → Training pending → Assessment pending → Practical pending → Ready. Material change, expiry, suspension, failure or stale verification may move readiness to Pending, Blocked or Revoked.

## A4. Assessment attempt

Created → Started → In progress → Submitted → Auto-marked → Manual review, when required → Finalised → Released. A timed-out or interrupted attempt follows explicit policy and is never silently scored as complete.

# Appendix B — Core API contracts

| Contract | Minimum fields |
| --- | --- |
| EventTrainingPackagePublished | message_id, event_id, organisation_id, package_version, approved_at, effective_at, scope, assignments, content domains, classification, checksum |
| EventAssignmentChanged | message_id, event_id, person_id, role_id, assignment_version, effective_at, reason |
| LearnerReadinessChanged | message_id, person_id, event_id, role_id, package_version, readiness_state, missing_requirements, calculated_at, valid_until |
| CertificateStatusChanged | message_id, person_id, certificate_id, role_scope, status, issued_at, expires_at, reason |
| ReconciliationSnapshot | system, organisation_id, cursor, entity summaries, generated_at, checksum |

All contracts include schema version, idempotency key, correlation ID, producer, occurred-at timestamp and signature or authenticated transport context.

# Appendix C — Traceability and definition of done

| Deliverable relationship | Blueprint commitment |
| --- | --- |
| 30-Module Competency Map | Every approved Knowledge Item maps to competencies, roles and evidence |
| Role and Learning-Path Matrix | Every controlled role has explicit requirements and equivalence rules |
| Curriculum Specification | Every course and lesson implements this hierarchy and governance lifecycle |
| Question Bank | Every scored item traces to approved knowledge and a competency |
| Certification Framework | Every certificate implements the separate-state and critical-failure laws |
| Implementation Specifications | Every slice preserves frontend parity, security, audit and acceptance |
| Independent Acceptance Pack | Every canonical law receives at least one verifiable test |
| Academy Governance Register | Every unresolved decision, exception, defect, risk and release is controlled |

## C1. Blueprint closure record

| Decision | Status |
| --- | --- |
| Separate Academy repository and database | Adopted |
| Shared identity with bounded service integration | Adopted |
| OS owns event truth; Academy owns competence truth | Adopted |
| 80% pass; 90% distinction; critical failures override total | Adopted |
| Unlimited governed retakes | Adopted |
| Annual default certification; six-month high-risk cycle | Adopted |
| Event-specific readiness before each assigned event | Adopted |
| Vertical and horizontal role-gap re-enrolment | Adopted |
| Full 30-module knowledge base and populated question bank are production deliverables | Adopted |
| Frontend receives equal acceptance weight to backend | Adopted |

RATIFICATION DECISION Approve this document as the canonical build authority for Maison Doclar Academy, subject only to recorded amendments.