MAISON DOCLAR

# Staffing, Zoning and Deployment Method

A consequence- and flow-based method rather than a single guest ratio

| Control | Value |
| --- | --- |
| Document ID | MD-USH-DEP-004 |
| Version | 1.0 |
| Status | DRAFT FOR CEO RATIFICATION |
| Doctrine | Every Guest, Considered. |
| Prepared | 04 September 2026 |

Authority: This document becomes Maison Doclar authority only after CEO ratification. Legal, radio-spectrum, equipment type approval, medical, security, accessibility, cultural and protocol determinations remain subject to the named competent authority. Vendor specifications are claims until verified.

# Contents

1. Staffing formula

2. Inputs

3. Calculation worksheet

4. Zone design rules

5. Validation drills

# 1. Staffing formula

Formula: Total deployed = fixed posts + arrival-flow positions + seating escorts + in-zone observation + transition positions + specialists assigned to FOH + break relief + contingency reserve. Never reduce the calculation to one usher per X guests.

# 2. Inputs

| Input | Measure | Why it matters |
| --- | --- | --- |
| Arrival curve | Expected arrivals per 5/15 minutes | Drives frontage, check and escort throughput |
| Entrances/checkpoints | Count and service time | Creates fixed minimum |
| Walking/escort time | Route minutes including return | Limits escorts per usher |
| Decision points | Doors, stairs, junctions, lifts | Requires fixed wayfinding posts |
| Seating complexity | Assigned/open, households, VIP, protocol | Changes verification and conflict load |
| Accessibility | Known/expected assistance and step-free routes | Requires time and trained capacity |
| Transitions | Number, simultaneity and direction | Creates temporary peak staffing |
| Venue geometry | Floors, rooms, external paths, noise | Affects zones and communication |
| Exception rate | Invites, late changes, missing names, disputes | Sizes exception desk and floats |
| Service tier | Acknowledgement and contact targets | Determines coverage density |
| Breaks | Shift length, heat, uniform and post criticality | Requires planned relief |
| Contingency | Absence, device failure, congestion | Minimum reserve |

# 3. Calculation worksheet

| Component | Calculation | Planned | Validated |
| --- | --- | --- | --- |
| Fixed posts | One per critical post for every open interval |  |  |
| Arrival processing | Peak arrivals ÷ verified throughput per position |  |  |
| Escorts | Peak escorts × round-trip minutes ÷ interval |  |  |
| Zone rovers | Area/density/service model validated by walk |  |  |
| Transitions | Route control + sending + receiving posts |  |  |
| Relief | Break schedule plus one-for-one critical post cover |  |  |
| Reserve | Risk-based minimum; recommended start 10–15% |  |  |

# 4. Zone design rules

Zones follow physical visibility, route and authority—not decorative floor-plan shapes.

Every zone has one supervisor, bounded table/seat ranges, entrances/exits, critical posts, accessible routes, specialist contacts, relief point and fallback communications.

Avoid boundaries through high-conflict tables, door pairs or shared VIP spaces unless one supervisor clearly owns the interface.

Colour is supplemented with letter/symbol so colour vision is not the only cue.

A zone map shows walking times and dead areas, not only tables.

# 5. Validation drills

Peak arrival simulation with realistic invitation exceptions.

Five simultaneous escorts and one accessible route request.

Seat conflict during doors-open peak.

Radio failure and runner fallback.

Late VIP arrival during programme transition.

Medical call while the zone supervisor is occupied.

Break relief and unplanned absence.

# Detailed controlled operating annex

This annex expands the governing requirements into operational design, verification and evidence. It is normative only after ratification with the parent document.

## Arrival throughput study

Before fixing staffing, measure or simulate the time to welcome, verify, resolve exceptions and escort. Use peak five- and fifteen-minute arrival forecasts rather than event total.

Required practice. Calculate each bottleneck separately and add relief for variability. A single slow exception desk can defeat a generous usher ratio.

Acceptance evidence. After the pilot, replace assumptions with observed service-time distributions and record venue/event-type applicability.

## Fixed post inventory

Walk the guest journey and record every location where absence would create wrong entry, unsafe movement, inaccessible routing, lost guests or protocol exposure.

Required practice. Each post has purpose, operating interval, sightline, relief, fallback and closure authority. Combine posts only when one person can perform both functions under peak conditions.

Acceptance evidence. A decorative welcome position is not counted as a control post unless it has a defined function.

## Escort capacity

Estimate the proportion requiring escort, round-trip time and concurrency. Long routes, lifts and household movement sharply reduce capacity.

Required practice. Use receiving handoffs so escorts can return efficiently without abandoning guests.

Acceptance evidence. When escort queue exceeds the defined threshold, supervisors deploy floats or change to an approved staged guidance model.

## Relief engineering

Break cover is designed with the roster, not negotiated during the event. Critical posts receive one-for-one trained relief; rovers may be pooled only when zone coverage remains adequate.

Required practice. Record actual leave and return. A delayed return triggers supervisor action before the post becomes uncovered.

Acceptance evidence. Reserve staff are protected from routine early assignment unless command accepts the resulting contingency reduction.

## Competence matching

Headcount is not capacity. Assign roles based on current Academy authorisation, language, mobility, experience, briefing completion and event-specific restrictions.

Required practice. A newly trained usher should not be placed alone at the highest-consequence exception or protocol post.

Acceptance evidence. The deployment record explains any exception and the additional supervision applied.