MAISON DOCLAR

Intelligence
Specification

Canonical operating knowledge, standards, data, decisions and intelligence architecture — Final Versioned Draft v1.0

CURRENT RELEASE Version 1.0 — Final Versioned Draft Modules 1–30 and post-capstone Sections 142–144 are integrated into one canonical operating specification. The knowledge design is complete; production authority remains subject to the release gates and external validations stated in this document.

Purpose

To convert Maison Doclar’s executive knowledge modules into a coherent, inspectable and machine-applicable operating intelligence system. This document is cumulative: each module may add, refine, supersede or challenge what came before.

| Document control | Value |
| --- | --- |
| Owner | CEO, Maison Doclar |
| Status | Final versioned draft — module sequence and reconciliation complete; approved knowledge may proceed to implementation planning, subject to the release gates and external validations stated in this document. |
| Source coverage | Modules 1 through 30, plus three CEO-supplied gap-closing documents (staffing policy, protocol register, AI shadow-mode evaluation plan) integrated at Sections 142–144 |
| Knowledge cutoff | Modules 1–30 plus the post-capstone staffing, Nigerian protocol and AI shadow-mode gap-closing documents supplied by the CEO. |
| Exclusion applied | No new exclusions — the three gap-closing documents contained no CEO exercises |
| Final review finding | The knowledge architecture is complete enough for implementation design. It is not yet production-authorised: provisional legal/protocol items require their stated verification, and no live AI protocol recommendation may be used until the shadow-mode release gate passes. |
| Next action | Move from specification to controlled implementation: approve the v1.0 knowledge baseline; complete counsel/protocol validations; build core records and workflows; populate one synthetic reference event; run tabletop and shadow-mode evaluations; then authorise a tightly controlled pilot event. |

FINAL REVIEW CONCLUSION The 30-module knowledge system is substantively coherent and implementation-ready as a controlled design baseline. It is not yet a claim of legal compliance, verified protocol correctness for a specific event, trained organisational capability or production-safe AI.

This finalisation layer resolves the packaging weaknesses of the incremental draft: it states the release truth, supplies a usable map through the 144-section specification, distinguishes design completion from operating readiness and consolidates the implementation gates that must remain visible to the CEO.

## Final release truth

| Dimension | Final v1.0 position |
| --- | --- |
| Knowledge coverage | All 30 CEO modules are incorporated; overlaps are reconciled into canonical models rather than implemented as parallel systems. |
| Traceability | Module contributions, decisions, exclusions, gaps and later resolutions remain visible in the module sections and change register. |
| Doctrine / standards | The Maison Doclar philosophy, rules, standards, SOP concept and assurance contracts are sufficiently defined for repository encoding. |
| Data / intelligence | Entities, provenance, freshness, sensitivity, confidence, recommendation and verified-outcome contracts are defined at specification level. |
| Human authority | CEO, Event Director, domain, specialist and AI boundaries are explicit; high-impact judgement remains human. |
| External validity | Employment, privacy, safety, medical, security, fire, food, crowd, technical and protocol claims still require the qualified/event-specific verification stated in their sections. |
| AI readiness | Architecture is complete; production use is blocked until the shadow-mode harness and acceptance criteria in Section 144 pass. |
| Operational evidence | No live Maison Doclar production event has yet validated thresholds, staffing ratios, alerting, workflows or model performance. |

## How to navigate the specification

| Operating domain | Primary sections |
| --- | --- |
| Foundation, architecture, data, roles and decisions | 1–12 |
| Guest journey and friction | 13–15 |
| Protocol and Nigerian precedence | 16–20, 138, 143 |
| Cultural, religious and international-guest intelligence | 21–27 |
| VIP/HNW intelligence and ownership | 28–36 |
| Event command, live intelligence and risk | 37–46, 71–89, 119, 125–134, 144 |
| Vendors, suppliers and quality control | 47–53, 99–107, 124 |
| Ceremony and run-of-show | 54–61 |
| White-glove service and standards assurance | 62–70, 135–139 |
| Operating system, Master Event File and knowledge base | 90–98, 123 |
| Staffing, culture, deployment and policy | 99–107, 124, 142 |
| Communication, concierge and host management | 108–118, 140 |
| Security, safety, privacy and safeguarding | 120–122, 137 |
| Capstone standard, CEO charter and release declaration | 141 |
| Reusable extraction and module traceability | Appendices A–B |

## Canonical system spine

| Layer | What the app must make possible |
| --- | --- |
| Know | Versioned doctrine, standards, rules, context packs, cases, SOPs and authority boundaries |
| Plan | Master Event File, journeys, requirements, owners, dependencies, risks, standards and contingencies |
| Assure | Evidence-based readiness gates, exceptions, rehearsals, specialist approvals and Event Readiness Declaration |
| Observe | Sourced live signals with event time, freshness, confidence, sensitivity and conflicting-report treatment |
| Interpret | Rules and bounded AI turn facts into risks, assertions, forecasts and options without inventing certainty |
| Decide | The correct human sees evidence, consequences, alternatives, deadline and reserved authority |
| Execute | Role-scoped tasks/instructions use acknowledgement, accepted handoff and change/version control |
| Verify | Real-world outcome and receiving-stage evidence prove whether the action or standard was achieved |
| Learn | After-action evidence proposes lessons; approval promotes them into reusable knowledge without contaminating clients/events |

## Implementation release gates

| Gate | Required evidence before progression |
| --- | --- |
| G0 — Baseline approval | CEO approves v1.0 knowledge states, canonical terms, reserved decisions and rejected/superseded items. |
| G1 — External validation | Qualified owners sign off applicable legal, privacy, employment, safety, security, medical, food, crowd, technical and event-specific protocol content. |
| G2 — Core system build | Identity/access/audit, knowledge registry, Master Event File, people/guest, journey, standards, tasks, decisions, risks/incidents, documents/versions and outcome records operate end to end. |
| G3 — Reference-event validation | One synthetic event demonstrates applicability, ownership, readiness, change propagation, offline continuity, privacy boundaries and complete audit. |
| G4 — Human operating validation | Staff tabletop, cue-to-cue, service role-play, incident simulation and executive decision exercises pass with measured evidence. |
| G5 — AI shadow mode | Section 144 harness passes its binding criteria; AI remains non-commanding and every high-impact recommendation remains human-approved. |
| G6 — Controlled pilot | A low-complexity event receives explicit go-live approval, enhanced observation, rollback/continuity plans and post-event ground-truth review. |

## Non-negotiable final safeguards

- No module prose is hardcoded directly as an opaque algorithm; executable knowledge retains ID, source, version, status, applicability, evidence, authority and audit.

- No “complete”, “sent” or “Green” state proves a real-world result without the evidence required by that domain.

- No absence of data becomes a negative fact; Unknown and stale remain visible.

- No AI-generated protocol, precedence, seating or address recommendation reaches a live event before Section 144’s release gate passes.

- No global or Lagos context pack substitutes for event facts, current authoritative sources or qualified specialist judgement.

- No client, guest, VIP, staff or vendor knowledge crosses purpose/event/client boundaries without explicit governance and traceability.

- No attempt to preserve luxury or invisibility suppresses safety, safeguarding, mandatory reporting, truthful client communication or affected-person choice.

- The CEO owns the standard and reserved executive judgement; the operating system must prevent the CEO from becoming the routine workflow.

## Detailed navigation

Use the domain map above and Word’s Navigation Pane to browse the complete Heading 1/Heading 2 hierarchy. The numbered sections and appendices remain the stable citation system for this specification.

# 1. How this document works

**GOVERNING RULE The source modules remain evidence. This specification

records what Maison Doclar has decided the operating system should

know, collect, infer, recommend and control.**

The document has two connected views:

- Consolidated system specification — the current truth after reconciling all modules.

- Module extraction register — the traceable record of what each module contributed, modified, contradicted or left unresolved.

## 1.1 Knowledge states

| State | Meaning | System treatment |
| --- | --- | --- |
| Proposed | Extracted but not yet approved | May be discussed; must not drive production decisions |
| Approved | Accepted Maison Doclar knowledge | May be encoded and applied |
| Provisional | Usable with a recorded assumption | Apply with qualification and confidence |
| Superseded | Replaced by later approved knowledge | Retain for audit; do not apply |
| Rejected | Explicitly not adopted | Retain rationale; do not apply |

## 1.2 Change discipline

- No later module silently overwrites an earlier rule.

- Every modification identifies the affected knowledge item and reason.

- Contradictions remain visible until the CEO or delegated authority resolves them.

- Event outcomes may propose learning, but cannot autonomously change doctrine.

- Every executable rule retains its source, version, status, owner and approval history.

# 2. System knowledge architecture

| Layer | Contains | Primary home |
| --- | --- | --- |
| Doctrine | Stable philosophy and non-negotiable principles | Version-controlled repository |
| Decision knowledge | Rules, standards, thresholds, taxonomies and playbooks | Structured, versioned knowledge files |
| Configuration | Event type, service tier, locale and operational parameters | Controlled configuration |
| Event data | Facts about events, guests, venues and operations | Database |
| Derived intelligence | Risks, recommendations, tasks, alerts and explanations | Intelligence store / database |
| Outcomes and learning | What happened and whether advice worked | Outcome store with review workflow |

**SYSTEM EQUATION Knowledge + event data + context → intelligence →

human decision or authorised action**

## 2.1 Hardcoding boundary

Application code should hardcode the mechanism and invariants: rule evaluation, versioning, permissions, auditability and safety boundaries. Maison Doclar judgment should be represented in human-readable, machine-evaluable knowledge files. Event facts belong in the database.

# 3. Module 1 — canonical knowledge extraction

Source: “The Philosophy of White-Glove Hospitality.” Status: approved foundation, subject to the CEO decisions listed in Section 11.

## 3.1 Canonical doctrine

**DEFINITION White-glove hospitality is the disciplined art of

anticipating a guest’s needs, protecting their time, preserving their

dignity and creating an experience that feels effortless, personal and

exceptionally considered.**

- Luxury is controlled, considered and effortless; expense alone does not create it.

- The better the operation, the less operational it should feel to the guest.

- The guest should experience the result, not the machinery or struggle.

- Different protocol treatment must not create different levels of dignity.

- Information is used to improve the experience, never to display how much is known about a guest.

- Maison Doclar protects the host and guest from avoidable operational management.

## 3.2 Luxury experience model

| Class | Dimension | Meaning |
| --- | --- | --- |
| Guest-facing outcome | Quality | The service or provision is excellent |
| Guest-facing outcome | Consideration | Choices reflect thoughtful regard |
| Guest-facing outcome | Anticipation | Needs are prepared for before requests |
| Guest-facing outcome | Discretion | Privacy and dignity are protected |
| Guest-facing outcome | Effortlessness | The guest does not manage the experience |
| Operational enabler | Recognition | The guest is appropriately known and received |
| Operational enabler | Consistency | The standard survives difficult conditions |
| Operational enabler | Control | Competent ownership is quietly evident |

## 3.3 Psychological outcomes

| Outcome | Intended perception |
| --- | --- |
| Recognition | We know who you are |
| Relevance | This has been considered for you |
| Respect | Your position and preferences matter |
| Ease | You do not have to struggle |
| Privacy | You are safe and protected |

## 3.4 Anticipation levels

| Level | Pattern | Interpretation |
| --- | --- | --- |
| 1 — Reactive | Guest asks → team responds | Service recovery; below target |
| 2 — Proactive | Team notices → team responds | Good awareness |
| 3 — Anticipatory | Team predicts → team prepares | Target where material, foreseeable, lawful and proportionate |

## 3.5 Five-layer experience model

| Layer | Question | Evidence examples |
| --- | --- | --- |
| Function | Does it work? | Vehicle, seat, meal and route exist |
| Comfort | Is it physically comfortable? | Temperature, access, lighting and noise |
| Emotion | How does the guest feel? | Welcome, safety, confidence and respect |
| Personalisation | Was it considered for this person? | Preferences, relationships, protocol and culture |
| Memory | What remains afterwards? | Confidence, advocacy and positive recollection |

Interpretation: the layers are cumulative. Higher layers do not compensate for failure at a lower layer.

## 3.6 Complete guest-journey architecture

**JOURNEY DOCTRINE The guest does not experience departments. The guest

experiences one continuous journey that begins before arrival and may

continue after departure.**

| Concept | Canonical meaning | Required system treatment |
| --- | --- | --- |
| Journey | The complete end-to-end guest experience | Maintain one traceable journey per guest or journey segment |
| Stage | A meaningful phase with a distinct guest objective | Define entry, exit, owner, required state and measures |
| Touchpoint | An interaction between guest and experience | Record channel, content, owner, outcome and emotional intent |
| Transition | Movement or change between stages or states | Model handoff, trigger, destination, timing, dependencies and contingency |
| Moment | A material point within a stage or transition | Identify knowledge, emotion, friction and recovery needs |
| Emotional state | How the guest is intended or observed to feel | Treat as an evidenced or declared state, never an invented fact |

## 3.7 Journey equation and emotional choreography

JOURNEY EQUATION Experience = touchpoints + transitions + emotion

A successful touchpoint cannot compensate for a failed transition. Maison Doclar must therefore design both the visible interaction and the gap or handoff that follows it.

| Desired progression | Adverse progression to prevent |
| --- | --- |
| Curiosity → anticipation → assurance → welcome → comfort → belonging → enjoyment → connection → satisfaction → memory | Confusion → anxiety → waiting → embarrassment → frustration → disappointment |

## 3.8 Seven-question journey test

- What does the guest know?

- What does the guest not know?

- What could confuse the guest?

- What could embarrass the guest?

- What could delay the guest?

- What would make the guest feel important?

- What would make the guest feel neglected?

The test applies to every material stage, touchpoint and transition. Answers must distinguish verified facts, design intentions, plausible risks and unsupported assumptions.

# 4. Decisions supported by Module 1

- Where is guest friction likely to occur, and who will be affected?

- What material need can reasonably be anticipated before arrival?

- Which preparations should happen invisibly and which human interactions should remain visible?

- Where is personalisation useful, and where would it become intrusive?

- What should the guest know, and what should the guest never need to ask?

- Does every touchpoint and transition have competent ownership?

- Are function, comfort, emotion, personalisation and memory deliberately protected?

- Are protocol distinctions being delivered without reducing anyone’s dignity?

- Is the host insulated from operational management?

- Should an issue produce information, a recommendation, a task, an alert or an executive decision?

- Where does each guest journey begin and legitimately end for this event?

- Which stages can use a shared journey and which require a differentiated path?

- What information, action and emotional outcome must each touchpoint deliver?

- Which transition or handoff is most likely to fail even if adjacent touchpoints succeed?

- What should trigger movement to the next stage, and who confirms that the receiving stage is ready?

- Which questions should the guest never have to ask at each stage?

- What guest-facing promise is created by an invitation, confirmation or communication?

- Where must a contingency preserve continuity when an owner, supplier or dependency fails?

## 4.1 Decisions outside Module 1 authority

- Formal protocol precedence

- Security tactics

- Medical accommodations or diagnosis

- Legal compliance and retention periods

- Accessibility standards

- Cultural or religious treatment

- Supplier capacity certification

Module 1 may identify the relevance of these matters but specialist modules and authorised people must govern the decision.

# 5. Data required

| Entity | Minimum data domains |
| --- | --- |
| Event | Purpose; experience intent; date/time; locations; attendance; programme; scope; priorities; constraints; promised standard; sensitivities; deadlines; status |
| Guest | Preferred identity/address; RSVP; relationships; role; arrival/departure; transport; voluntarily provided access/diet needs; communication; language; seating; verified preferences; privacy; assigned liaison; source; verification; sensitivity; expiry; minor status and Responsible Adult reference where applicable (M14-D07) |
| Guest journey | Journey template/version; applicable segments; start/end boundary; stages; current state; deviations; completion status; overall owner |
| Stage | Guest objective; entry/exit criteria; planned and actual timing; knowledge state; intended emotion; needs; owner; measures; status |
| Venue | Access; routes; traffic exposure; checkpoints; parking; drop-off; accessible paths; distances; lifts/stairs; capacities; holding areas; toilets; climate; acoustics; visibility; connectivity; power; exits; vendor routes; constraints |
| Touchpoint | Stage; channel; planned time; content/action; owner; dependencies; guest-facing promise; intended emotion; completion evidence; result; current status |
| Transition | Origin/destination; trigger; handoff owner; receiving owner; readiness condition; expected duration; route; dependencies; contingency; actual outcome |
| Communication | Purpose; audience; channel; sender; content version; send time; delivery/read/response state; promise created; follow-up rule |
| Transport movement | Origin/destination; route; driver/vehicle; ETA; traffic; parking/access; contacts; notifications; contingency; live status |
| Protocol identity | Verified name; current office/title; honours/post-nominals; institution; jurisdiction; category; direct address; introduction form; pronunciation; source; verified by/at; expiry |
| Event protocol profile | Event authority/context; host; principal; highest relevant precedence guest; official/private status; palace/mission/office contacts; governing guidance; approvals |
| Precedence assessment | Office; formal rank; institution; host relationship; ceremonial role; authority source; context; proposed treatment; conflicts; approval |
| Seating assignment | Seat/table/zone; event function; adjacent guests; exclusions; sightline/access/security/media/diet needs; precedence rationale; version; approval; contingency |
| Ceremonial movement | Arrival order; receiving line; procession; introduction; speaking; presentation; photography; departure sequence; owner; cue; contingency |
| Protocol source | Issuing authority; jurisdiction; subject; effective/current date; version; evidence link/reference; verification contact; confidence; review date |
| Cultural context | People/institutions; community/place; ceremony/practice; meaning; cultural authority; source; locality; applicability; confidence; review date |
| Cultural requirement | Domain: language/greeting/dress/food/music/gender/age/religion/tradition/photography/symbol; requirement; affected guests; stage; owner; verifier; contingency |
| Cultural authority | Authority type; institution/community/family/faith; jurisdiction; designated person; mandate; contact; decision scope; availability; approval evidence |
| Ceremonial object | Name/local term; meaning; ownership/custody; authorised handlers; placement; timing; movement; photography; restrictions; return/accountability |
| Cultural group / household | Group identity; type; leader/spokesperson; members; arrival; seating; ceremonial role; attire identifiers; information visibility |
| Religious observance | Faith/tradition; applicable guests; prayer/fasting/calendar/timing/food/alcohol/modesty/gender/symbol requirements; authority; confirmation |
| Cultural briefing | Audience; language; purpose; essential guidance; do/avoid; confidence objective; delivery/acknowledgement; version; authority approval |
| VIP handling profile | Guest; event; handling reasons/dimensions; applicable journey variant; service intent; owner/deputy; status; review/expiry; approval |
| VIP intelligence item | Domain; value/instruction; source; verification; purpose; sensitivity level; permitted roles; validity; event-only/reusable status; consent/legal basis where required |
| VIP preference | Comfort/convenience/experience/personal/restricted level; preference versus requirement; source; confidence; discreet delivery method; do-not-disclose wording; expiry |
| VIP relationship requirement | Relevant person/group; requested interaction or separation; operational purpose; sensitivity; authority; stage; completion; expiry |
| VIP live state | Expected/actual stage; coarse operational location; owner; last confirmed time; next action; ETA/deadline; deviation; communication state |
| VIP incident/recovery | Issue; detection; guest impact; owner; immediate action; resolution; comfort restoration; disclosure; outcome; learning candidate |
| VIP intelligence access | User/role; field/record scope; purpose; grant/approver; start/expiry; access/export/share audit; revocation |
| Command structure | Event; command role; accountable person/deputy; authority scope; escalation limits; reporting line; availability; handover state |
| Master timeline item | Planned/actual time; event/action; owner; dependency; receiving readiness; status; variance; contingency; evidence; version |
| Operational document version | Document type; event; semantic/release version; owner; approved at/by; effective time; change summary; distribution; supersedes; withdrawal |
| Vendor command record | Vendor; contracted scope; lead/deputy; deliverables; deadlines; inputs; dependencies; readiness evidence; status; escalation; contingency; performance |
| Supplier organisation | Identity; ownership; category/specialisation; contacts; operating history; capacity; equipment; key personnel; licences/insurance where relevant; subcontracting; commercial position; review state; geographic coverage; pricing band; typical lead time; failure patterns; recovery ability (Module 18) |
| Supplier capability evidence | Capability claimed; scale/context; evidence/reference; assessor; verification date; limitations; expiry; confidence |
| Supplier relationship status | A strategic/B core/C specialist/D support class; preferred/conditional/suspended/do-not-use state; rationale; approval; review date |
| Supplier scorecard | Event/scope; quality; reliability; professionalism; responsiveness; guest impact; problem-solving; commercial discipline; value (added per M13-D01); communication; timeliness; flexibility (three fields added per M18-D01); scored /10 per field (standardised per M18-D01); weighted result; evidence; reviewer. Field set closed to further proposals absent a new CEO decision. |
| Vendor appointment | Event; required capability; candidates; due diligence; operational lead; availability; selection rationale; approvals; contract/readiness state |
| Vendor brief / acknowledgement | Experience intent; permitted guest/VIP view; aesthetic/service standard; timeline; venue; dependencies; non-negotiables; code; version; questions; acknowledgement |
| Scope of work | Deliverables/quantity; place; milestones (including mock-up/first-article gate, 49.2.1); acceptance standard/evidence; accountable people; dependencies; exclusions; price/payment tied to milestone chain with review-linked retention (49.2.3); change terms; contingency; version |
| Vendor access / check-in | Arrival gate/time; vehicle; roster/identification; equipment; parking/loading; zone; restrictions; check-in/out; security approval |
| Vendor inspection | Checkpoint; deliverable; appearance/function/cleanliness/safety/position/timing/staff/branding/guest impact/backup; evidence; defect; owner; acceptance |
| Commercial change | Request/source; scope/cost/time/quality/dependency impact; authority; decision; communications; implementation evidence; resulting version |
| Vendor failure / corrective action | Failure; affected capability/promise; containment; backup/replacement; recovery; evidence; contractual action; cause; corrective action; reapproval |
| Ceremony architecture | Event purpose/identity; principal(s); governing authority contexts; approved ceremony spine; control-sheet version; architect; approvals; status |
| Ceremonial moment | Moment/type; purpose/meaning; participants; required location/position; planned window/duration; entry/exit; prerequisites; owner; cue; next moment; flexibility class |
| Ceremonial person movement | Person/role; authority context; arrival window; receiver; route; holding; entrance; position/seat; speaking/presentation/photo/departure instructions; owner; privacy/access |
| Cue | Moment; trigger/source; GO/HOLD state; cue giver; recipient; action; prerequisites/readiness checks; acknowledgement; execution evidence; expiry/cancellation |
| Ceremony clock | Authoritative time source; synchronisation owner; offsets; last sync; drift/tolerance; fallback time source |
| Run-of-show item | Operational time/window; duration; action; location; responsible/backup; participants; cue; dependencies; next; status; actual timing; version |
| Cue-sheet item | Department/role; precise instruction; trigger; equipment/content; channel; acknowledgement; rehearsal/test; execution result |
| Holding area | Type; location; capacity; eligible people; access/privacy/security; comfort; route; host/liaison; readiness; release authority |
| Receiving line | Purpose; ordered participants; positions/spacing; arrival window; greeting duration; guest route; photography; exit route; flow threshold; owner |
| Speaker assignment | Speaker; confirmation; topic/purpose; approved introduction; pronunciation/title; slot/window; duration limit; holding; cue; microphone; exit; content/sensitivity restrictions |
| Ceremonial position | Stage/table/seat/standing position; person/role; governing hierarchy/context; rationale; sightline/access/mobility/photo/security constraints; approval/version |
| Photography group | Group/order; named participants; positions; assembly/holding; location; photographer/assistant; restriction; time limit; cue; release state |
| Programme item classification | Non-negotiable/flexible/removable; protected purpose; minimum/target/maximum duration; shortening/removal authority; affected dependencies |
| Transition / bridge | From/to moments; movement; route/location; duration; owner; cue; bridge option/content; readiness; fallback; guest-facing continuity |
| Ceremony variance / recovery | Delay/early state; cause; cascade impact; protected items; shorten/remove/resequence options; dignity/protocol effects; authority; decision; recovered time/outcome |
| Service standard | Stable ID/version; domain; requirement; rationale; applicability rule; mandatory/advisory status; prohibited behaviour; owner; evidence method; exception authority; training content; review date |
| Event standard plan | Event; applicable standard/version; applicability reason; planned control; zone/stage/touchpoint; accountable owner/deputy; verification checkpoint; evidence required; status; exception |
| Standard verification | Event standard; checkpoint/time; verifier; observed result; pass/fail/not-applicable/unknown; evidence; defect; corrective action; recheck; acceptance |
| Service zone | Zone/stage; operating hours; guest need; coverage position; service roles/count/capability; line of sight; response target; handoff/escalation; backup; readiness |
| Staff service assignment | Person/vendor; role; zone/shift; briefing version; training/role-play evidence; standards acknowledged; language/protocol/access permissions; supervisor; check-in/out; performance |
| Guest request | Guest/context; request/category; time/channel/location; initial owner; acknowledgement; priority; destination owner; promised update; resolution; guest confirmation; closure; privacy |
| Service observation | Observable signal; zone/time; possible need; confidence; non-intrusive action; guest consent/response; escalation; outcome; retention rule |
| Service interaction | Guest/touchpoint; greeting/recognition/orientation/escort/assistance action; title/name source; start/end; staff owner; outcome; friction or correction |
| Dining service plan | Service waves/rhythm; tables/owners; water/replenishment; dietary/allergy controls; VIP discretion; clearing; temperature/holding; escalation; acceptance evidence |
| Dietary service instruction | Guest/table; declared requirement or allergy; exact instruction; approved alternative; kitchen/service owners; verification; discreet delivery; incident/escalation; sensitivity/expiry |
| Restroom service check | Location; interval/trigger; cleanliness; tissue/soap/water/towels/waste/odour/floor/light; attendant; defect; corrective action; recheck; guest impact |
| Comfort condition | Zone/time; temperature/humidity/crowd/noise/sightline/seating/water signal; affected group; threshold/context; owner; intervention; outcome |
| Service recovery case | Issue; guest impact; listen/acknowledge/own/solve/follow-up states; owner; authority/spend; solution; guest confirmation; disclosure; evidence; learning |
| Lost property | Item/description; found location/time; finder; custodian; secure storage; possible/verified owner; contact; identity proof; handover; disposal/retention; audit |
| Staff competency | Behaviour/standard; training method; scenario; assessor; demonstrated/needs-coaching state; evidence; expiry/refresher; event qualification |
| Operational picture snapshot | Event/master time; current programme state; now/next/later; guest/VIP/vendor/protocol/production/security/transport/weather states; incidents; risks; pending decisions; source freshness; compiler |
| Command lens status | Lens/role; primary question; RAG/unknown; evidence; owner; last update/expiry; current issue; next action; dependency; escalation |
| Look-ahead item | Horizon; future milestone/movement; required outcome; prerequisites; latest-safe completion; readiness forecast; predicted blockers; owners; actions; confidence |
| Operational signal | Signal type; observed/received value; source; event time; location/domain; verification; freshness; confidence; sensitivity; affected objects; anomaly state |
| Intelligence assertion | Question; signal set; applicable rule/model; interpretation; alternative explanations; confidence; materiality; validity window; human reviewer; status |
| Prediction / forecast | Predicted state/event; horizon; probability/range; model/method; inputs/freshness; assumptions; uncertainty; trigger; affected outcomes; calibration record |
| Conflict / cascade | Signals or requirements in conflict; shared resource/time/route/person; forecast intersection; consequence; time-to-impact; prevention options; owner; decision |
| Command recommendation | Situation; recommended action; rationale; supporting evidence; alternatives; expected benefit/harm; urgency; owner; required authority; expiry; acceptance/rejection/outcome |
| Situation report | Audience/role; status; issue; impact; action underway; requested decision; evidence/confidence; update due; sensitivity; author/acknowledgement |
| Radio / command message | Priority; information/instruction/decision/escalation type; sender/recipient role identifiers; WHO/WHERE/WHAT/WHEN/ACTION; timestamp; acknowledgement; completion; sensitivity |
| Risk indicator | Linked risk; leading indicator; source; threshold/range; observation window; current value/trend; confidence; owner; preventive action; escalation/expiry |
| Incident record | Verified event; incident class/severity; identify/contain/assess/act/communicate/recover/record states; affected people/outcomes; owners/authorities; timestamps; evidence; closure |
| Command decision | Decision question; options; deadline; recommending owner; decision authority; consulted specialists; chosen action/rationale; consequences; communicated/implemented/verified states |
| Dashboard view policy | Role; permitted lenses/fields; aggregation; redaction; freshness/unknown treatment; alert rules; drill-down; offline mode; audit |
| Intelligence evaluation | Alert/recommendation; predicted versus actual; accepted/actioned; timeliness; usefulness; false positive/negative; harm/near miss; reviewer; model/rule change candidate |
| Operational status | Area/item; RAG state; objective criteria; evidence; owner; update time; expiry/freshness; impact; next action; deadline; escalation |
| Issue / decision | Observation; expected state; variance; impact/priority; owner; proposed action; decision authority; deadline; status; resolution confirmation |
| Handoff | Sender; receiver; subject/person/item; planned/actual time; readiness; message; acknowledgement; acceptance; completion evidence; exception |
| Command communication | Channel; sender/recipient roles; timestamp; situation; impact; action/owner; deadline/trigger; acknowledgement; sensitivity |
| Contingency | Critical element; Plan A/B/C; trigger metric; threshold; decision owner; activation time; dependencies; guest communication; reset/closure |
| Command-board state | Now; next 15 minutes; later; risks; VIPs; decisions; stale items; last refresh; controller |
| Crowd / experience signal | Observed behaviour; zone/time; count/trend where appropriate; possible explanations; confidence; validation; action; privacy constraints |
| Incident / event recovery | Type; severity; safety/security authority; identify/contain/resolve/communicate/recover steps; guest impact; owner; timestamps; post-event review |
| Capability | Roster; roles; briefing; suppliers; vehicles; equipment; capacity; shifts; communications; escalation; contingencies; confirmations; last verification |
| Live operation | Actual timing; queues; disruption; vehicle and transition status; conditions; requests; incidents; programme variance; task completion; escalations |
| Outcome | Friction; requests; feedback; response/resolution; plan-versus-actual; recognition failures; repeated questions; interventions; recommendation usefulness; false alarms; approved lessons |
| Risk register entry | Risk description; category; probability (1–5); impact (1–5); score; owner; (Module 11) prevention action; contingency action; trigger; review date; status |
| Decision trigger (Module 11) | Governing risk/vendor/weather item; IF condition; THEN action; BY deadline; decision owner; activation evidence; reset/closure |
| Crisis escalation assessment (Module 11) | Event; the five test questions and answers; recommended escalation level; responding authority; timestamp; outcome (incident/crisis) and rationale |
| Weather decision point (Module 11) | Venue/event; GREEN/AMBER/RED thresholds; current reading; source; forecast horizon; decision owner; activation time; Plan B reference |
| Critical load register (Module 11) | Equipment/system; priority tier; power source; backup source; fuel/runtime; technical owner; last test/changeover evidence |
| Service recovery ledger entry (Module 11) | Guest; issue; time; department; response; resolution; follow-up confirmation; root cause; preventive action |
| Crisis log entry (Module 11) | Time; event; decision; owner; status; linked incident/risk record |
| After-action review (Module 11) | Event; what worked; what failed; what nearly failed; near misses; root cause(s); proposed learning candidates; approval status; effective date |
| Master Event File (Module 12) | Master Event ID; event name/type; owner; status; version; linked sub-record references (guest, VIP, protocol, cultural, programme, vendor, production, risk, command, incident, departure, follow-up, review); open/closed state |
| Event protection principle (Module 12) | Statement (what must never happen); rationale; affected domain; owner; visibility requirement (always visible to command, not scored as a gradable risk) |
| Principal profile (Module 12) | Person; preferred address; role; family structure; key relationships; schedule; communication style; decision authority (includes named Family Decision Owner for guest-experience matters, M15-D04); privacy requirements; linked VIP file reference if applicable |
| Guest segment / priority record (Module 12) | Guest; segment(s) (Principal/VIP/Dignitary/Royal/Family/International/Elder/ General/Staff, may be multiple); experience need; protocol need; mobility; security; owner |
| Event dependency link (Module 12) | Predecessor element; successor element; type (vendor/production/ceremony/command); required completion state; owner; slack/buffer; consequence if broken |
| Standard Operating Procedure (Module 12) | Procedure name; domain; ordered steps; evidence basis (events it was proven on); status (Proposed/Approved/Provisional/Superseded/Rejected); owner; version |
| Known unknown register entry (Module 12) | Fact not yet available; expected availability point; owner; consequence if still unknown at decision time; current assumption if any; resolution status |
| Client debrief / event report (Module 12) | Event; audience; executive summary; guest/VIP/protocol/operations/vendor/programme findings; incidents; risk; feedback; financial summary; lessons; recommendations; distribution; sign-off |
| Cross-event knowledge index entry (Module 12, resolved M12-D07) | Subject type (Vendor/Guest-pattern/Venue/Protocol Pattern/Risk Type); subject reference; observation; privacy tier (Level 1/2/3, 123.3); supporting event references (internal only); confidence; promotion state (Proposed/Approved/ Provisional/Superseded/Rejected); approving Curator; review date |
| Venue Identity record (M12-D07) | Venue name/location; stable physical facts (capacity, access points, power infrastructure, parking, accessible routes); accumulated evidence references (internal only); known limitations; last verified date |
| Pattern Library entry (M12-D07) | Pattern name; subject type (Protocol/Risk-Incident); description; triggering conditions; accumulated evidence references (internal only); recommended response/mitigation; confidence; source After-Action Reviews |
| Role card (Module 14) | Role; reports to; location; responsibilities; do-not list (guest details, photography, unreplaced post-abandonment as standard fields); escalation triggers; version |
| RACI assignment (Module 14) | Task; Responsible; Accountable; Consulted; Informed; event reference |
| Staffing position map entry (Module 14) | Zone; role; headcount; shift window; coverage source (Module 9 zone-plan capability requirement); backup/relief owner |
| Candidate assessment record (Module 14) | Candidate; role applied for; interview-technique results (upset-guest, proactive-service, discretion tests); character-criteria assessment; decision; assessor; date |
| Recognition / accountability entry (Module 14) | Person; event; behaviour observed; category (recognition/accountability); action taken; owner; date; linked role/standard where applicable |
| Staff wellbeing plan (Module 14) | Event; shift; break schedule; meal arrangement; rotation plan; relief coverage owner; fatigue signal escalation path |
| Staff communication code registry entry (Module 14) | Code word/identifier; meaning; event; approved users; expiry; review status |
| Invitation (Module 15) | Event; guest; format/channel; content version; sent date; RSVP method/link; status |
| RSVP record (Module 15) | Guest; event; response (attending/declined/plus-one); special requirements captured; timestamp; source; linked guest profile reference |
| Concierge channel (Module 15) | Event; channel type (WhatsApp/phone/email/in-person); assigned concierge variant (Floating/Cultural/Digital); hours of operation; intelligence pack reference; escalation path |
| Access zone record (Module 17) | Event; zone (Public/Controlled/Restricted/Highly Restricted); physical boundary; permitted roles/credentials; overlapping service zone reference (Module 9); entry control method |
| Security override authority (Module 17) | Event; zone/decision requiring override; named Security Override Authority; escalation path; distinct from Family Decision Owner (M15-D04); expiry |
| Lost child incident record (Module 17) | Event; report time/location; searcher(s); exits controlled; guardian contact method; security notified; resolution time; closure evidence |
| Security audit scorecard (Module 17) | Event; area scores (access control/guest safety/VIP protection/medical/fire/ vehicle/privacy/vendor control/emergency response/communication); evidence; reviewer; learning candidates |
| Minor guardianship record (M14-D07) | Minor guest reference; Responsible Adult (name, relationship, contact, on-site/delegated status); verification method; delegated alternate (if any) and evidence of delegation; release rule (verified Responsible Adult only) |
| Minor photography consent record (M14-D07) | Minor guest reference; consent status (opt-in required by default); consented scope (general event/specific moments/none); consenting guardian; expiry; photographer/vendor acknowledgement |
| Handover record (Module 19) | Position; outgoing/incoming staff; time; important guests; outstanding requests; problems; special instructions; pending arrivals; acknowledgement |
| Staff performance scorecard (Module 19) | Event; person; presentation; warmth; composure; discretion; initiative; communication; protocol; guest awareness; reliability; overall; scored /10; evidence; reviewer |
| Staff talent record (Module 19, M14-D05 partial) | Person; skills; languages; experience; events worked; accumulated Staff Performance Scorecards; strengths; training completed (M19-D02); availability; preferred deployment; privacy/retention state (M19-D01) |
| AI output record (Module 20, 128.6, extended 134.4) | Output type (extraction/synthesis/draft recommendation/draft communication/ consult response); retrieved source records; confidence tier (Confirmed/ Reported/Inferred, 128.3); requesting role; query text (for consult responses); authority tag (who holds decision authority for this matter, 134.1); approving human (if actioned); timestamp; command-loop stage (127) |
| Lost property record (Module 21) | Item; location found; time; finder; storage location; handover (to guest/ disposal); closure evidence |
| Event Score (Module 21) | Event; guest experience; VIP management; protocol; operations; production; vendor performance (from that event’s Supplier scorecards, 52.5); staff performance (from Staff Performance scorecards, 124.5); timing; security (from Security Audit scorecard, 120.6); client satisfaction; overall; scored /10; reviewer |
| Entourage record (Module 24) | Principal guest; entourage member; category (official/personal/security/ support); access required; seating required; catering required; transport required; security coordination required; confirmed before arrival |
| Judgement Case Library entry (Module 25, 139.3) | Case title; scenario; stated lesson; source (CEO-authored, not event evidence); domain(s); knowledge state (1.1); citable by Consult (134.3), never presented as Pattern Library evidence |
| Authority Map entry (Module 26, 140.2) | Person; relationship to principal; authority domain(s); can instruct staff (yes/no/limited); scope of “defined” authority; event reference. Family Decision Owner (115.1) is this record’s guest-experience-domain row |
| Host Brief (Module 26) | Event; who host must personally receive/thank; who to avoid; ceremonial duties; family dynamics; essential photographs; private preferences; rest windows; likely decisions; fallback authority when host unavailable |
| Host Time Budget (Module 26) | Event; arrival; receiving period; ceremonial obligations; photography; meal; guest engagement; private time; departure preparation |
| Principal Suite access record (Module 26) | Event; location; who may enter; who may knock; who may accompany; emergency protocol; photography permission |
| Host Debrief (Module 26, 140.6) | Event; timing (deliberately delayed); what worked; what should never happen again; which guest experience mattered most; where the host felt unsupported; what should have been anticipated; Host Experience Score (informed/protected/respected/enjoyed/unnecessary-decisions/abandoned/ overwhelmed/private-time/trust, each answered directly) |
| Event Readiness Declaration (Module 30, 141.3) | Event; principal and critical guests confirmed; protocol/cultural/guest-flow risks confirmed; vendor dependencies confirmed; critical transitions confirmed; top-five failure points and contingencies confirmed; function ownership confirmed; principal information-filtering plan confirmed; each item references its underlying domain gate rather than re-deriving it; Event Director sign-off; timestamp |
| Vetting Record (Section 142.3) | Candidate; identity verification; right-to-work evidence; references (min. 2); background-check evidence (VIP-facing roles); qualifications; medical fitness where applicable; Hiring Manager sign-off; Approved Staff Register status |
| Disciplinary Record (Section 142.6) | Person; misconduct tier (minor/serious/gross); procedure step; evidence; warning validity period; hearing record where applicable; appeal status; outcome |
| Shadow-mode test case (Section 144.3) | Case source (Judgement Case Library/Protocol Register/excluded CEO exercise); category; known-good human decision; AI shadow-mode output; agreement/divergence result; reviewer |
| Divergence report (Section 144) | Test case reference; nature of divergence; severity (critical/non- critical); root-cause analysis; resolution (model adjustment/human- override rule); reviewed by (CTO/Protocol Director/external validator) |

**DATA RULE A fact without source, verification state, sensitivity and

valid-use purpose is not reliable operational intelligence.**

# 6. Application lifecycle

| Stage | Knowledge application | Primary outputs |
| --- | --- | --- |
| 1. Discovery | Interpret the host’s desired feeling, service promises and intolerable friction | Experience intent; discovery questions; initial risks |
| 2. Data sufficiency | Determine whether responsible design is possible with current facts | Missing-data requests; assumptions; confidence |
| 3. Experience design | Evaluate journeys through the five layers | Requirements; preparations; service design |
| 4. Friction audit | Test for waiting, searching, repetition, uncertainty, discomfort, exposure and dependency failure | Friction register; mitigations; priorities |
| 5. Invisible choreography | Convert approved requirements into coordinated actions | Owners; timings; dependencies; contingencies |
| 6. Readiness review | Verify ownership, resources, briefing, rehearsal and contingency | Readiness status; blockers; approvals |
| 7. Live orchestration | Compare plan with actual state and recommend intervention | Live recommendations; alerts; escalations |
| 8. Post-event learning | Compare predictions, actions and outcomes | Debrief; proposed learning; rule-performance evidence |

# 7. Intelligence products

## 7.1 Briefs

- Event Command Board and executive situational-awareness brief

- Master Event Timeline, Run of Show and guest Programme views

- Command structure, escalation ladder and decision-authority register

- Vendor Matrix, dependency map and readiness evidence report

- RAG operational status and stale-update report

- Handoff/closed-loop communication monitor

- Contingency trigger and active-recovery report

- Pre-open readiness, T-15 stabilisation and go-live decision

- Guest experience/crowd signal and bottleneck intelligence

- Guest experience brief

- Guest Journey Map and live journey state

- Friction map

- Significant-guest readiness brief

- VIP Intelligence File, role-limited VIP Event Brief and live VIP Dashboard

- VIP privacy/access report and preference-validity review

- VIP arrival, ownership, contingency and recovery readiness

- Protocol Brief and Protocol Master Sheet

- Title and Forms-of-Address Verification Register

- Precedence Conflict Report

- Seating and adjacency risk report

- Arrival, receiving-line and ceremonial-movement readiness

- Cultural Intelligence Brief and cultural friction audit

- International Guest Cultural Brief

- Cultural Authority and Ceremonial Object Registers

- Religious and interfaith accommodation readiness

- Host confidence brief

- Arrival and departure intelligence

- Accessibility and comfort brief

- Privacy and discretion brief

- Touchpoint and transition readiness brief

- Unresolved assumptions report

### 7.1.1 Module 7 products

- Supplier Intelligence File and capability-evidence dossier

- Appointment comparison, due-diligence exceptions and approval recommendation

- Vendor brief, acknowledgement and code-of-conduct compliance view

- Scope, milestone, acceptance and commercial-change register

- Vendor arrival, check-in, setup-zone and guest-ready inspection dashboard

- Supplier scorecard, preferred-network review and corrective-action report

### 7.1.2 Module 8 products

- Ceremony Architecture and Ceremony Control Sheet

- Ceremony spine, movement matrix and principal-route plan

- Released Run of Show, role-specific Cue Sheets and guest Programme

- GO/HOLD board, cue-readiness and acknowledgement monitor

- Receiving-line, holding-area, speaker and stage-position readiness

- Pronunciation and Address Sheet linked to verified protocol records

- Transition, bridge, buffer and dead-air risk report

- Delay-cascade analysis and ceremony recovery recommendation

- Departure/farewell readiness and ceremony debrief

### 7.1.3 Module 9 products

- CEO Standards Library and event applicability review

- Event Service Standards Plan with owner, checkpoint and evidence

- Standards coverage, readiness and exception dashboard

- Role-specific staff briefing cards and five-minute huddle view

- Service-zone coverage and service-vacuum map

- Guest request ownership, escalation and closure monitor

- Dining, dietary/allergy, restroom, comfort and departure assurance views

- Service recovery case and follow-up dashboard

- Staff competency, role-play and coaching report

- Post-event standards-performance and improvement review

### 7.1.4 Module 10 products

- Master Operational Picture and multi-lens Event Status

- Role-scoped Event Command Dashboard with freshness and Unknown states

- NOW/NEXT/LATER, 15-minute and 60-minute look-ahead views

- CEO briefing: status, issue, impact, action and decision required

- Signal quality, stale-source and conflicting-report monitor

- Predicted conflict, cascade and latest-safe-action alerts

- Risk-indicator, incident, decision and recovery intelligence

- Radio/closed-loop communication and acknowledgement monitor

- Human-command/AI-recommendation audit and outcome evaluation

- After-action intelligence accuracy, usefulness and missed-signal report

## 7.2 Recommendation contract

Every recommendation must state: what; why; affected guest or group; applicable principle; supporting data; confidence; urgency; expected benefit; proposed owner; approval requirement; and expiry time.

## 7.3 Alert policy

Alerts are reserved for material exceptions, including conflicting instructions, inaccessible routes, unowned critical touchpoints, unresolved critical dependencies, privacy conflicts, approaching arrivals without readiness, capacity breaches, excessive waiting, adverse comfort conditions, programme disruption, repeated requests for known information, host intervention and unauthorised sensitive-data exposure.

Alerting must include severity, acknowledgement, escalation, deduplication and suppression. Information overload is itself operational friction.

## 7.4 Scores

- Friction exposure

- Touchpoint readiness

- Data completeness

- Dependency confidence

- Anticipation coverage

- Guest-journey readiness

- Event-experience readiness

- Supplier performance by dimension

- Vendor readiness and resilience

**PROHIBITION Do not create a single “guest importance score.” Keep

protocol, security, assistance, relationship and service requirements

as distinct dimensions.**

# 8. Roles, permissions and approval boundaries

| Role | Primary authority |
| --- | --- |
| CEO / Executive Command | Owns brand, client, strategic decisions, reputation, commercial relationship and Level-4 escalation |
| Event Director | Operational commander; owns execution, coordination, timeline, vendors, staff and live event command |
| Command Controller | Maintains command board, issue/decision log, version state, acknowledgement and freshness |
| Operations Lead | Owns venue, production, vendor and operational integration under Event Director |
| Department / Function Lead | Owns defined scope, readiness, staff, dependencies, handoffs and Level-2 decisions |
| Vendor Lead | Single accountable vendor representative for contracted deliverables and escalation |
| Experience Director | Designs journeys and approves experience recommendations |
| VIP Experience Lead | Owns VIP operating model, portfolio readiness, Control Desk and escalations |
| VIP Owner | Accountable for one assigned guest’s end-to-end preparation, monitoring, recovery and closure |
| VIP Owner Deputy | Assumes continuity under defined triggers; prevents single-person dependency |
| Journey Owner | Owns end-to-end continuity across stages and departments |
| Stage / Transition Owner | Delivers entry, handoff, readiness and exit conditions |
| Guest Intelligence Lead | Manages guest profiles, verification and segmentation |
| Communications Lead | Controls guest messages, versions, timing and response states |
| Protocol Lead | Owns event protocol architecture, precedence, introductions, ceremonial handling and rehearsal |
| Protocol Verifier | Verifies identity, title, office, address, pronunciation and authoritative sources independently where required |
| Cultural Intelligence Lead | Owns cultural-context discovery, authority consultation, friction review and team integration |
| Cultural Experience Concierge | Bridges guest, culture, protocol and ceremony; briefs guests and prevents misunderstanding |
| Institutional Liaison | Obtains authoritative guidance from palace, mission, government office, religious body, family or other institution |
| Ceremonial Object Custodian | Controls receipt, authorised handling, placement, movement, photography and return of significant objects |
| Seating Authority | Owns seating rationale, adjacency/exclusion controls, version approval and controlled release |
| MC / Announcer | Delivers only approved introductions, address forms, order and pronunciation |
| Logistics Lead | Controls transport, movement and dependencies |
| Guest Liaison / Escort | Maintains assigned-guest continuity using minimum necessary information |
| Supplier Lead | Sees assigned deliverables, not full guest intelligence |
| Security Lead | Owns authorised security coordination; specialist authority for security procedures/incidents |
| Medical / Emergency Lead | Qualified owner for medical/emergency procedures and liaison with public emergency services |
| Data Steward | Controls sensitivity, permission, retention and access reviews |
| Client / Host | Supplies and approves selected event information without becoming the operational manager |

## 8.0.1 Vendor governance roles added by Module 7

| Role | Primary authority |
| --- | --- |
| Vendor & Partnerships Lead | Owns supplier intelligence, classification, due diligence, appointment recommendation, performance review and preferred network |
| Commercial Approver | Approves commitments, scope changes, payment exceptions, damages/credits and replacement spend within delegated limits |
| Quality / Acceptance Owner | Defines evidence and accepts/rejects deliverables at checkpoints; cannot waive specialist safety approval |
| Vendor Check-in Coordinator | Controls roster, access, vehicles, equipment, zones and check-in/out with Operations and Security |

## 8.0.2 Ceremony governance roles added by Module 8

| Role | Primary authority |
| --- | --- |
| Ceremony Architect | Designs the ceremony spine, moment logic, movement matrix, transitions and recovery options with relevant authorities |
| Stage Manager | Controls backstage/holding readiness, speaker/participant positions and execution of released stage cues |
| Cue Caller | Issues GO/HOLD and departmental cues from the released Run of Show under delegated Event Director authority |
| Timekeeper | Maintains the ceremonial clock, actual timing, variance and recovery-time calculations |
| Principal Movement Lead | Owns principal route, readiness, holding, movement, handoffs and departure with VIP/Protocol/Security leads |
| Speaker Coordinator | Confirms, briefs, positions, cues and releases speakers; protects approved timing and introductions |
| Photography Marshal | Assembles approved groups, controls positions/time/release and protects ceremony/privacy restrictions |

## 8.0.3 Service assurance roles added by Module 9

| Role | Primary authority |
| --- | --- |
| Guest Experience Lead | Owns event service design, applicable standards, zone coverage, guest-request performance and service recovery |
| Service Standards Owner | Maintains approved standards, applicability logic, evidence requirements, training content and controlled revisions |
| Hospitality Supervisor | Owns a service zone/shift, staff positioning, request handoffs, inspections, coaching and escalation |
| Service Assurance Verifier | Independently verifies planned standards/checkpoints and records defects/rechecks; does not self-certify where independence is required |
| Dining Service Lead | Owns dining rhythm, table coverage, dietary handoffs, water/replenishment, clearing and catering escalation |
| Restroom Experience Lead | Owns attendant coverage, inspection cadence, supplies, cleanliness defects and escalation |
| Lost Property Custodian | Controls secure recording, storage, owner verification, handover and retention/disposal audit |

## 8.0.4 Live intelligence roles clarified by Module 10

| Role | Primary authority |
| --- | --- |
| Operational Picture Controller | Maintains the canonical live picture, time/state alignment, source freshness, conflicting reports and released snapshots |
| Intelligence Analyst | Validates signals, identifies patterns/conflicts/cascades, states uncertainty and prepares recommendations without command authority |
| Dashboard / Access Administrator | Maintains role-scoped views, redaction, offline access, device/session controls and audit |
| Incident Commander | Named human controlling one incident under Event Director/specialist authority; does not replace whole-event command |
| Radio Controller | Maintains role identifiers, channel discipline, priority, message routing, acknowledgements and backup communication |
| Scribe / Decision Logger | Records material situation reports, decisions, rationale, communications, actions and verification timestamps |

## 8.0.5 Risk and crisis governance roles added by Module 11

| Role | Primary authority |
| --- | --- |
| Risk Owner | Named accountable person for one register risk; answers “what are we doing about this” for prevention and contingency; a team cannot hold this role |
| Crisis Commander | Confirmed relationship to Incident Commander (CEO-confirmed). Activated only at Escalation Level 4–5 (Module 11 Crisis Scale, resolved onto the 76.2 ladder at 86.2); reduces decision-making to a single authority for the duration of a significant/critical incident. This does not replace the Incident Commander role from Module 10 for contained, non-crisis incidents — Crisis Commander is the escalated form that authority takes when 11.3’s crisis test is answered yes, not a separate, competing role |
| Client Communication Lead | Owns the single approved outward message to the client during a live incident/crisis; applies the client briefing formula (issue/impact/action/next update) and the one-voice principle; prevents the client hearing bad news from a guest, vendor or social media first |
| Crisis Log / Room Controller | Controls the Crisis Command Centre during a significant incident: information flow, decision record, communication and access; not every person may enter |
| Post-Incident Reviewer | Runs the after-action review, near-miss register and root-cause (five whys) analysis; proposes learning candidates for CEO/delegated approval — cannot itself change doctrine, thresholds or rules |

## 8.0.6 Operating-system governance roles added by Module 12

| Role | Primary authority |
| --- | --- |
| Master Event File Owner | Named person who may open, close, merge or archive a Master Event File and is accountable for its sub-records being current, versioned and consistent with the Master Event ID; normally the Event Director, but must be named per event rather than assumed |
| SOP Custodian | Owns the SOP library promotion path: reviews repeated-success evidence, proposes an SOP for approval, versions and retires SOPs; cannot unilaterally promote a procedure to canonical status |
| Knowledge Base Curator | Owns the cross-event knowledge index, fully designed at Section 123 (M12-D07 resolved): assesses privacy tier and evidentiary strength before admitting a Venue Identity, Pattern Library or Vendor cross-client entry; cannot approve a fact generated from an event they themselves directed (second-person review, 123.6); enforces the privacy-segregation boundary between different clients’ events before any pattern is surfaced across them |
| 8.0.7 Staffing and | culture roles added by Module 14 |

| Role | Primary authority |
| --- | --- |
| Floating Guest | No fixed station; scans assigned area for |
| Concierge | confusion, isolation, discomfort, queues and unmet |
|  | need and either resolves directly (within |
|  | delegated limits, 104.3) or escalates; reports |
|  | through the normal command structure, not a |
|  | separate channel |

People/Culture Owns the recruitment-through-repetition culture Owner cycle (104.1) for the organisation, not one event: hiring criteria, role-card library, recognition and accountability practice. Does not have authority over the HR/legal matters listed at 107.2, which remain outside this specification

## 8.0.8 Communication roles added by Module 15

| Role | Primary authority |
| --- | --- |
| Digital/WhatsApp Concierge Owner | Owns the concierge channel (112) before, during and after the event; works from Level 1 service information only (29.2) unless granted higher access; escalates through 76.2 like any other role; may be the same person as the Floating Guest Concierge (Module 14) or Cultural Experience Concierge (Module 4) on smaller events |
| 8.0.9 AI governance | role added by Module 20 |
| Resolved (M20-D01).* ison Doclar. Unlike fixed at the organi nsistent with the ro yer may access acros th the CEO’s existin d quality assurance roughout). | * The CEO is the named AI Systems Owner for every other role in this specification, this one sational level rather than assigned per event — le’s own scope (131.2: it governs what the AI s the business, not one event’s execution), and g standing responsibility for experience standard (14.40’s role framing, carried forward |

| Role | Primary authority |
| --- | --- |
| AI Systems Owner | CEO, Maison Doclar (named, M20-D01). |
| (131.2) | Accountable for what data and tools the Anthropic |
|  | API integration may actually retrieve and call; |
|  | reviews the AI output audit trail (128.6, Section |
|  | 5) for grounding failures or boundary violations; |
|  | the only role authorised to change what the AI |
|  | layer can access. Governs the AI’s plumbing, not |
|  | the event — holds none of the decision authority |
|  | described at Section 127, and does not gain any |
|  | event-day authority beyond what the CEO already |
|  | holds on the 76.2 ladder by virtue of this role |

## 8.0.10 Host management role added by Module 26

| Role | Primary authority |
| --- | --- |
| Host Companion (140.3) | Stays close enough to the principal throughout the event to manage cues, transitions, timing, photography coordination and graceful conversation exits; the principal-specific analogue of the VIP Host role. Does not hold decision authority beyond what the Authority Map (140.2) assigns them for this event — proximity to the principal is not itself authority |
| 8.0.11 AI validatio | n role added by Section 144 |

| Role | Primary authority |
| --- | --- |
| CTO (144.4) | Primary owner of the shadow-mode test harness’s |
|  | technical implementation: building and operating |
|  | the comparison engine, running test cases, |
|  | producing divergence reports. Distinct from the AI |
|  | Systems Owner (8.0.9, the CEO), who governs what |
|  | the AI layer may access and reviews its audit |
|  | trail — the CTO proves the layer is safe to grant |
|  | that access to in the first place. Protocol |
|  | Director supports as test-case provider/validator; |
|  | an external protocol expert serves as independent |
|  | validator of divergence analysis |

## 8.1 AI boundary

Governing pattern (fully designed at Sections 126-131): across every rule below, AI may identify, rank, explain, extract, synthesise, draft and recommend; a named, accountable human decides and acts on anything consequential. This is not incidental caution accumulated rule by rule — it is one consistent architecture, mapped explicitly onto the Observe/Interpret/Decide/Act/Verify/Learn command loop at Section 127. The specific rules below remain the authoritative, checkable form of that architecture for each situation they cover.

- AI may identify, rank, explain and recommend.

- AI must not invent guest facts or silently treat absence as a negative fact.

- AI must not autonomously change protocol precedence, diagnose needs or contact guests outside an approved workflow.

- AI must not expose sensitive information beyond need-to-know access.

- AI must not convert observations into permanent guest knowledge without review.

- AI must not invent or independently declare precedence where an authoritative source or contextual protocol judgment is required.

- AI must not treat wealth, fame, title or social prominence as automatic formal rank.

- AI must not publish, print or cue an important title, introduction, seat or ceremonial order without the required verification and approval state.

- AI must not generalise a practice from a broad ethnic, regional, religious, gender or age label to a particular guest, family, institution or occasion.

- AI must not invent sacred, palace, chieftaincy, greeting, prayer, object-handling or interfaith requirements.

- AI must distinguish cultural guidance from verified event-specific requirements and disclose confidence and authority.

- AI must not classify a person as a VIP solely from wealth, fame, online profile or inferred social status.

- AI must not enrich a VIP file from public or private sources merely because information is obtainable; every item requires an approved service purpose and provenance.

- AI must not expose confidential/restricted VIP details in general chat, dashboards, exports, notifications or team groups.

- AI must not turn an observation into reusable VIP memory without validation, purpose, authority and expiry review.

- AI may support situational awareness, but must not present unverified crowd behaviour, stale updates or model inference as operational fact.

- AI must not autonomously override qualified security, medical, emergency, venue or public-authority instructions.

- AI must not activate a high-impact contingency, change a released programme, direct evacuation or make a safety-critical decision unless an explicitly authorised human workflow permits it.

- AI must preserve command authority, version state, evidence, acknowledgement and decision auditability in every material recommendation.

- AI must not autonomously appoint, contract, pay, suspend, blacklist or publish allegations about a supplier.

- AI must not treat preferred status, a portfolio, price or a composite score as proof of event-specific capability or readiness.

- AI must not waive vendor evidence, guest-ready acceptance or qualified safety/regulatory approval.

- AI must share only the minimum guest/VIP information required for the supplier’s released scope.

- AI must not invent or resolve precedence, ceremonial meaning, cultural/religious practice or principal treatment without the required authority and approval.

- AI must not issue a live GO/HOLD, move a protected person, alter an approved introduction or resequence a protected ceremonial act unless an authorised human workflow explicitly permits it.

- AI must distinguish planned time, operational window, actual time and prediction; it must not present an estimate as a confirmed cue condition.

- AI may propose shortening, removal, resequencing or a bridge, but must disclose protocol, cultural, contractual, safety, guest and dependency consequences and the required approver.

- AI must not infer disability, allergy, medical condition, loneliness, distress, intoxication or personal preference as fact from appearance or behaviour alone.

- AI may flag an observable service signal and suggest a respectful offer, but a person decides how to approach and records only minimum necessary information.

- AI must not promise an unavailable service, approve compensation, override security/protocol/safety restrictions or close a guest request without human-confirmed resolution evidence.

- AI must not expose names, titles, dietary/allergy data, VIP identity, movements or private requests in staff views beyond role-specific necessity.

- AI may evaluate standards evidence, but must not mark a standard met from task completion alone when observation, guest confirmation or specialist verification is required.

- AI must label observation, report, inference, prediction and confirmed fact distinctly; confidence does not convert inference into fact.

- AI must surface source, timestamp, freshness, assumptions, alternative explanations, uncertainty and validity window for material intelligence.

- AI must not optimise solely for schedule or concealment when safety, dignity, privacy, protocol, culture, law or truthful executive reporting is affected.

- AI must not autonomously issue radio instructions, command staff, activate emergency plans, direct evacuation, disclose sensitive movements or make executive/specialist decisions.

- AI may rank consequential issues, but a fixed priority pyramid cannot override case-specific vulnerability, scale, irreversibility, legal duty or qualified incident command.

- AI recommendations require acceptance/rejection and outcome logging; silent automation is limited to approved low-impact presentation, deduplication and routing functions.

- Material decisions retain their data, rule, author, approver and timestamp.

- AI may calculate a probability x impact risk score and rank register entries, but must not decide that a risk is acceptable; a named Risk Owner and, above threshold, the CEO/delegated authority approves residual risk.

- AI must not itself classify an event as an incident versus a crisis; it may surface the five crisis-escalation-test questions and their supporting evidence, but the classification decision belongs to a human at or above the indicated escalation level.

- AI must not activate a weather, power, vendor or programme contingency; it may detect that a defined decision trigger (IF/THEN/BY) has been reached and alert the named decision owner before the deadline.

- AI must not issue, approve or send external crisis communication, client updates or social/media statements; it may draft a message against the client-briefing formula for the Client Communication Lead to approve and send.

- AI must not suppress, soften or delay a safety-relevant fact to protect a schedule, a vendor, the client relationship or Maison Doclar’s reputation.

- AI must not name or imply individual blame in a risk, incident or after-action record; root-cause analysis is captured at the system level (the five whys), not the person level.

- AI may flag that a near miss occurred and propose a learning candidate, but a near miss becomes doctrine, a threshold or a rule only through the same approval path as any other knowledge change.

- AI must not open, close, merge or archive a Master Event File, nor reconcile conflicting sub-record versions, without the Master Event File Owner’s action.

- AI must not promote a procedure to a canonical Standard Operating Procedure from a single successful event; it may surface repeated- success evidence to the SOP Custodian, who decides.

- AI must not surface a cross-event pattern, comparison or ranking (e.g. “Venue X has poor VIP parking”) that draws on more than one client’s events without the Knowledge Base Curator’s confirmation that privacy segregation between those clients’ events permits it.

- AI must not treat an event-protection principle as a gradable risk subject to probability x impact trade-off; it is non-negotiable by definition and any conflict with it is escalated, not scored.

- AI must not silently resolve a Known Unknown into an assumed value for planning purposes without recording that it is an assumption with a stated confidence and an owner.

- AI must use the single canonical Supplier scorecard (Section 5, resolved per M13-D01) for every vendor score; it must not reconstruct or present either of the retired Module 13 scorecard variants.

- AI must not screen, shortlist, reject or score a hiring candidate autonomously; it may structure interview-technique results (101.2) for a human assessor’s decision only.

- AI must not compile or expose an individual staff member’s performance, recognition or accountability history outside the People/Culture Owner and that person’s direct management chain, and must not use it to infer fitness for unrelated roles without human review.

- AI must use the single canonical 5-second acknowledgement target (64.1, resolved per M14-D01) wherever an acknowledgement-time target is referenced; it must not reconstruct or present the retired 3-second or 10-second variants.

- AI must not treat the Module 14 staff escalation matrix as a separate authority from the 76.2 ladder; it is the same mechanism viewed at staff-facing resolution.

- AI must not send a guest-facing message (invitation, confirmation, reminder, concierge reply, service-recovery message) autonomously for anything above routine, pre-approved content; it may draft against the approved templates and hierarchy (Section 113) for human send approval.

- AI must apply the 29.1 data-minimisation test to guest correspondence specifically; it must not surface a stored preference or personal detail in a message unless the guest would reasonably expect Maison Doclar to know it and doing so improves the experience rather than demonstrating surveillance.

- AI must not action a guest-experience instruction from anyone other than the event’s named Family Decision Owner or, in their absence, the Event Director (115.1, resolved M15-D04); it may surface a conflicting instruction to the correct authority but must not execute it itself.

- AI must use the single canonical 86.2 Crisis Scale for event-day incident severity (resolved per M16-D01); it must not reconstruct or present the retired Module 16 Incident Priority scale.

- AI must not grant, expand or waive access-zone permission for any person, including family members or the CEO informally; only the named Security Override Authority for that event may do so (120.4), and this authority is never the Family Decision Owner (115.1).

- AI must not attempt to locate, identify or communicate about a lost child beyond routing the report to the designated security/search roles; it must not broadcast a child’s description or location outside that controlled channel.

- AI must not release, or advise releasing, a minor to anyone other than their verified Responsible Adult or a recorded delegate (120.5.1); it must not treat an asserted family relationship alone as sufficient.

- AI must treat photography or publication of a minor as unconsented by default; it must not present a minor’s image as clearable without an explicit, recorded guardian opt-in (120.5.2).

- AI must not present the Module 17 Security Audit Scorecard and the canonical Supplier scorecard (M13-D01) as measuring the same thing; they assess different subjects and must not be merged or confused.

- AI must not promote a fact into the cross-client-queryable knowledge base (Venue Identity, Pattern Library, or a Vendor’s cross-client summary) itself; it may propose a candidate with its supporting evidence and privacy-tier assessment for the Knowledge Base Curator to admit, hold or reject (123.4).

- AI must not surface a Level 2 or Level 3 fact (123.3) in any cross-client context, regardless of how the query is phrased or how much time has passed since the originating event.

- AI must not treat a single event’s evidence as a pattern; corroborating evidence from multiple events is required before a Pattern Library or Venue Identity entry may be proposed (123.4).

- AI must apply the higher aggregation/de-identification bar to any guest-behaviour pattern specifically, consistent with 29.1, before proposing it for the cross-client layer (123.4).

- AI must use the canonical Supplier scorecard including the three fields added per M18-D01 (Communication, Timeliness, Flexibility), scored /10 throughout (52.5); it must not reconstruct Module 18’s original field set (with Presentation/Guest interaction as separate fields) or any other variant.

- AI must apply the commercial authority ladder (49.2.2) by spend type, not amount alone: like-for-like emergency vendor replacement is Event Director authority regardless of value; net-new spend is capped at the event-specific percentage, defaulting to CEO approval required if that percentage has not been set for the event. AI must not release a payment-milestone tranche (49.2.3) without evidence that its gating condition (mock-up approval, delivery sign-off, or filed Supplier scorecard) has actually been met.

- AI must not present the Staff Performance Scorecard (124.5), the Supplier scorecard (52.5), the Security Audit Scorecard (120.6) or the Event Score (135.6) as the same instrument; all four assess different subjects, and AI must compute the Event Score’s vendor, staff and security fields from that event’s actual underlying scorecards rather than scoring them independently.

- AI must treat the Staff Talent Record (124.6) as staff personal data subject to the same care as guest data: no compiling or exposing a person’s performance history outside their management chain and the People/Culture Owner (8.0.7), and no retention or use beyond what M19-D01 eventually authorises.

- In every Consult response (134), AI must tag the correct decision authority for the matter and must never phrase a recommendation as executable instruction to a requester who does not hold that authority themselves; where precedent is weak or absent, AI must say so rather than produce a confident-sounding answer to fill the gap (134.3).

- AI must clearly label a citation to the Judgement Case Library (139.3) as illustrative CEO-authored doctrine, and must never present it as Pattern Library (123.2) evidence or imply it reflects an observed, corroborated event outcome.

- AI must not generate a protocol, precedence, seating or forms-of- address recommendation for a live event until the shadow-mode evaluation harness (144) has validated that capability against its acceptance criteria; until then, any such AI output must be labelled as unvalidated and routed for full human derivation rather than treated as a reviewable draft.

- AI must never state an officeholder name, title-holder or other [Verify]-marked entry from the Protocol Register (143) as current fact; it must always present such entries as requiring event-specific verification, consistent with the absence-handling rule (128.2).

- AI must treat the Staffing Policy Framework (142) as Provisional, not Approved, in any output referencing it, and must note that employment-counsel sign-off is outstanding wherever the framework is cited for a compliance-sensitive purpose.

# 9. Global doctrine and Lagos context

| Globally reusable | Lagos / Nigeria context pack |
| --- | --- |
| Anticipation, dignity, discretion, effortlessness, friction auditing, recognition, journey design, five-layer evaluation, personalisation boundaries, readiness and contingency | Traffic variability; venue access and parking; heat, humidity and rainfall; power resilience; communications resilience; airport variability; drivers and entourages; political, religious and traditional protocol; multi-location events; emergency access; local suppliers and currency |

Context packs create considerations and evidence requirements, not stereotypes. The system must use event facts, historical evidence and verified live conditions rather than assuming uniform guest behaviour.

# 10. Friction taxonomy — foundation

| Journey stage | Illustrative friction |
| --- | --- |
| Pre-event | Unclear invitation, RSVP, dress, directions, timing or communication |
| Travel | Traffic uncertainty, missing transport status or route failure |
| Arrival | Waiting, searching, security repetition, parking, exposed walking or failed recognition |
| Orientation | Unclear destination, route or next step |
| During event | Seating, temperature, sound, sightline, toilet, food, programme or movement issues |
| Transitions | Congestion, timing uncertainty, missing escort or dependency failure |
| Departure | Vehicle search, belongings, unsafe waiting, farewell or transport failure |
| Post-event | Missing follow-up, unresolved issue or inappropriate reuse of information |

Every future friction record should include cause, affected group, likelihood, impact, confidence, prevention, contingency, owner, escalation and resolution deadline.

## 10.1 Friction severity scale

| Score | Guest impact | Required treatment |
| --- | --- | --- |
| 0 — None | Effortless | Preserve and monitor |
| 1 — Minor | Barely noticeable | Reduce when proportionate |
| 2 — Moderate | Guest must think or ask | Mitigate and monitor |
| 3 — Significant | Guest experiences inconvenience | Must be eliminated or explicitly accepted before readiness |
| 4 — Serious | Guest is frustrated or embarrassed | Critical remediation and escalation |
| 5 — Critical | Experience, dignity, safety or reputation is materially damaged | Stop/contain, escalate and recover immediately |

Severity is not the full risk score. Prioritisation must also consider likelihood, duration, affected population, guest vulnerability, recoverability, confidence and reputational or safety consequences.

## 10.2 Never-ask test

For every journey segment, the system must identify questions the guest should never need to ask. Each prohibited question must map to a preventive communication, cue, person, process or environmental design. A repeated “never ask” question is evidence of a design failure, not merely a guest enquiry.

# 11. Open decisions and unresolved knowledge

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M1-D01 | What is the minimum dignity standard for every guest? | Define a universal baseline before service tiers |
| M1-D02 | Which promises are non-negotiable at every Maison Doclar event? | Create an acceptance and readiness floor |
| M1-D03 | What failures prevent readiness approval? | Use critical blockers plus evidence requirements |
| M1-D04 | What may the system decide automatically? | Automate low-impact classification and routing; approve material actions |
| M1-D05 | What guest information will Maison Doclar refuse to collect? | Adopt minimum-necessary and purpose-limited collection |
| M1-D06 | When may knowledge from one event be reused at another? | Require relevance, provenance, validity and permission |
| M1-D07 | How should conflicting host instructions be handled? | Dignity, safety, legality and privacy override convenience |
| M1-D08 | What authority must Maison Doclar possess to own the experience? | Record contractual responsibility and operational control separately |
| M1-D09 | What does “memory” mean operationally? | Define emotional recollection, advocacy and signature moments separately |
| M1-D10 | How is guest significance represented? | Use independent dimensions; never one status score |

## 11.1 Module 2 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M2-D01 | What is the canonical journey-stage vocabulary? | Adopt fourteen stages but allow event templates to omit or extend with traceability |
| M2-D02 | When does a journey begin and end? | Set boundaries by event scope and promise, not event start/end time |
| M2-D03 | What makes a touchpoint or transition “material”? | Material if failure can affect knowledge, time, dignity, comfort, safety, protocol, emotion or continuity |
| M2-D04 | How are emotional states captured? | Use intended, self-reported and evidenced-observed states separately; prohibit fabricated certainty |
| M2-D05 | What friction severity blocks readiness? | All unresolved 4–5 and unaccepted 3 risks block readiness |
| M2-D06 | Who may accept a level-3 friction risk? | Event Lead within policy; CEO/Experience Director for dignity, reputation or principal impact |
| M2-D07 | How are journey variants assigned? | Use needs and operating requirements, not labels alone |
| M2-D08 | What is the baseline confirmation service level? | Define delivery, acknowledgement and escalation rules by segment/channel |
| M2-D09 | What evidence proves a transition is ready? | Receiving owner acknowledgement plus verified dependencies for critical transitions |
| M2-D10 | When can follow-up become relationship management? | Only within consent, client mandate and purpose/retention rules |

## 11.2 Module 3 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M3-D01 | Who has final authority over event protocol architecture? | Protocol Lead proposes; Event Lead approves operations; CEO approves unresolved high-impact conflicts |
| M3-D02 | Which guest categories require mandatory independent verification? | All dignitaries, titled persons, principals, speakers and publicly displayed important guests |
| M3-D03 | What sources qualify as authoritative? | Current issuing institution or designated protocol authority first; recorded secondary evidence only with qualification |
| M3-D04 | How recent must title/office verification be? | Set risk-based expiry; reverify immediately before print/publication and event day for changeable offices |
| M3-D05 | Who approves cross-system precedence conflicts? | Relevant institutional authority plus Maison Doclar Protocol Lead; CEO where dignity/reputation risk remains |
| M3-D06 | What seating changes require approval and version release? | All principal, dignitary, protocol, security-sensitive and exclusion-sensitive changes |
| M3-D07 | How should sensitive adjacency/exclusion reasons be stored? | Restricted coded reason with minimum disclosure; full rationale accessible only to authorised roles |
| M3-D08 | What constitutes protocol readiness? | Verified identities/roles, approved architecture, rehearsed critical movements, contingencies and one released master version |
| M3-D09 | When does institutional guidance override host preference? | Where it governs the represented institution, custom, safety or official participation; conflicts escalated before execution |
| M3-D10 | Who may authorise live protocol deviations? | Named Protocol Lead/deputy within documented limits and escalation policy |
| M3-D11 | How should dignity-preserving corrections be standardised? | Create discreet correction playbooks for seats, titles, arrivals, introductions and unexpected entourages |
| M3-D12 | Which national symbols may Maison Doclar deploy? | Only after authoritative requirements, approvals and responsible owner are confirmed |

## 11.3 Module 4 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M4-D01 | What makes an event culturally significant enough to require a Cultural Brief? | Any event involving traditional, family, community, religious, international or identity-bearing ceremonial requirements |
| M4-D02 | Who owns final cultural correctness? | Relevant cultural authority confirms meaning/custom; Cultural Intelligence Lead integrates; Event Lead approves execution |
| M4-D03 | What cultural information may be reused across events? | Only sourced contextual guidance; re-confirm applicability for each family, institution, place and occasion |
| M4-D04 | What requires mandatory stop-and-verify? | Royal/palace procedure, sacred/religious practice, chieftaincy rite, greeting mandate, title, prayer, ceremonial object and symbol |
| M4-D05 | How should cultural needs be assigned to guests? | From declaration, authorised context or individual confirmation; never broad-label inference alone |
| M4-D06 | Who may approve ceremonial-object handling and photography? | Recorded custodian/authority for the specific object and occasion |
| M4-D07 | When is a Cultural Experience Concierge mandatory? | International/principal guests or high-complexity multi-cultural events where uncertainty could affect confidence or dignity |
| M4-D08 | What belongs in an international guest briefing? | Only essential, actionable guidance needed for confidence; layered detail available on request |
| M4-D09 | How are interfaith conflicts resolved? | Respect the occasion’s identity, protect each faith, consult authorities and avoid forced equivalence |
| M4-D10 | What religious data may be stored? | Minimum necessary, purpose-limited requirement with restricted access and appropriate consent/legal basis |
| M4-D11 | How should attire be used as operational intelligence? | As an optional/contextual identification aid confirmed by group data, never as sole identity evidence |
| M4-D12 | What blocks cultural readiness? | Unverified high-impact practices/objects, unresolved faith/food/prayer conflicts, missing authority or unbriefed critical staff |
| M4-D13 | How does Maison Doclar distinguish authentic expression from theatre? | Every cultural element must have verified meaning, authority, purpose and appropriate execution |
| M4-D14 | Who may make live cultural corrections? | Named cultural authority or delegated Cultural Intelligence Lead using dignity-preserving correction rules |

## 11.4 Module 5 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M5-D01 | Who qualifies for a VIP handling profile? | Use explicit host/event designation or verified status, relationship, experience, security or principal handling need |
| M5-D02 | Can one guest have multiple VIP reasons? | Yes; store independent dimensions and requirements, never one importance score |
| M5-D03 | Who may designate or remove VIP handling? | Host/authorised client and VIP Experience Lead within policy; sensitive disputes escalate to CEO |
| M5-D04 | What is the minimum viable VIP file? | Only verified data necessary for identity, journey, ownership, critical needs, risk and contingency |
| M5-D05 | How are service/confidential/restricted levels assigned? | Field-level classification by sensitivity, harm, security and operational necessity; default to narrower access |
| M5-D06 | What may enter reusable VIP memory? | Validated service preference with provenance, continuing purpose, appropriate authority/consent, expiry and guest-safe use |
| M5-D07 | How long should event-only and reusable data be retained? | Define distinct schedules by purpose and legal/privacy review; auto-review before expiry |
| M5-D08 | Who can view/export/share each VIP data level? | Role- and field-scoped access; no blanket spreadsheet or group distribution |
| M5-D09 | Is continuous location tracking permitted? | No by default; use coarse operational journey state, minimum necessary updates and defined end time |
| M5-D10 | How many VIPs may one Owner handle? | Set event-complexity capacity limits; mandatory deputy for critical guests |
| M5-D11 | What if the VIP rejects visible treatment? | Record visibility preference and deliver quiet excellence without reducing required safety/protocol controls |
| M5-D12 | Which changes require immediate command escalation? | Security, unexpected entourage, privacy/media, principal schedule, seating refusal, early departure and ownership failure |
| M5-D13 | What constitutes VIP readiness? | Approved profile/brief, owner/deputy, journey, access controls, verified dependencies, contingencies and live communication |
| M5-D14 | Who approves relationship or separation intelligence? | Guest/host-authorised source plus restricted review; store only operational instruction where possible |
| M5-D15 | How is recovery authority bounded? | Owners may resolve within approved service limits; reputation, security, protocol or material spend escalates |
| M5-D16 | What may be shared by WhatsApp or consumer messaging? | Only minimum, time-limited operational instructions permitted by communications/security policy |
| M5-D17 | How is “never tell twice” reconciled with privacy? | Reuse verified information only within its purpose and validity; do not collect more merely to avoid asking |
| M5-D18 | What measures VIP success? | Guest effort, continuity, readiness, privacy, recovery and host confidence—not visible fuss or spend |

## 11.5 Module 6 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M6-D01 | Which event classes require a formal Command Centre? | Use risk/complexity thresholds based on scale, sites, vendors, VIPs, ceremony, security and live dependencies |
| M6-D02 | Who is operational commander on event day? | One named Event Director with deputy; CEO retains executive authority without routine bypass |
| M6-D03 | What is the command hierarchy and span of control? | Event-specific structure with one accountable owner per critical function and manageable direct reports |
| M6-D04 | Which documents form the source of truth? | Controlled Master Timeline plus linked released views for programme, run of show, command, vendors and specialist plans |
| M6-D05 | Who may approve and release material changes? | Document owner proposes; Event Director approves operational changes; CEO/specialists approve within reserved authority |
| M6-D06 | What evidence defines Green, Amber and Red? | Objective criteria, current evidence, owner, next action and expiry per operational area |
| M6-D07 | Does the five-minute rule apply to every issue? | No; safety/security/medical and severe reputation issues escalate immediately while containment begins |
| M6-D08 | What decisions are reserved for qualified specialists? | Medical, emergency, security, structural, electrical and other regulated/safety-critical matters |
| M6-D09 | What triggers the T-15 freeze or exception? | Freeze approved baseline; allow only unsafe, incorrect, missing or materially damaging exceptions through change authority |
| M6-D10 | What constitutes go-live approval? | Critical readiness gates passed, residual risks accepted, command operational and emergency routes/authorities confirmed |
| M6-D11 | How are radio and quiet-channel permissions structured? | Role/channel matrix, call signs, sensitivity rules, backup channel and acknowledgement protocol |
| M6-D12 | What handoffs require closed-loop confirmation? | All principal/VIP, safety/security, programme cue, transport, catering and critical dependency transitions |
| M6-D13 | Who may activate Plan B or C? | Named decision owner using pre-approved trigger; safety authorities retain immediate override |
| M6-D14 | How is a trigger defined and monitored? | Metric/source, threshold, observation window, confidence, owner, deadline and activation consequence |
| M6-D15 | How should crowd observations be used? | As privacy-respecting signals requiring contextual validation—not emotion or intent facts |
| M6-D16 | When should the host be informed of an issue? | When host decision, safety, principal experience, reputation or promised outcome materially requires it; otherwise provide controlled assurance |
| M6-D17 | What recovery authority and spend limits apply? | Tiered authority by role, impact and cost with after-action review |
| M6-D18 | How are vendor failures separated from guest recovery? | Recover guest experience immediately; preserve vendor accountability in internal evidence/contract process |
| M6-D19 | What is the freshness standard for live command data? | Set risk-based update intervals and visible stale-state warnings by domain |
| M6-D20 | What metrics define command effectiveness? | Detection, ownership, decision, handoff, recovery, continuity, guest impact and host-intervention measures |

## 11.6 Module 7 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M7-D01 | What distinguishes approved, preferred, conditional, suspended and do-not-use suppliers? | Separate relationship status from event-specific appointment; require evidence, owner, approval and review date |
| M7-D02 | Which vendors require enhanced due diligence? | Use capability criticality, guest impact, safety/regulatory exposure, substitution difficulty, spend and data access—not category name alone |
| M7-D03 | What evidence proves capability? | Recent comparable delivery, operational-lead review, references, capacity/resources, required credentials and tested backup; photographs or sales claims alone are insufficient |
| M7-D04 | Who appoints a vendor? | Vendor & Partnerships Lead recommends; Event Director confirms operating fit; Commercial Approver commits; CEO reserves strategic/reputation exceptions |
| M7-D05 | How are client-nominated or friend vendors governed? | Apply the same minimum access, conduct, privacy, safety, briefing, scope and command controls; record any accepted capability exception |
| M7-D06 | What may a vendor see about guests and VIPs? | Only the minimum role-specific instruction necessary to deliver; restricted identity, relationship, security and preference data remain segregated |
| M7-D07 | What makes a brief accepted? | Named operational lead receives the released version, resolves questions and acknowledges scope, standards, dependencies, authority and contingencies |
| M7-D08 | What must every scope of work contain? | Deliverables, quantities, place, milestones, acceptance evidence, accountable people, dependencies, exclusions, commercials, change rules and contingency |
| M7-D09 | Who may instruct vendors? | One designated Maison Doclar contact per vendor; specialist stop authority and emergency override remain explicit |
| M7-D10 | Who may approve live scope, cost or quality changes? | Role-based limits by impact and spend; affected dependencies and released artefacts must be assessed and updated before implementation where time permits |
| M7-D11 | What blocks vendor readiness? | Missing accountable lead, unaccepted brief/scope, overdue critical milestone, failed inspection, unverified dependency, absent backup, access conflict or unresolved high-risk exception |
| M7-D12 | Who accepts vendor work as guest-ready? | Named Quality/Acceptance Owner using objective evidence; qualified specialists retain safety/regulatory acceptance |
| M7-D13 | How is the score calculated and used? | Retain weighted dimensions and evidence; do not let one average hide a critical failure or automatically appoint/ban a supplier |
| M7-D14 | When is a supplier suspended or removed? | Immediate containment for serious safety, privacy, integrity or guest harm; otherwise evidence-based review with corrective action and approval |
| M7-D15 | Who may activate replacement? | Event Director within pre-approved plan and spend; Commercial/CEO approval for material exposure; specialists may stop unsafe work |
| M7-D16 | What learning becomes institutional memory? | Verified event evidence, context, limitations and review outcome; supplier claims and one-off impressions remain distinguishable |
| M7-D17 | What are the scorecard weights and minimums? | Treat Module 7 weights as provisional; calibrate by capability category and include non-compensable gates for critical dimensions |
| M7-D18 | How are vendor data, references and performance records retained/shared? | Purpose-limited access, fair evidence, review/response process and jurisdiction-appropriate retention/privacy policy |

## 11.7 Module 8 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M8-D01 | Which events require formal ceremony architecture? | Use ceremony complexity and consequence: principals, multiple authority systems, formal movement, cultural/religious acts, speakers, stage cues or material timing dependencies |
| M8-D02 | Who owns the ceremony architecture? | Ceremony Architect designs; Protocol/Cultural authorities validate reserved meaning/order; Event Director approves execution; CEO resolves strategic host-intent conflicts |
| M8-D03 | How are multiple principals represented? | Permit joint or phase-specific principals with explicit protected outcomes and conflict resolution; do not force one person into every moment |
| M8-D04 | Which hierarchy governs each moment? | Record formal, traditional and social/personal authority separately and name the governing authority/context for each ceremonial decision |
| M8-D05 | Who approves the ceremony spine and protected acts? | Host/CEO approves intent; authorised protocol/cultural/religious owner approves reserved content; Event Director approves executable sequence |
| M8-D06 | What is the source-of-truth relationship among timeline, Run of Show, cue sheet and guest programme? | One controlled content model generates role-specific views with explicit ownership, version, release and supersession |
| M8-D07 | Who can issue GO/HOLD? | Named Cue Caller/Event Director within a cue-authority matrix; Security or qualified safety authority retains immediate stop power |
| M8-D08 | What evidence makes a critical cue ready? | Required people positioned, route/space clear, receiving stage ready, equipment/content tested, dependencies confirmed and cue recipients acknowledged |
| M8-D09 | How is the ceremonial clock governed? | One authoritative event time source, synchronisation check, tolerance, owner and fallback; record actual timestamps separately |
| M8-D10 | How are arrival windows set and changed? | Define earliest/ideal/latest from dependencies, host intent, security/protocol and holding capacity; live changes require cascade assessment |
| M8-D11 | When may a ceremony proceed without a late VIP? | Use pre-approved hold/continue logic based on the person’s required role, dignity impact, protected act, latest safe time and authority |
| M8-D12 | What makes a holding area acceptable? | Appropriate access, privacy, comfort, capacity, liaison, route, information and release control; security/safety acceptance where relevant |
| M8-D13 | Who approves titles, pronunciation and introductions? | Protocol verification plus authorised source/person; MC executes only the released sheet and authorised limited improvisation |
| M8-D14 | How are speaking-time limits enforced? | Approved minimum/target/maximum, discreet warning/cutoff method and escalation; do not let automated intervention create public embarrassment |
| M8-D15 | Who approves stage, seat and receiving-line positions? | Protocol/Seating authorities propose within governing context; Experience/Accessibility/Security constraints are reconciled; Event Director releases |
| M8-D16 | What photography rules are mandatory? | Named groups/positions/order, movement zones, restricted moments, privacy/media authority, time limit, cue and release owner |
| M8-D17 | Who classifies programme items as non-negotiable, flexible or removable? | Relevant content authority proposes; Event Director owns operational recovery; host/CEO approval is required for material intent/reputation change |
| M8-D18 | What triggers delay-cascade intelligence? | Forecast breach of a moment’s tolerance, protected dependency, meal/transport/venue deadline, principal window or guest-comfort threshold |
| M8-D19 | Who may shorten, remove or resequence items live? | Pre-delegate by class and consequence; never modify sacred, official, contractual or safety-critical content without its reserved authority |
| M8-D20 | What is the “10-minute rule”? | Use as a scenario-test increment, not a universal operational threshold; calibrate tolerances per moment and event |
| M8-D21 | What prevents ceremony go-live? | Unverified precedence/authority, unapproved spine/Run of Show, missing principal/cue owners, unsafe route/stage, unready protected act, conflicting versions or absent recovery options |
| M8-D22 | How is ceremony performance measured? | Readiness, cue accuracy, movement/handoff completion, variance, dead air, recovery, dignity incidents, guest disruption and principal/host confidence |

## 11.8 Module 9 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M9-D01 | What is the canonical service-standard contract? | Every standard needs stable ID/version, rationale, applicability, requirement/prohibition, owner, evidence, checkpoints, exception authority, training and review state |
| M9-D02 | Which standards apply to a particular event? | Generate applicability from event type, journey, zones, guest needs, dining, VIP/protocol/culture, venue and scope; require owner review before release |
| M9-D03 | Which Module 9 statements are doctrine, standards, heuristics or examples? | Keep master principles as doctrine; encode testable behaviours as standards; treat 3-second, 5-second, one-metre and final-ten-minute language as provisional heuristics |
| M9-D04 | Who approves and changes the Maison Doclar Service Standard? | Service Standards Owner proposes; Guest Experience Lead validates operations; CEO approves doctrine, mandatory thresholds and material exceptions |
| M9-D05 | What constitutes evidence that a standard is planned? | Applicable control, named owner/deputy, resources, zone/touchpoint, checkpoint, acceptance method, contingency and released briefing |
| M9-D06 | What constitutes evidence that a standard was met? | Use the standard’s specified observation, time/event record, inspection, closed-loop handoff or guest-safe confirmation—not a generic checkbox |
| M9-D07 | Who may mark pass, fail or not applicable? | Named owner provides evidence; verifier confirms higher-risk standards; approver controls not-applicable and exception decisions |
| M9-D08 | What blocks service readiness? | Uncovered service zones, unbriefed/unqualified staff, missing request/escalation ownership, unresolved critical comfort/dietary/privacy issues or unaccepted mandatory-standard failures |
| M9-D09 | How is one request → one resolution implemented? | Create one case with continuous ownership, formal transfer acceptance, promised update, resolution evidence, guest follow-up and closure |
| M9-D10 | When may a frontline employee decline a request? | Immediate decline/containment for safety, security, privacy, protocol, law or unavailable authority; offer an approved alternative and escalate as required |
| M9-D11 | What may staff know about guests? | Only minimum actionable instructions for their role/zone; sensitive reason and wider VIP/profile context remain restricted |
| M9-D12 | How are service observations used safely? | Record objective signal and offered assistance, not inferred condition/intent; do not persist a profile unless separately validated and authorised |
| M9-D13 | What response thresholds should be enforced? | Calibrate by zone, request severity and event; treat 3/5-second rules as training targets until measured and approved |
| M9-D14 | How is service-zone coverage calculated? | Use journey demand, line of sight, distances, flow, staff capability, breaks and backup—not a universal one-metre radius |
| M9-D15 | Who owns dietary/allergy correctness? | Guest/authorised source provides requirement; Catering/Food-Safety owner verifies preparation; Dining Lead controls discreet handoff; uncertainty escalates |
| M9-D16 | What restroom and comfort checks are mandatory? | Set event/venue-specific intervals and trigger checks with objective fields, discreet correction and urgent hazard escalation |
| M9-D17 | Who may initiate social bridging? | Trained staff only where context and consent cues make it appropriate; never infer loneliness or disclose private relationship information |
| M9-D18 | Who may approve compensation or recovery spend? | Tiered role/spend/reputation authority; frontline staff may use approved no-cost remedies and immediate comfort actions |
| M9-D19 | When can a service recovery case close? | Resolution delivered, affected dependencies updated, follow-up completed where appropriate and guest outcome recorded without coercing satisfaction |
| M9-D20 | How is lost property governed? | Secure chain of custody, minimum description/access, owner verification, logged handover, retention/disposal policy and escalation for sensitive/valuable items |
| M9-D21 | What proves staff are ready? | Acknowledged briefing plus demonstrated competency for assigned behaviours; role-play, coaching and reassessment scaled to event risk |
| M9-D22 | When does the CEO intervene? | Reserved for principal/high-impact sensitivity, systemic failure, reputation/client relationship, exception authority or executive judgement—not routine requests |
| M9-D23 | How are vendor staff held to Maison Doclar standards? | Standards flow into brief, code, role training, supervision, evidence and scorecard; vendor employment authority remains distinct |
| M9-D24 | What measures meaningful white-glove service? | Ignored/waiting exposure, first ownership, handoff completion, request resolution, anticipation usefulness, privacy/dignity, recovery, final-touch and guest-effort outcomes |

## 11.9 Module 10 decisions

| ID | Decision required | Recommended starting position |
| --- | --- | --- |
| M10-D01 | Does Module 10 create a second command system? | No; it refines and extends the canonical Module 6 system. Duplicate terms map to shared entities, owners and rules |
| M10-D02 | What is the canonical escalation ladder? | Adopt five levels: frontline, supervisor, department lead, Event Director, CEO/executive; specialist immediate authority remains outside ordinal delay |
| M10-D03 | What qualifies as the operational source of truth? | A controlled state store with provenance, version, event time, freshness, conflicting-report handling and role-scoped released views—not one document or chat |
| M10-D04 | Who may write and correct live status? | Named domain owners submit; Operational Picture Controller validates/reconciles; material corrections retain audit and never silently overwrite history |
| M10-D05 | What is the minimum viable operational picture? | Master time, current programme, now/next, key people/movements, lens status, incidents, risks, blockers, pending decisions, freshness and CEO action |
| M10-D06 | How are look-ahead horizons configured? | Support NOW/NEXT/LATER and event-configured horizons; 15/60 minutes are defaults, supplemented by latest-safe-action calculations |
| M10-D07 | What belongs in a CEO briefing? | Status, material issue, impact, action underway, residual exposure and precise decision required; suppress routine detail without hiding uncertainty or bad news |
| M10-D08 | How is live intelligence distinguished from data? | Signal → validated assertion → forecast/conflict → recommendation → human decision → action → verification, each with provenance and state |
| M10-D09 | What makes a signal trustworthy? | Named source, event time, location/domain, verification state, freshness, confidence, sensitivity and conflict handling |
| M10-D10 | When may the system predict a conflict? | When time/route/resource/person/dependency requirements intersect within their uncertainty ranges; show assumptions, confidence and time-to-impact |
| M10-D11 | Who may act on AI intelligence? | AI informs/recommends; named humans decide and command. Only approved low-impact routing/display automation may execute without case approval |
| M10-D12 | How are RAG and radio priority related? | Keep separate: RAG describes state/risk; routine/priority/critical governs message handling. Map them only through explicit rules |
| M10-D13 | What are the canonical RAG criteria? | Domain-specific objective evidence and thresholds with Unknown/stale state; Red is not synonymous with incident or failure |
| M10-D14 | How is consequence prioritised? | Life/safety is non-negotiable; otherwise score severity, urgency, affected people, vulnerability, irreversibility, dignity/protocol, recoverability, confidence and cascade—not loudness |
| M10-D15 | Who can declare and command an incident? | Defined by incident type/severity; Event Director assigns Incident Commander while qualified security/medical/fire/public authorities retain reserved command |
| M10-D16 | When does “solve first, investigate later” apply? | During containment/recovery where delay increases harm; preserve evidence and never defer mandatory reporting, safeguarding or specialist assessment |
| M10-D17 | How are risk, issue and incident separated? | Risk is possible future harm; issue is current variance requiring management; incident is a verified event entering formal response |
| M10-D18 | What is required before Plan B/C activation? | Defined trigger/source, confidence/tolerance, activation owner, resources, downstream effects, communications and reset/closure—except immediate specialist safety action |
| M10-D19 | How is weather intelligence governed? | Use authoritative/local source, location/time horizon, uncertainty and event thresholds; convert forecast into route/space/equipment/guest actions through human approval |
| M10-D20 | How are power, crowd, security and medical signals handled? | General command coordinates; qualified domain owners define thresholds, verification, actions and stop/override authority |
| M10-D21 | What data can the dashboard expose by role? | Minimum necessary operational fields; restricted VIP/security/medical/private requests remain segmented, redacted and audited |
| M10-D22 | How do we prevent alert overload? | Materiality thresholds, deduplication, correlation, suppression, escalation, acknowledgement, role routing and measured false/missed-alert review |
| M10-D23 | What proves a command action succeeded? | Recipient acceptance plus real-world completion/outcome evidence and receiving-stage confirmation; sent/ticked is insufficient |
| M10-D24 | How is intelligence performance measured? | Detection lead time, calibration, conflict accuracy, usefulness, acceptance/action, decision latency, false positives/negatives, missed signals, harm and guest continuity |
| M10-D25 | What happens when live systems fail? | Maintain offline operational picture, printed/controlled essentials, backup time/comms, device/session loss procedures and later reconciliation |
| M10-D26 | What command data becomes organisational learning? | Verified incident/risk/decision/action/outcome evidence with context; retain candidate lessons for approval rather than auto-changing doctrine/models |

## 11.10 Module 11 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M11-D01 | What are the calibrated Lagos-specific probability baselines (rainy-season by month, grid outage frequency, road-closure patterns)? | Requires local operational and meteorological/utility data; 81.2’s 1–5 scale is a method, not a dataset |
| M11-D02 | What are the default weather GREEN/AMBER/RED thresholds per venue type? | Requires venue-by-venue professional advice; no global default proposed |
| M11-D03 | How does the 86.2 crisis scale map to the 76.2 five-level ladder as a single machine-evaluable rule? | RESOLVED. 76.2 is the one canonical mechanism; the crisis scale is a severity label on top of it, with 86.2’s table as the single mapping rule. |
| M11-D04 | Who are the external authorities engaged at Crisis Scale Level 5, and under what trigger? | Requires legal/regulatory/security specialist input per jurisdiction |
| M11-D05 | What are Maison Doclar’s legal/regulatory incident-reporting obligations (insurance, liability, mandatory reporting)? | Requires legal counsel; not addressed by module source |
| M11-D06 | What is the required response-time standard for the Client Communication Lead during a live incident? | Open; module requires single-voice external communication but not a latency standard |
| M11-D07 | Who holds compensation approval authority during an active service-recovery event, and up to what threshold? | Cross-references Module 9’s compensation boundary (68.2); not resolved by either module |
| M11-D08 | What staff welfare standard (rotation, rest, supervision) applies during extended incidents/“incident fatigue”? | Partial (Module 19, 124.3). Relief-coverage requirement and Handover Standard now defined as the mechanism. Numeric standards (shift length, break frequency, maximum consecutive hours) remain unset. |
| M11-D09 | What is the critical-load priority order by event type/venue when backup power is limited? | 83.4 lists categories (emergency lighting, security, communications, production, refrigeration, VIP systems) without a default ranking |
| M11-D10 | Who has authority to activate the Crisis Command Centre and restrict access to it? | 86.3 states access is restricted; owning role not yet named |
| M11-D11 | What evidence standard closes a near-miss record as “reviewed, no action required” versus “learning candidate approved”? | 87.1/87.2 define the review; approval workflow not specified |
| M11-D12 | Should the CEO Master Exercise (nine-issue chieftaincy scenario) be adopted as a formal AI shadow-mode evaluation case? | Flagged as a candidate at 89.3; requires CEO decision to formalise |

## 11.11 Module 12 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M12-D01 | Is the proposed mapping between the fourteen-phase MD-EOS Delivery Lifecycle and the eight-stage Section 6 application lifecycle (91.1) approved as stated? | Proposed here; requires CEO/architecture confirmation before encoding |
| M12-D02 | Should a formal cross-index be built between the five control layers and the six knowledge-architecture layers (91.2)? | Open; not required for either model to function independently, but useful for tooling |
| M12-D03 | What naming convention distinguishes the guest journey (per-guest) from the event operating lifecycle (per-event) to prevent implementation confusion (91.3)? | RESOLVED. Renamed to the MD-EOS Delivery Lifecycle, whose parts are called phases; “stage” is now reserved for the Guest Journey only. |
| M12-D04 | How should a Principal Profile and a VIP Intelligence File be linked when one person qualifies for both (93.2)? | RESOLVED. Shared person identifier via the Principal Profile’s “linked VIP file reference” field (Section 5); shared fields entered once, read by both. |
| M12-D05 | Should event dependency links become a first-class predecessor/successor structure rather than free-text fields (94.1)? | Recommended; not yet approved |
| M12-D06 | How exactly are the Module 12 touchpoint quality test and the Module 2 seven-question/never-ask tests applied together at one touchpoint (94.3)? | Open; risk of duplicated or conflicting checks if not defined |
| M12-D07 | What is the design, ownership, privacy-segregation model and retention policy for the cross-event knowledge base (95.3)? | RESOLVED (Section 123). Five subject registries (Vendor/Guest-VIP already existed; Venue Identity and Pattern Library newly designed); a three-tier privacy model reused from 29.2 governs what may cross client boundaries; nothing is promoted without Knowledge Base Curator second-person review. Retention periods and client-contract language remain open engineering/legal follow-ups (123.7), not design gaps. |
| M12-D08 | What counts as “the system is ready” when specialist readiness gates disagree or one is missing/stale (96.2)? | Open; needs an explicit aggregation rule, not just a checklist |

## 11.12 Module 13 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M13-D01 | Which of the three vendor scorecard category/weight sets (Section 53.4) becomes the single canonical scorecard? | RESOLVED. The original Module 7 scorecard is canonical, with “value” added as an eighth field (Section 5). The two Module 13 scorecard variants are retired. |
| M13-D02 | Should the Module 13 Vendor Pyramid be folded into the existing Approval State dimension rather than kept as a separate model? | RESOLVED. Folded into Approval State (48.2): Strategic Partners/Preferred->Preferred, Approved->Approved, Probationary/New->Conditional. Pyramid retired as a separate model. |
| M13-D03 | What are the commercial authority limits, deposit rules and emergency payment/replacement approval thresholds? | RESOLVED IN STRUCTURE (49.2.2-49.2.3). Commercial authority reuses the 76.2 ladder, with like-for-like emergency vendor replacement as unconditional Event Director authority (distinct from net-new spend). Payment ties to the milestone chain with a review-linked final retention. Exact percentage caps and payment splits remain event-specific parameters, not global defaults, defaulting to CEO approval until set per event. |
| M13-D04 | Who holds authority to downgrade or remove a vendor under the 48.6 pattern criteria, and what appeal rights exist? | Open; criteria now defined, governance process is not |

## 11.13 Module 14 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M14-D01 | Which single acknowledgement-time target is correct: Module 9’s “~3 seconds,” Module 9’s “~5 seconds,” or Module 14’s “10 seconds” (Section 103)? | RESOLVED. CEO selected 5 seconds as the canonical acknowledgement target (64.1, 62.0). 3-second and 10-second variants retired. |
| M14-D02 | What is the recruitment sourcing, vetting and background/right-to-work check process? | RESOLVED IN DESIGN (142.3). Provisional pending employment-counsel sign-off. |
| M14-D03 | What is Maison Doclar’s employment classification model (staff/contractor/agency) and labour-law compliance approach? | RESOLVED (142.2). Control test adopted as binding policy, effective immediately. |
| M14-D04 | What is the formal training curriculum, delivery method and certification-expiry tracking system? | Restates Module 9 gap (70.5); still open |
| M14-D05 | What is the performance-review cadence, promotion and retention model beyond a single event? | Open; neither Module 9’s competency model nor Module 14’s maturity model addresses this |
| M14-D06 | What is the formal HR disciplinary/grievance process and appeal right? | RESOLVED IN DESIGN (142.6). Provisional pending employment-counsel sign-off. |
| M14-D07 | What safeguarding policy applies to events involving minors or vulnerable guests? | RESOLVED. Operational child-safeguarding policy: guardian-authority verification (Responsible Adult, release rule, two-person rule) and minor photography opt-in consent (120.5.1-120.5.2). Scope limited to private events with accompanying children, not a standalone childcare service (120.5.3). |
| M14-D08 | What governs staff personal-data privacy (performance data, background-check results, retention)? | Open; needs HR/privacy governance |
| M14-D09 | What are the compensation, payroll and overtime rules? | RESOLVED IN DESIGN (142.4). Provisional pending employment-counsel sign-off and current statutory-rate confirmation. |
| M14-D10 | What staff insurance and liability coverage applies? | RESOLVED IN DESIGN (142.7). Provisional pending employment-counsel sign-off. |
| M14-D11 | What work-authorisation process applies for international staff deployment? | RESOLVED IN DESIGN (142.7). Provisional pending employment-counsel sign-off. |
| M14-D12 | What diversity, equity and inclusion standard applies to hiring? | RESOLVED IN DESIGN (142.8). Provisional pending employment-counsel sign-off. |
| M14-D13 | Should a formal rule link the Module 14 maturity model (104.4) to Module 9’s per-standard competency states (69.1)? | Open; no linkage currently defined |

## 11.14 Module 15 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M15-D01 | What WhatsApp Business API, and what data-retention/consent policy, governs guest-facing concierge messaging? | Outside module authority; needs legal/vendor-selection ownership |
| M15-D02 | What response-time SLA applies per enquiry class or guest segment? | Open; principle stated (“silence creates uncertainty”), no number set |
| M15-D03 | Does firm-boundary phrasing (e.g. “adults-only celebration”) need legal/tact review before use as an approved template? | Open; minor but real |
| M15-D04 | Who is the named decision authority for family-hierarchy guest-experience conflicts (115.1)? | RESOLVED. Pre-event: Principal-designated Family Decision Owner (Principal Profile field). Live fallback: Event Director (76.2 Level 4), same routing discipline as the existing 49.3 rule. |
| M15-D05 | Should the logistics (this module) and cultural (Module 4) international-guest briefs merge into one delivered document? | RESOLVED. Merged into one International Guest Brief (Logistics + Culture sections), delivered together. |
| M15-D06 | What feedback-survey platform/tool is used for post-event feedback? | Outside module authority; vendor-selection matter |

## 11.15 Module 16 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M16-D01 | Should Module 16’s four-level Incident Priority scale be retired in favour of the existing five-level Crisis Scale (86.2)? | RESOLVED. Incident Priority retired; event-day incident severity routes through the 86.2 Crisis Scale, with “no guest impact” as a Level 1 qualifier. |

## 11.16 Module 17 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M17-D01 | Who is the named Security Override Authority for a given event? | RESOLVED. Default is the Security Lead, named on the Master Event File; falls back to Event Director if unreachable. Never the Family Decision Owner, never informal CEO/family override (120.4). |

## 11.17 Module 18 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M18-D01 | Should Communication, Timeliness and Flexibility be added to the canonical Supplier scorecard, and should its scale be standardised to /10? | RESOLVED. Three fields added; scale standardised to /10 across all fields; field set closed to further proposals (52.5, Section 5). |

## 11.18 Module 19 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M19-D01 | What governs staff personal-data privacy (retention, access, correction rights) now that the Staff Talent Record (124.6) makes this a live system rather than a hypothetical? | RESOLVED IN DESIGN (142.5). Lawful-basis categories, retention table and breach protocol defined. Provisional pending employment-counsel sign-off. |
| M19-D02 | Who owns curriculum design and refresh cadence for the training content areas now defined (124.4), and what certification/expiry tracking applies? | Partial resolution only; content and rehearsal method exist, ownership and tracking system do not |
| M19-D03 | What is the review cadence, promotion criteria and compensation-progression policy for staff tracked in the Talent Record (124.6)? | Partial resolution only; the persistence mechanism now exists, the HR policy governing it does not |

## 11.19 Module 20 decisions

| ID | Question | Direction |
| --- | --- | --- |
| M20-D01 | Who is named AI Systems Owner (8.0.9, 131.2), and when is the Anthropic API integration actually built against this design? | RESOLVED (role). CEO named as AI Systems Owner (8.0.9). Technical build timing remains open. |
| M20-D02 | When is the AI shadow-mode/evaluation capability built (first flagged at Module 10, Section 79) so AI outputs can be tested against known-good human judgement before being trusted live? | RESOLVED IN DESIGN (144). Architecture, acceptance criteria, test-case library and ownership (CTO + Protocol Director + external validator) defined. Implementation not started — this remains a launch-blocking precondition, not a completed item. |

# 12. Initial repository representation

Proposed logical structure:

- knowledge/doctrine/white-glove-hospitality.yaml

- knowledge/doctrine/protocol-and-dignity.yaml

- knowledge/doctrine/cultural-intelligence.yaml

- knowledge/doctrine/vip-discretion-and-ownership.yaml

- knowledge/doctrine/event-command.yaml

- knowledge/frameworks/five-layer-experience-model.yaml

- knowledge/frameworks/anticipation-levels.yaml

- knowledge/frameworks/friction-taxonomy.yaml

- knowledge/frameworks/guest-journey-model.yaml

- knowledge/frameworks/precedence-assessment-model.yaml

- knowledge/frameworks/cultural-authority-model.yaml

- knowledge/frameworks/vip-handling-model.yaml

- knowledge/frameworks/command-authority-model.yaml

- knowledge/frameworks/rag-and-priority-model.yaml

- knowledge/frameworks/closed-loop-handoff-model.yaml

- knowledge/journey-templates/base-event.yaml

- knowledge/journey-variants/

- knowledge/protocol/forms-of-address/

- knowledge/protocol/authoritative-sources/

- knowledge/protocol/institution-packs/

- knowledge/protocol/event-templates/

- knowledge/culture/context-packs/

- knowledge/culture/ceremonial-objects/

- knowledge/culture/religious-observances/

- knowledge/culture/briefing-templates/

- knowledge/vip/profile-schema/

- knowledge/vip/preference-taxonomy/

- knowledge/vip/brief-views/

- knowledge/vip/contingencies/

- knowledge/command/timeline-schemas/

- knowledge/command/status-criteria/

- knowledge/command/communication-templates/

- knowledge/command/contingency-triggers/

- knowledge/command/readiness-gates/

- knowledge/rules/experience/

- knowledge/rules/transitions/

- knowledge/rules/protocol/

- knowledge/rules/cultural-intelligence/

- knowledge/rules/vip-intelligence/

- knowledge/rules/event-command/

- knowledge/playbooks/invisible-choreography/

- knowledge/playbooks/protocol-corrections/

- knowledge/playbooks/cultural-bridging/

- knowledge/playbooks/vip-recovery/

- knowledge/playbooks/event-recovery/

- knowledge/context-packs/global/

- knowledge/context-packs/nigeria/

- knowledge/context-packs/lagos/

- knowledge/governance/data-classification.yaml

- knowledge/governance/access-and-retention.yaml

- knowledge/governance/decision-rights.yaml

- knowledge/governance/

- knowledge/schemas/

## 12.0.1 Module 7 repository additions

- knowledge/doctrine/vendor-ecosystem.yaml

- knowledge/vendors/profile-schema/

- knowledge/vendors/capability-evidence/

- knowledge/vendors/classification-and-status/

- knowledge/vendors/due-diligence/

- knowledge/vendors/brief-templates/

- knowledge/vendors/scope-and-change/

- knowledge/vendors/inspection-templates/

- knowledge/vendors/scorecards/

- knowledge/vendors/contingencies/

- knowledge/rules/vendor-intelligence/

- knowledge/playbooks/vendor-recovery/

- knowledge/vendors/partner-code.yaml (Module 13)

- knowledge/vendors/due-diligence-interview-protocol/ (Module 13)

- knowledge/vendors/inspection-techniques/ (Module 13)

- knowledge/vendors/mockup-approval-milestones/ (Module 18)

- knowledge/vendors/recovery-ladder/ (Module 18)

- knowledge/vendors/six-p-evaluation-frame/ (Module 18)

## 12.0.2 Module 8 repository additions

- knowledge/doctrine/ceremony-as-movement.yaml

- knowledge/frameworks/ceremony-architecture-model.yaml

- knowledge/frameworks/cue-and-go-hold-model.yaml

- knowledge/ceremony/control-sheet-schema/

- knowledge/ceremony/run-of-show-schema/

- knowledge/ceremony/cue-sheet-views/

- knowledge/ceremony/movement-matrices/

- knowledge/ceremony/holding-and-receiving/

- knowledge/ceremony/speaker-and-mc/

- knowledge/ceremony/photography-groups/

- knowledge/ceremony/transition-and-buffer/

- knowledge/ceremony/recovery/

- knowledge/rules/ceremony-command/

- knowledge/playbooks/ceremony-recovery/

## 12.0.3 Module 9 repository additions

- knowledge/doctrine/white-glove-service.yaml

- knowledge/standards/service/standard-contract.schema.yaml

- knowledge/standards/service/master-principles.yaml

- knowledge/standards/service/guest-facing-behaviour/

- knowledge/standards/service/language-and-discretion/

- knowledge/standards/service/zones-and-positioning/

- knowledge/standards/service/greeting-escort-seating/

- knowledge/standards/service/dining-and-dietary/

- knowledge/standards/service/restroom-and-comfort/

- knowledge/standards/service/requests-and-recovery/

- knowledge/standards/service/departure-and-lost-property/

- knowledge/standards/service/staff-competencies/

- knowledge/service/applicability-rules/

- knowledge/service/briefing-views/

- knowledge/service/assurance-checkpoints/

- knowledge/playbooks/service-recovery/

## 12.0.4 Module 10 repository additions

- knowledge/doctrine/live-command-intelligence.yaml

- knowledge/frameworks/operational-picture-model.yaml

- knowledge/frameworks/signal-to-action-model.yaml

- knowledge/frameworks/consequence-priority-model.yaml

- knowledge/command/operational-picture-schema/

- knowledge/command/lens-status-schema/

- knowledge/command/lookahead-rules/

- knowledge/command/situation-report-templates/

- knowledge/command/radio-message-contract/

- knowledge/command/risk-indicators/

- knowledge/command/incident-taxonomy/

- knowledge/command/dashboard-access-views/

- knowledge/intelligence/assertion-schema/

- knowledge/intelligence/prediction-contract/

- knowledge/intelligence/conflict-and-cascade-rules/

- knowledge/intelligence/evaluation/

- knowledge/playbooks/offline-command-continuity/

## 12.0.5 Module 11 repository additions

- knowledge/doctrine/risk-and-crisis.yaml

- knowledge/frameworks/risk-scoring-model.yaml

- knowledge/frameworks/incident-vs-crisis-test.yaml

- knowledge/frameworks/crisis-scale-reconciliation.yaml

- knowledge/risk/register-schema/

- knowledge/risk/decision-triggers/

- knowledge/risk/weather-thresholds/

- knowledge/risk/critical-load-registers/

- knowledge/crisis/command-centre-protocol/

- knowledge/crisis/log-schema/

- knowledge/crisis/communication-templates/

- knowledge/service/recovery-ledger-schema/

- knowledge/rules/risk-and-crisis/

- knowledge/playbooks/domain-incident-response/

- knowledge/playbooks/after-action-review/

## 12.0.6 Module 12 repository additions

- knowledge/doctrine/event-operating-system.yaml

- knowledge/frameworks/event-lifecycle-model.yaml

- knowledge/frameworks/control-layer-model.yaml

- knowledge/frameworks/guest-segmentation-taxonomy.yaml

- knowledge/master-event-file/schema/

- knowledge/master-event-file/event-id-registry/

- knowledge/event-protection-principles/

- knowledge/principal/profile-schema/

- knowledge/guest/priority-matrix/

- knowledge/dependency/event-dependency-map/

- knowledge/sops/

- knowledge/readiness/system-readiness-aggregation/

- knowledge/risk/known-unknowns-register/

- knowledge/reporting/client-debrief-templates/

- knowledge/reporting/event-report-templates/

- knowledge/intelligence/cross-event-knowledge-index/

- knowledge/intelligence/venue-identity-registry/ (M12-D07)

- knowledge/intelligence/pattern-library/ (M12-D07)

- knowledge/governance/knowledge-base-privacy-segregation.yaml

- knowledge/governance/cross-client-privacy-tier-model.yaml (M12-D07)

- knowledge/governance/knowledge-promotion-path.yaml (M12-D07)

## 12.0.7 Module 14 repository additions

- knowledge/doctrine/service-culture.yaml

- knowledge/frameworks/staff-maturity-model.yaml

- knowledge/staffing/team-architecture-templates/

- knowledge/staffing/raci-templates/

- knowledge/staffing/role-cards/

- knowledge/staffing/positioning-map-schema/

- knowledge/staffing/hiring-interview-protocol/

- knowledge/staffing/recognition-accountability/

- knowledge/staffing/wellbeing-planning/

- knowledge/staffing/communication-code-registry/

- knowledge/governance/staff-hr-scope-boundary.yaml

## 12.0.8 Module 15 repository additions

- knowledge/doctrine/guest-communication.yaml

- knowledge/communication/invitation-templates/

- knowledge/communication/rsvp-schema/

- knowledge/communication/confirmation-reminder-cadence/

- knowledge/communication/message-hierarchy-templates/

- knowledge/concierge/intelligence-pack-schema/

- knowledge/concierge/channel-governance/

- knowledge/rules/family-authority-escalation/

- knowledge/governance/guest-messaging-consent.yaml

## 12.0.9 Module 17 repository additions

- knowledge/doctrine/safety-security-privacy.yaml

- knowledge/frameworks/protection-model-people-place-info-reputation.yaml

- knowledge/security/access-zoning-schema/

- knowledge/security/authority-matrix/

- knowledge/security/lost-child-protocol/

- knowledge/security/security-audit-scorecard/

- knowledge/governance/child-safeguarding-scope-boundary.yaml

## 12.0.10 Module 19 repository additions

- knowledge/staffing/handover-standard/

- knowledge/staffing/training-content-and-rehearsal-scenarios/

- knowledge/staffing/staff-performance-scorecard/

- knowledge/staffing/talent-record-schema/

- knowledge/governance/staff-data-privacy-scope-boundary.yaml

## 12.0.11 Module 20 repository additions

- knowledge/doctrine/ai-layer-operating-philosophy.yaml

- knowledge/ai/command-loop-role-mapping.yaml

- knowledge/ai/grounding-and-confidence-tiers.yaml

- knowledge/ai/capability-boundary-2026.yaml

- knowledge/ai/output-audit-trail-schema/

- knowledge/governance/ai-systems-owner-scope.yaml

- knowledge/rules/message-priority-taxonomy.yaml

- knowledge/ai/consult-capability-schema/ (134)

- knowledge/ai/authority-tagging-rules.yaml (134.2)

- knowledge/doctrine/judgement-case-library/ (139.3)

- knowledge/doctrine/decision-frameworks.yaml (six-dimension model, smallest-effective-intervention, escalation test)

- knowledge/host/authority-map-schema/ (140.2)

- knowledge/host/host-brief-template/ (140.3)

- knowledge/host/time-budget-schema/ (140.3)

- knowledge/host/principal-suite-access-rules/ (140.3)

- knowledge/host/host-journey-model.yaml (140.5)

- knowledge/host/host-debrief-template/ (140.6)

## 12.0.12 Module 21 repository additions

- knowledge/execution/readiness-t24-checklist.yaml

- knowledge/execution/four-state-status-model.yaml

- knowledge/execution/first-guest-test.yaml

- knowledge/doctrine/energy-curve.yaml

- knowledge/execution/guest-experience-pulse-schema/

- knowledge/execution/imperfection-triage-model.yaml

- knowledge/execution/lost-property-schema/

- knowledge/reporting/event-score-schema/

## 12.0.13 Staffing/Protocol/AI-validation gap-closing additions (Sections 142–144)

- knowledge/staffing/policy-framework/ (Provisional, 142)

- knowledge/staffing/vetting-schema/

- knowledge/staffing/disciplinary-schema/

- knowledge/staffing/statutory-compliance-tables.yaml

- knowledge/protocol/nigerian-precedence-register/ (Provisional, verification-required-per-event, 143)

- knowledge/protocol/edge-case-rules.yaml (143.2)

- knowledge/ai/shadow-mode-harness-architecture.yaml (144)

- knowledge/ai/test-case-library/ (144.3)

- knowledge/ai/divergence-reports/

- knowledge/governance/employment-counsel-signoff-tracking.yaml

## 12.1 Minimum executable rule contract

- Stable ID and semantic version

- Title and purpose

- Source module and source passage

- Status and owner

- Applicable principles and scope

- Conditions and required data

- Outputs and explanation template

- Confidence and severity logic

- Approval and execution authority

- Effective date, supersession and audit history

# 13. Canonical guest-journey operating model

## 13.1 Default journey stages

| # | Stage | Primary guest need | Required operating outcome |
| --- | --- | --- | --- |
| 1 | Invitation | Clarity and appropriate tone | Guest understands host, occasion, time, place, expectations, response method and transferability |
| 2 | RSVP | Ease and consideration | Response and only experience-relevant needs are captured once |
| 3 | Confirmation | Assurance | Guest knows they are expected and understands the next required action |
| 4 | Pre-event preparation | Confidence | Identity, arrival, reception, destination, seating, needs and ownership are sufficiently prepared |
| 5 | Journey to venue | Navigation and certainty | Route, ETA, access, communication and contingencies are controlled |
| 6 | Arrival | Recognition and immediate direction | First 60–90 seconds answer where, who, destination and next step |
| 7 | Reception | Welcome and confidence | Guest feels expected and is transferred to the appropriate path |
| 8 | Orientation | Environmental understanding | Guest can locate relevant spaces and services without feeling lost |
| 9 | Seating | Correct placement, comfort and respect | Verified assignment respects approved hospitality and protocol requirements |
| 10 | Programme | Flow and understanding | Guest understands what is happening, what follows and when movement is required |
| 11 | Dining | Comfort and seamless service | Menu, sequence, timing, requirements, clearing and beverage service are coordinated |
| 12 | Interaction | Connection and consistent hospitality | Staff and curated interactions support warmth, relevance and dignity |
| 13 | Departure | Ease and a strong final impression | Vehicle, belongings, escort, farewell, security and onward journey are coordinated |
| 14 | Follow-up | Appreciation and appropriate continuity | Approved thanks, media, feedback or keepsake closes or extends the relationship |

Stages are a canonical vocabulary, not a compulsory linear script. An event journey template may omit, repeat, branch or add stages, but every variation requires an explicit reason and must preserve traceability.

## 13.2 Guest Journey Map record

| Field group | Required fields |
| --- | --- |
| Identity | Journey ID; event; guest/segment; journey template/version; owner; status |
| Stage context | Stage; objective; entry/exit criteria; planned/actual timing; current state |
| Guest perspective | Needs; knows; does not know; intended emotion; possible confusion, embarrassment, delay, importance and neglect |
| Touchpoint | Channel/person/environment; content/action; promise; visibility; owner; outcome |
| Transition | Origin; destination; trigger; handoff; receiving readiness; duration; dependencies; route |
| Friction | Scenario; cause; severity; likelihood; confidence; affected dimensions; prevention; contingency; residual risk |
| Execution | Responsible role; deadline; status; evidence; escalation; failure substitute |
| Measurement | Success measure; target; observed result; guest feedback; learning candidate |

## 13.3 Stage intelligence cycle

- Select the applicable journey template and assign only justified variants.

- Assess data sufficiency and label missing facts, assumptions and confidence.

- Run the seven-question test for each material stage, touchpoint and transition.

- Score friction and identify every “never ask” question.

- Generate preventive requirements, contingency actions and responsible owners.

- Verify receiving-stage readiness before critical handoffs.

- Monitor actual state and deviation during production.

- Capture outcomes and propose learning for authorised review.

## 13.4 Transition control contract

Every material transition must specify: origin state; destination state; movement trigger; who releases the guest; who receives the guest; readiness confirmation; route or channel; expected duration; dependencies; guest cue; contingency; escalation; and completion evidence.

**CONTINUITY RULE No critical transition is complete merely because the

releasing team has finished. Completion requires the guest to be

received into the intended next state.**

## 13.5 Communication intelligence

- Every message must have a purpose, audience, approved content version, channel, sender, timing and expected response.

- The system must track delivery, acknowledgement, response and unresolved uncertainty separately.

- A message creates an operational promise; downstream teams must be able to see and fulfil that promise.

- Communication should be segmented where needs differ, but dignity and privacy remain universal.

- Do not collect information merely because a form can ask for it; every field requires an experience purpose.

## 13.6 Measurement model

| Measure class | Examples | Caution |
| --- | --- | --- |
| Operational | Wait time; transition duration; delivery; response; seating accuracy; vehicle readiness | Completion alone does not prove a good experience |
| Guest effort | Questions asked; repetitions; searches; unnecessary decisions; host interventions | Differentiate genuine enquiry from design failure |
| Emotional evidence | Self-reported confidence; complaint; compliment; observed hesitation with context | Do not present inferred emotion as fact |
| Continuity | Missed handoff; receiving readiness; deviation; recovery time | Measure end-to-end, not department-by-department |
| Relationship | Follow-up delivery; consented feedback; referral or future engagement | Do not equate contact frequency with relationship quality |

# 14. Journey segmentation and variants

**SEGMENTATION RULE Archetypes are planning lenses, not permanent

identities. Assign journey requirements from verified needs, roles and

context; one guest may require several lenses.**

| Planning lens | Priorities | Distinct knowledge/data requirements |
| --- | --- | --- |
| VIP guest | Recognition; speed; privacy; personalisation | Confirmation authority; contact; arrival; reception; escort; seating; protocol; departure; privacy |
| Royal guest | Protocol; precedence; cultural respect; ceremony | Institution/title; forms of address; receiving party; greeting order; entourage; procession; seating; photography |
| Government dignitary | Protocol; security; time; formality | Office/rank; precedence; security/convoy liaison; arrival window; speaking role; media; departure |
| International guest | Clarity; orientation; cultural intelligence; comfort | Travel; language; first-visit context; transport; local customs; dress; titles; security; accommodation |
| Elder / senior guest | Dignity; comfort; access; respect | Voluntarily provided needs; distance; stairs/lifts; waiting; temperature; toilets; noise; seating; transport |
| Principal family member | Protection; confidence; emotional participation | Decision role; guest role; protected time; delegated authority; escalation filter; programme obligations |

## 14.1 Segmentation safeguards

- Do not infer needs solely from age, title, nationality or social status.

- Separate protocol precedence from hospitality dignity and service need.

- Do not make accessibility support feel medicalised or patronising.

- Do not expose security or personal data merely because a guest is placed in a planning segment.

- A guest may move between journey variants as role, context or verified needs change.

- All journey variants inherit the universal Maison Doclar dignity floor.

# 15. Module 2 knowledge relationships and gap analysis

## 15.1 Relationship to Module 1

| Module 1 foundation | Module 2 operationalisation |
| --- | --- |
| Anticipation | Seven-question test and pre-event preparation |
| Effortlessness | Never-ask test and guest-effort measures |
| Invisible choreography | Touchpoint, transition and handoff control |
| Five-layer model | Stage-by-stage function, comfort, emotion, personalisation and memory |
| Friction audit | Journey-stage taxonomy and 0–5 severity scale |
| Recognition / dignity / privacy | Segmented journeys with universal safeguards |
| Host confidence | Principal-family journey and escalation protection |

## 15.2 Knowledge delegated to later modules

- Seating precedence and placement logic — Module 3 or specialist protocol knowledge.

- Royal, government and religious protocol — specialist protocol modules.

- Security operations and convoy handling — authorised security knowledge.

- Accessibility standards and medical response — specialist/legal knowledge.

- Dining-service standards — catering and service choreography module.

- Communication copy standards, channel rules and response service levels — future communications module.

- Detailed arrival, transport, departure and airport playbooks — future logistics modules.

- Relationship management, consent and retention — governance/CRM knowledge.

## 15.3 Explicit gaps identified

- No formal definition yet exists for material touchpoints and transitions.

- The fourteen stages have no approved minimum data-completeness thresholds.

- The friction scale lacks approved likelihood and residual-risk matrices.

- Success measures are illustrative; targets and service levels remain undefined.

- The six archetypes are not exhaustive and need composable assignment rules.

- Emotion requires an evidence taxonomy to prevent overconfident inference.

- Live journey-state capture frequency and operating channels are not yet defined.

- Follow-up authority, consent, ownership and relationship boundaries remain unresolved.

- Fallback ownership is required when the named responsible person fails or becomes unavailable.

- Journey templates need event-type, service-tier and locale versioning.

# 16. Nigerian protocol intelligence framework

**PROTOCOL DOCTRINE Protocol is the architecture of respect;

hospitality makes that architecture feel natural. Protocol preserves

institutions and dignity, manages contextual precedence and prevents

avoidable embarrassment.**

**PROTOCOL FORMULA Protocol = status + context + precedence +

ceremony + dignity**

## 16.1 Multiple-authority model

| Authority system | Illustrative offices or roles | Control rule |
| --- | --- | --- |
| Political / constitutional | Federal, state and local officeholders | Verify current office, level, representative status and applicable official guidance |
| Traditional | Rulers, title holders, councils and royal families | Institution-, territory- and occasion-specific; consult designated customary authority |
| Diplomatic | Ambassadors, high commissioners, consuls and mission representatives | Verify mission, rank, accreditation, title and mission/protocol guidance |
| Religious | Christian, Muslim and other recognised religious offices | Verify denomination/body, office, jurisdiction, seniority and ceremonial role |
| Military / security | Military, police and paramilitary leadership | Verify service, current rank, representation and authorised security requirements |
| Institutional | Judiciary, academia, public institutions and corporations | Distinguish office authority from social prominence and event role |
| Family / community | Family heads, elders, in-laws and community representatives | Document event-specific authority with host/family confirmation |
| Social prominence | Business leaders, philanthropists, celebrities and media figures | May shape hospitality or host relevance; never automatically creates formal precedence |

**NON-EQUIVALENCE RULE Authority, rank, wealth, fame, title,

relationship and ceremonial importance are distinct dimensions. The

system must never collapse them into a popularity or importance

score.**

## 16.2 Five-dimensional precedence model

| Dimension | Question | Evidence requirement |
| --- | --- | --- |
| Office | What formal position does the person currently hold? | Current official or institutional verification |
| Rank | What recognised precedence attaches in this context? | Applicable authoritative hierarchy or protocol advice |
| Institution | What body, territory, mission, palace, faith, family or organisation is represented? | Confirmed institution and jurisdiction |
| Relationship | Why is the person important to this host and event? | Host/event evidence, not public profile alone |
| Ceremonial role | What function does the person perform today? | Approved programme and occasion architecture |

The model produces a contextual treatment proposal, not an automatic universal ranking. A person may score highly on one dimension and have no claim on another.

## 16.3 Three event authorities

| Authority | Definition | Required data |
| --- | --- | --- |
| Host | Person or entity that owns or convenes the occasion | Identity; mandate; delegated decision authority |
| Principal | Person, institution or purpose primarily honoured or centred | Identity; role; relevant tradition/office; programme significance |
| Highest relevant precedence guest | Guest with the greatest applicable protocol status in this occasion | Verified status; context; participation capacity; governing source |

These may be three different people. The event protocol profile must identify all three before seating, receiving, introductions, speaking order or ceremonial movement is approved.

## 16.4 Formal and ceremonial precedence

| Type | Meaning | Application |
| --- | --- | --- |
| Formal precedence | Recognised hierarchy attached to an office, rank, honour or institution | Use only where applicable and currently verified |
| Ceremonial precedence | Order appropriate to the purpose and architecture of the occasion | Designed from host, principal, institution, role, event type and governing custom |
| Hospitality treatment | How recognition, comfort, privacy and dignity are delivered | May vary without pretending to change formal rank |

**CONTEXT RULE There is no universal Nigerian seating or recognition

order suitable for every event. Research and authorised consultation

precede execution.**

## 16.5 Protocol conflict-resolution sequence

- Identify what gives each person authority or status.

- Identify the true purpose and ownership of the occasion.

- Identify each person’s ceremonial role for this event.

- Verify applicable formal or institutional precedence using current authoritative evidence.

- Consult the relevant palace, mission, office, religious body, family or institutional authority where required.

- Design the most dignified solution, using separate arrival, reception, seating, speaking, photography or departure structures where necessary.

- Document rationale, approvals, residual sensitivities and contingencies.

- Release one controlled protocol version to authorised operators.

**CONFLICT PRINCIPLE The objective is not to manufacture a winner and

loser. It is to recognise each form of authority appropriately without

diminishing another guest.**

# 17. Protocol operating controls

## 17.1 Title and form-of-address verification

Before an important name appears publicly or is spoken ceremonially, the verification chain is: name → spelling → current office → title → honours/post-nominals → institution/jurisdiction → preferred direct address → introduction form → pronunciation → ceremonial role.

| Control | Required treatment |
| --- | --- |
| Source | Record issuing institution or authorised contact; do not rely on memory or stale messages |
| Currentness | Apply expiry and re-verification based on how changeable the office/title is |
| Two forms | Store introduction wording separately from direct-address wording |
| Pronunciation | Record phonetic and, where useful, audio guidance confirmed by a reliable source |
| Publication gate | Prevent print, display, MC cue or outbound message until required approval state is met |
| Change propagation | A verified update must flag every programme, card, screen, brief, cue and seating artefact that uses it |

## 17.2 Arrival, receiving and advance controls

| Control area | Minimum operational knowledge |
| --- | --- |
| Arrival | Expected window; vehicle; driver/contact; entourage; security; entrance; holding; destination; departure |
| Receiving line | Participants; order; positions; introduction flow; photography; interaction duration; congestion capacity |
| Simultaneous arrivals | Priority logic; parallel reception; holding options; deputies; security and dignity safeguards |
| Advance | Route; entrance; parking; security; venue; seating; holding; toilets; communications; signage; lighting; photography; emergencies |
| Escort | Guest destination, purpose, next receiver, seat, movement cues, meetings, departure and fallback owner |

**ARRIVAL RULE An important arrival must never surprise the operation.

The advance converts uncertainty into verified information, and the

escort preserves continuity until the next owner receives the guest.**

## 17.3 Procession and ceremonial movement

Every procession or formal movement must define order, spacing, escorts, music, announcement, route, destination, positioning, seating, cues, timing, accessibility, photography, security and contingency. Every movement requires a documented ceremonial or operational reason.

## 17.4 Seating intelligence

Seating is visual protocol and a guest-experience control. It must reconcile applicable precedence with event purpose, relationships, comfort, accessibility, security and dignity.

| Decision dimension | Required questions |
| --- | --- |
| Identity and authority | Who is the guest, what do they represent and what precedence applies here? |
| Occasion relationship | What role and relationship do they have to the host, principal and ceremony? |
| Adjacency | Who should they sit beside, and which pairings require separation or review? |
| Experience | What comfort, access, language, dietary, sightline, sound or interaction needs apply? |
| Exposure | What security, privacy, media, photography or political sensitivity exists? |
| Resilience | What happens if the seat is occupied, refused, added, moved or rendered unavailable? |

Sensitive adjacency reasons must use need-to-know access. The guest-facing seat plan should never expose private conflict, religion, health, political sensitivity or other restricted rationale.

## 17.5 Introductions, speaking order and MC control

- Every significant introduction is written, ordered, verified and rehearsed before use.

- The MC manages energy, communication and audience engagement; the Protocol Lead controls precedence, address, dignitary handling and approved order.

- Speaking order communicates precedence, respect, authority and narrative, and must be agreed before publication.

- The MC must not independently change who speaks, who is introduced first, where dignitaries sit or how they are addressed.

- Live changes require an authorised cue/version and discreet communication to all affected operators.

## 17.6 National symbols and official emblems

Flags, coats of arms, anthems, state symbols and official emblems are governed artefacts, not decorative assets. Their use requires authoritative verification of display, order, positioning, wording, timing and approval. The system should block unverified deployment and record the responsible authority.

## 17.7 Institutional consultation rules

| Context | Primary consultation requirement |
| --- | --- |
| Traditional / royal | Palace or designated traditional protocol authority for the specific institution, territory and occasion |
| Government | Current office/protocol contact and applicable official guidance; establish official versus private attendance |
| Diplomatic | Mission or appropriate protocol authority for mission, rank, accreditation, title, spouse/partner treatment, flags and security |
| Religious | Relevant religious body or authorised representative for office, seniority, address and ceremonial expectations |
| Family / community | Host-designated family head or authorised representative for hierarchy, roles and sensitivities |
| Military / security | Authorised institutional/security liaison for rank, representation, access and protection requirements |

# 18. Protocol intelligence products and readiness

## 18.1 Protocol Brief

| Section | Required content |
| --- | --- |
| Event | Name; date; venue; event type; official/private status; host; principal; governing institutions |
| Dignitaries | Verified identity; category; office/rank; institution; event role; verification state |
| Address | Introduction form; direct address; pronunciation; restrictions |
| Arrival | Window; vehicle; entourage/security; receiving party; entrance; holding; escort; destination |
| Seating | Table/seat; contextual precedence; adjacency; access; rationale; version |
| Ceremony | Entry; procession; introduction; speaking; presentation; photography; departure |
| Special controls | Security; dietary/access; cultural/family; privacy; media; symbols; contingencies; escalation |

## 18.2 Protocol Master Sheet — single source of truth

The controlled master record must link each significant guest to: category, formal rank, institution, event role, verified address, arrival, receiving party, seating, escort, speaking, photography, security, departure, source/verification state, owner and last-approved version. Operational views may expose only the columns required by each role.

**VERSION RULE No operator should execute from an old WhatsApp message,

personal spreadsheet, printout or unapproved guest list. Changes occur

in the master record and propagate to role-specific views.**

## 18.3 Rehearsal and contingency test

Critical dignitary journeys must be walked through from vehicle arrival to departure. Rehearsal verifies who moves, receives, greets, introduces, photographs, escorts, seats and hands off the guest, including simultaneous-arrival capacity.

- Early or late arrival

- Unexpected or larger entourage

- Unplanned security team or vehicle

- Simultaneous important arrivals

- Occupied, refused or unavailable seat

- Early departure

- Programme or speaking-order change

- Unavailable host, receiver, escort or Protocol Lead

- Incorrect or disputed title

- Photography/media conflict

- Route, entrance or holding-area failure

## 18.4 Protocol readiness gate

| Gate | Pass condition |
| --- | --- |
| Identity | All material names, titles, offices, institutions, address forms and pronunciation verified to policy |
| Architecture | Host, principal, highest relevant precedence guest, event authority and ceremonial roles approved |
| Movements | Arrival, receiving, escort, procession, seating, speaking, photography and departure designed |
| Conflicts | Cross-system conflicts, adjacency restrictions and institutional guidance resolved or formally accepted |
| Resources | Owners, deputies, communications, spaces, security and accessibility dependencies confirmed |
| Rehearsal | Critical movements and simultaneous-arrival contingencies tested |
| Version | One approved master version released; superseded views withdrawn |
| Live authority | Deviation limits, escalation chain and dignity-preserving correction playbooks briefed |

## 18.5 Protocol alerts and recommendations

- Title, office or address is missing, stale, conflicting or sourced only from an unverified message.

- Formal rank is being inferred from wealth, fame or an informal title.

- Host, principal or highest relevant precedence guest is undefined.

- Traditional, diplomatic, religious or official guidance is required but not recorded.

- A dignitary appears in public material before verification approval.

- Two authoritative systems produce incompatible orders without a resolved ceremonial design.

- A proposed seat creates an adjacency, dignity, access, security, media or protocol risk.

- Receiving-line or holding capacity cannot absorb simultaneous arrivals.

- An arrival, escort, introduction, speech, procession, photograph or departure lacks an owner or contingency.

- A live change has not propagated to the MC, arrival, escort, seating, security and event-command views.

- A national symbol or official emblem is scheduled without verified requirements.

- A correction is likely to be public, humiliating or operationally visible to the guest.

# 19. Module 3 relationships, exclusions and gaps

## 19.1 Relationship to earlier modules

| Earlier foundation | Module 3 operationalisation |
| --- | --- |
| Dignity floor | Protocol preserves recognition without superiority or humiliation |
| Personalise without intrusion | Protocol information is used only for correct treatment and controlled access |
| Invisible choreography | Advance, receiving, escort, procession, seating and departure are prepared behind the scenes |
| Guest journey transitions | Protocol handoffs receive explicit release/receive ownership |
| Friction and embarrassment prevention | Titles, seats, introductions and arrivals are verified and rehearsed |
| Journey variants | Royal, government, diplomatic, religious, elder and principal journeys gain protocol context |
| Host protection | Protocol decisions, conflicts and live deviations are filtered through authorised command |

## 19.2 Global doctrine and Nigerian context

| Globally reusable | Nigeria / Lagos context |
| --- | --- |
| Verify identity and office; distinguish authority from prestige; contextual precedence; controlled introductions; seating rationale; dignity-preserving correction; institutional consultation; rehearsal and version control | Concurrent political, traditional, diplomatic, religious, institutional, family and social systems; palace- and territory-specific customs; Yoruba/Southwestern institutions; private-event family hierarchy; local arrival/security/entourage realities |

## 19.3 Exclusions applied

Module 3 sections labelled CEO Exercise and CEO Challenge were intentionally excluded from the specification. The surrounding operational principles, decision questions and contingency requirements were retained without reproducing the scenarios or assignments.

## 19.4 Source and verification limitation

Module 3 cites illustrative external sources, but the specification does not treat those references as a complete or current Nigerian order of precedence. Before production use, legal, official, palace, mission, religious and institutional rules must be represented as separately sourced, dated and approved knowledge records. Current officeholders and protocol requirements must be verified at the time of each event.

## 19.5 Explicit gaps identified

- (Resolved in design, Section 143) No approved Nigerian formal precedence dataset or authoritative-source hierarchy has yet been supplied. The Protocol Register (143) supplies this, Provisional and verification-required-per-event — every officeholder entry remains marked [Verify] rather than invented.

- (Resolved in design, Section 143) No institution-specific traditional, Yoruba, palace, diplomatic, religious, military or family protocol packs have yet been encoded. The Protocol Register supplies all of these (143.1).

- (Resolved in design, Section 143) Forms of address, honours order, post-nominals and pronunciation standards are not yet populated. The Protocol Register’s forms-of-address quick reference (143.1) closes this; pronunciation guidance remains event-specific per the existing verification chain (17.1).

- The boundary between advice, institutional authority and final Maison Doclar approval needs policy definition. Not closed by the Protocol Register; the existing Protocol Huddle (138.4) governs live disputes, but the general advice/authority/approval boundary this bullet describes remains open.

- (Resolved in design, Section 143) Representative, spouse/ partner, former-officeholder and acting-office treatment requires specialist rules. The Protocol Register’s edge-case rules (143.2) close this specifically.

- Seating algorithms, adjacency sensitivity categories and privacy controls require detailed schema and evaluations.

- Receiving-line capacity, acceptable interaction duration and simultaneous-arrival service levels are undefined.

- National-symbol requirements need authoritative jurisdiction-specific sources.

- (Partially closed, Module 24, Section 138) Protocol correction, dispute, refusal and live-deviation playbooks remain to be authored. The Protocol Huddle, co-honouring techniques, the discreet-identification channel and the diplomatic-no script now give live protocol conflict a real operating procedure (138.1– 138.4). Still open: representative/spouse/former-officeholder/ acting-office treatment, and measurable rehearsal/readiness thresholds (the two gaps immediately below, unchanged).

- Rehearsal evidence, readiness thresholds and deputy/continuity requirements need measurable standards.

# 20. Module 3 completion reconciliation

**COMPLETED MAISON DOCLAR PROTOCOL SEQUENCE Know who they are.

Understand why they matter. Know where they belong. Know how they

should be treated. Know what could go wrong. Then make the entire

process feel effortless.**

This resolves the incomplete Module 3 takeaway recorded in v0.3. The completion reinforces existing doctrine and does not alter the protocol model: verified, contextual preparation should disappear into an effortless guest experience.

# 21. Cultural intelligence operating framework

**CULTURAL DOCTRINE Protocol indicates what may be appropriate;

cultural intelligence establishes why it matters, when it applies, who

has authority and how to express it without stereotyping, theatre or

guest discomfort.**

**CULTURAL INTELLIGENCE FORMULA Knowledge + context + humility +

verification + respect**

## 21.1 Five-question cultural model

| Question | System interpretation | Required output |
| --- | --- | --- |
| Who? | People, groups, institutions, offices, faiths, families and communities involved | Cultural stakeholder map |
| Where? | Country, state, community, palace, family, faith environment and venue | Applicable locality and jurisdiction |
| What? | Ceremony, tradition, practice, object, expression or observance | Defined cultural element and event stage |
| Why? | Meaning, identity, history, relationship, authority or ceremonial function | Purpose and risk of misuse/omission |
| Who has authority? | Person or institution entitled to confirm what applies here | Named verifier, scope and approval evidence |

**SPECIFICITY RULE Never ask only what “Nigerian,” “Yoruba,” “Igbo,”

“Northern,” “Muslim” or “Christian” culture requires. Ask what applies

to this people, institution, place, family and occasion, and who can

confirm it.**

## 21.2 Culture is meaning, not decoration

Attire, fabric, beads, music, food, dance, instruments and imagery may express culture, but culture also includes hierarchy, kinship, age, authority, language, religion, community, identity, history and belonging. A cultural element may enter experience design only after its meaning, authority, purpose, restrictions and guest impact are understood.

| Element state | Meaning | System treatment |
| --- | --- | --- |
| Ceremonial / sacred | Carries authorised ritual, institutional or spiritual meaning | Stop-and-verify; restricted handling and approval |
| Identity-bearing | Signals family, group, title, community or affiliation | Use only with confirmed context and privacy-aware interpretation |
| Cultural expression | Supports welcome, honour, transition, celebration or storytelling | Record purpose, timing and responsible authority |
| Decorative reference | Aesthetic element without ceremonial claim | Confirm it does not misrepresent, trivialise or conflict with the occasion |
| Unknown | Meaning or status not established | Do not deploy, move, script or photograph until verified |

## 21.3 Cultural authority chain

| Authority domain | Illustrative authority | Decision scope |
| --- | --- | --- |
| Traditional | Palace, ruler, chief, traditional council or designated representative | Institution-specific custom, palace procedure, titles, rites, objects and ceremonial order |
| Family | Designated senior family representative or family head | Family hierarchy, relationships, roles, sensitive pairings and change consultation |
| Religious | Officiating clergy, imam or authorised religious institution | Prayer, worship, titles, food/fasting, modesty, symbols and ceremonial practice |
| Government / diplomatic | Relevant protocol office or mission | Official status, national/mission requirements and institutional participation |
| Security | Designated authorised security lead | Protection, access, routes and safety constraints |
| Maison Doclar | CEO, Event Lead, Protocol Lead and Cultural Intelligence Lead | Experience integration, operations, guest protection, controlled execution and escalation |

Authority is scoped. Maison Doclar does not overrule a palace on palace custom, and a cultural adviser does not independently control event safety or production. Conflicts must be surfaced and resolved through the recorded authority chain.

# 22. Cultural context packs

Cultural knowledge should be stored as modular context packs. Packs contain sourced considerations and questions, not universal instructions automatically applied to every person associated with a culture.

## 22.1 Yoruba / Southwestern context

| Domain | Operational consideration | Control |
| --- | --- | --- |
| Traditional institution | An Oba represents an institution/community, not merely personal VIP status | Model royal household, palace authority and institutional journey |
| Royal party | Chiefs, aides, family, security, attendants, media and protocol may accompany the ruler | Confirm composition, roles, arrival, holding, procession, seating and departure |
| Greeting | May communicate age, position, relationship and respect | Brief staff on when to use conventional greeting and when to defer |
| Prostration / kneeling | May express respect but varies by family, gender, setting and institution | Never mandate theatrically; confirm context and guide discreetly |
| Elders / age | Age may influence greeting, seating, speaking and family authority | Treat age as one factor; provide support without exposure or patronisation |
| Attire / aso-oke | May communicate identity, group, heritage, occasion or status | Use as a confirmed supporting signal, never sole identity evidence |
| Coral / regalia | May carry royal, chieftaincy, family or ceremonial meaning | Record meaning and restrictions; do not reduce to luxury jewellery |
| Music / praise | May welcome, announce, honour, transition, celebrate or preserve lineage/history | Treat practitioners as possible ceremonial actors, not generic entertainment |

## 22.2 Ceremonial-object control

Staffs of office, irukere, stools, beads, crowns, religious objects, instruments and national symbols require an object record before operational use.

| Required question | Why it matters |
| --- | --- |
| What is it and what does it mean here? | Prevents decorative misuse and false interpretation |
| Who owns or has custody? | Establishes authority and accountability |
| Who may handle or carry it? | Prevents dignity, sacredness or security breaches |
| When and where does it appear? | Integrates ceremony, procession and production cues |
| May it be moved, touched, displayed or photographed? | Protects restrictions and privacy |
| How is it secured, transferred and returned? | Creates chain of custody and contingency |

**OBJECT RULE A cultural object is not a prop. Unknown meaning or

authority creates a mandatory stop-and-verify state.**

## 22.3 Family and community intelligence

Family and community structures may carry authority invisible to public-office data. Before a major family event, conduct a controlled Family Protocol Interview.

- Who is the family head and who are the senior elders?

- Who receives important guests and who speaks for the family?

- Who must be consulted before ceremony changes?

- Who holds authority over traditional matters?

- Which people or groups should or should not be seated together?

- Who should be informed, and who should never be surprised?

- Which community, age-grade, hometown, council, association or club representatives have ceremonial roles?

- Who leads and speaks for each recognised group, and do they arrive or sit together?

Sensitive family relationships and exclusion reasons require restricted access and discreet operational codes. They must not appear in general guest-facing or supplier views.

## 22.4 Igbo and community-structure context

Igbo ceremonial knowledge must identify the specific community, family, occasion, title and local custom. Potentially relevant domains include lineage, elders, titles, age grades, community institutions, hospitality, achievement and communal participation. No rule should be applied merely because a guest or event is labelled “Igbo.”

## 22.5 Northern Nigerian context

Northern context packs must identify the specific location, community, emirate/traditional council, faith environment, office, district structure and occasion. Potential participants may include emirs, councils, scholars, elders, political authorities, military figures and community leaders; their relationships are institution- and locality-specific.

# 23. Religious and interfaith intelligence

## 23.1 Islamic hospitality

| Domain | Data / decision requirement |
| --- | --- |
| Prayer | Prayer times, space, ablution/access, direction and programme accommodation as confirmed |
| Food | Halal requirements, ingredient/service assurance and cross-contamination considerations |
| Fasting / Ramadan | Fasting status where appropriately provided; iftar time; immediate provision; Maghrib accommodation; meal sequence |
| Alcohol | Event, venue and guest-environment appropriateness confirmed by host/religious authority |
| Modesty / interaction | Dress, privacy and gender-interaction considerations only where applicable and verified |
| Calendar | Religious dates, holidays and observance timing incorporated into programme and service design |

## 23.2 Christian ceremonial environments

Christian context is denomination-, church-, clergy- and occasion-specific. Verify clergy titles, procession, prayer, scripture, music, communion, dress, timing, photography and religious-symbol requirements with the officiating church or authorised clergy. Do not transfer one denomination’s practice to another.

## 23.3 Interfaith rule

**INTERFAITH DOCTRINE Respect every faith without forcing every faith

into the same expression. Preserve the identity of the occasion,

recognise differences, protect dignity and avoid unnecessary offence.**

| Decision domain | Required evaluation |
| --- | --- |
| Prayer / speaking | Purpose, representation, order, duration and authority |
| Food / alcohol | Requirements and conflicts across invited groups and event identity |
| Symbols / music | Meaning, placement, prominence and possible exclusion or offence |
| Seating / interaction | Any verified faith, modesty or ceremonial considerations |
| Timing | Prayer, fasting, worship and religious-calendar constraints |
| Communication | Explain necessary arrangements without labelling or exposing private beliefs |

Religious affiliation is sensitive data. Store only what is necessary for an approved experience purpose, restrict access, and avoid inferring personal belief from name, clothing, community or attendance.

# 24. Cultural bridging and international guests

**BRIDGING OBJECTIVE Make Nigerian culture accessible without diluting

it, turning it into theatre or making the guest feel tested. The guest

should feel confident, not anxious or overwhelmed.**

## 24.1 Cultural Experience Concierge

- Brief international and culturally unfamiliar guests with essential, actionable guidance.

- Liaise with palace, family, religious and other cultural authorities.

- Translate verified cultural requirements into guest-facing confidence and team action.

- Monitor cultural touchpoints and intervene discreetly before misunderstanding becomes embarrassment.

- Escalate uncertainty rather than improvising beyond delegated authority.

## 24.2 International Guest Cultural Brief

| Section | Content rule |
| --- | --- |
| Greeting | What is expected, what is optional and when to follow a designated guide |
| Dress | Essential dress code and meaning only where useful |
| Titles / authority | How to recognise and address relevant ceremonial figures |
| Ceremony | What the occasion means, what will happen and what the guest may be asked to do |
| Religion | Relevant prayer, food, alcohol, modesty or observance information |
| Photography | What may not be photographed or shared and whom to ask |
| Dining / gifts | Only actionable etiquette and restrictions |
| Do / avoid | Short, prioritised behaviours that prevent embarrassment |
| Support | Named contact for discreet questions during the journey |

Use progressive disclosure: a one-page essentials brief, optional deeper context, and a named human guide. Do not burden the guest with a cultural lecture or imply that a respectful mistake will be punished.

# 25. Cultural friction and application engine

## 25.1 Cultural friction audit

| Domain | Audit question | Typical intelligence output |
| --- | --- | --- |
| Language | Could wording, pronunciation or interpretation exclude or confuse? | Language support, revised copy or pronunciation verification |
| Greeting | Could a guest or staff member greet inappropriately or hesitate visibly? | Brief, guide, authority cue or receiving adjustment |
| Dress | Could dress conflict with occasion or be misread as identity/status? | Clarification, optional support or group validation |
| Food / drink | Could ingredients, preparation, service or alcohol conflict with requirements? | Menu/service change and assurance task |
| Music | Could content, performer or timing undermine ceremony or faith? | Programme review and authority approval |
| Gender | Are any interaction or privacy considerations actually applicable and verified? | Restricted operational accommodation; no stereotype |
| Age / elders | Could distance, waiting, standing or public assistance diminish comfort/dignity? | Route, seating, escort and discreet support |
| Religion | Are prayer, fasting, symbols, timing and observance protected? | Religious-accommodation readiness tasks |
| Tradition / objects | Could practice or object be mishandled, staged or improvised? | Stop-and-verify, custodian and chain-of-custody control |
| Photography / media | Could capture or publication breach sacred, palace, family or privacy expectations? | Photo zones, consent/authority rules and staff cues |
| Symbols | Are cultural, religious, institutional or national symbols accurate and authorised? | Verification gate or removal recommendation |

## 25.2 Cultural requirement application logic

- Detect a potentially culturally significant event element, guest need, institution, ceremony or object.

- Identify specificity: people, place, practice, meaning and authority.

- Retrieve only relevant sourced context-pack knowledge.

- Distinguish general guidance, event-specific confirmation, individual preference and prohibited assumption.

- Request missing confirmation from the correct authority without exposing unnecessary guest data.

- Evaluate affected journey stages, friction, dignity, accessibility, protocol, security and supplier dependencies.

- Generate a recommendation, task, briefing, control or stop-and-verify alert with evidence and approval requirement.

- Propagate approved requirements to only the roles and artefacts that need them.

- Capture outcome and propose learning without converting one event’s custom into a universal rule.

## 25.3 Cultural alerts

- A broad cultural label is being used as if it were an event-specific requirement.

- A palace, sacred, chieftaincy, religious, greeting or object-handling detail lacks an authority.

- A cultural object has no custodian, handler, placement, photography or return control.

- Attire is being used as the sole basis for identity, role or access.

- A guest briefing contains excessive, unverified or anxiety-producing instructions.

- An elder’s accommodation is public, patronising or based on age alone rather than need.

- Food, prayer, fasting, alcohol, timing or interfaith requirements conflict or remain unresolved.

- Photography, music, symbols or décor risk trivialising a sacred or institutional element.

- A live cultural correction is likely to embarrass the guest publicly.

- An event-specific custom is being promoted into permanent knowledge without review.

# 26. Cultural intelligence products and readiness

## 26.1 Cultural Intelligence Brief

| Section | Required content |
| --- | --- |
| Event context | People; place; purpose; ceremony; institutions; cultural complexity and scope |
| Authorities | Traditional, family, religious, government, security and Maison Doclar owners with decision scope |
| People / groups | Elders, households, entourages, community groups, international guests and ceremonial roles |
| Practices | Language, greetings, titles, attire, food, religion, music, photography and relevant customs |
| Objects / symbols | Meaning, custody, handling, timing, location, photography and restrictions |
| Journey integration | Affected stages, touchpoints, transitions, guest briefs, staff cues and supplier tasks |
| Risks / controls | Friction, prohibited assumptions, stop-and-verify items, contingencies and escalation |
| Approval | Sources, verification state, authority sign-off, version and review date |

## 26.2 Cultural readiness gate

| Gate | Pass condition |
| --- | --- |
| Specificity | Relevant people, place, practice, meaning and authority identified |
| Authority | Named authorised verifier exists for every high-impact cultural requirement |
| Guest protection | Briefings and accommodations are discreet, proportionate and non-stereotyping |
| Religious / food | Prayer, fasting, diet, alcohol, timing and interfaith conflicts resolved as applicable |
| Objects / symbols | Custody, handling, placement, photography and return controls approved |
| Team / suppliers | Critical people understand only the instructions necessary for their role |
| Journey | Requirements are embedded in stage, touchpoint, transition and contingency plans |
| Version / live authority | One approved brief is released; correction and escalation owners are known |

# 27. Module 4 relationships, exclusions and gaps

## 27.1 Relationship to Modules 1–3

| Existing foundation | Module 4 contribution |
| --- | --- |
| Anticipation and dignity | Cultural misunderstandings and observance needs are prevented discreetly |
| Personalisation without intrusion | Culture informs service without labelling, surveillance or stereotype |
| Guest journey | Cultural requirements are attached to stages, touchpoints, transitions and briefings |
| Friction audit | Adds language, greeting, attire, food, music, faith, object, photography and symbol domains |
| Protocol contextuality | Explains meaning and identifies the institution/person authorised to confirm custom |
| Multiple-authority model | Adds scoped cultural, family, religious and object-custody accountability |
| International journey lens | Creates cultural bridging, progressive disclosure and Concierge support |

## 27.2 Exclusions applied

Module 4 CEO Exercise and CEO Challenge were excluded. The operational need they illustrate—brief unfamiliar guests concisely and prevent team hesitation through verified preparation—is already represented as system knowledge without retaining the assignments.

## 27.3 Source and verification limitation

Module 4’s external references and examples are illustrative, not a complete or current authority for Nigerian cultures, faiths, palaces or communities. Production knowledge requires separately sourced, dated, scoped and approved context packs. Cultural practices must be re-confirmed for the specific family, institution, place and occasion.

## 27.4 Explicit gaps identified

- No approved palace-, community-, faith-, denomination-, emirate-, family- or locality-specific cultural packs have yet been supplied.

- No authoritative catalogue of ceremonial objects, meanings, handlers and restrictions has been encoded.

- Cultural-authority credentials, mandate verification and conflict-resolution rules need formal policy.

- Language, translation, pronunciation and guest-briefing service levels remain undefined.

- Religious-data governance needs legal/privacy review and explicit access/retention controls.

- Halal, prayer-space, fasting, alcohol and interfaith operating standards require specialist validation.

- Cultural complexity scoring and criteria for mandatory Concierge assignment remain undefined.

- Cultural briefing templates need versions by audience, event type, locale and desired depth.

- Object custody, loss/damage, insurance, security and evidence procedures need operational policy.

- Attire/group-identification logic needs safeguards and evaluations against misidentification or discriminatory access.

- No measurable cultural-confidence, belonging or misunderstanding indicators have yet been approved.

- Supplier cultural-competence requirements, briefing evidence and failure consequences remain undefined.

- The boundary between respectful guidance and compelled cultural performance needs an explicit guest-autonomy standard.

# 28. VIP intelligence operating framework

**VIP DOCTRINE Know enough to remove decisions, uncertainty and

friction without making the guest feel observed. Never make the VIP

tell Maison Doclar twice within a valid purpose; never let them see the

machinery required to make the experience effortless.**

**VIP FORMULA VIP experience = intelligence + anticipation +

discretion + ownership + recovery**

## 28.1 VIP handling dimensions

| Dimension | Why handling may differ | Examples of resulting requirements |
| --- | --- | --- |
| Status | Current formal, institutional, diplomatic, royal or religious position | Protocol verification, receiving, ceremonial and address controls |
| Relationship | Importance to the host, principal, family or event purpose | Host interaction, placement, communication and protected moments |
| Experience | Host-approved exceptional-care intent or unusual journey complexity | Dedicated owner, tailored service, briefings and contingencies |
| Security | Verified protection, privacy, access or exposure needs | Restricted routes, access, holding, media and security coordination |
| Principal | Event is fundamentally structured around the person or their role | Programme, command, transition and host-protection integration |

**CLASSIFICATION SAFEGUARD VIP is an operating designation, not a

measure of human worth. A guest may have several handling dimensions,

and wealth or fame alone does not create automatic precedence or VIP

status.**

## 28.2 VIP intelligence domains

| Domain | Decision purpose | Boundary |
| --- | --- | --- |
| Identity | Recognise and address correctly | Current, verified and minimum necessary |
| Status | Apply relevant protocol/institutional handling | Do not infer precedence from prominence |
| Relationship | Deliver authorised interactions/separations | Do not map private relationships without operational need |
| Experience | Design comfort, confidence, privacy and personalisation | Use discreetly; do not display what is known |
| Logistics | Control arrival, movement, timing and departure | Share only stage-specific instructions |
| Protocol | Apply titles, reception, seating and ceremony | Use approved protocol architecture |
| Culture | Apply verified context and briefing | No broad-label assumptions |
| Security | Coordinate authorised protection requirements | Restricted need-to-know access |
| Sensitivity | Protect information, relationships and exposure | Prefer operational instruction over private explanation |

## 28.3 VIP Intelligence File contract

A VIP Intelligence File is a controlled operational record, not a biography. Every item must be relevant, verified where material, necessary, appropriate, useful, purpose-linked, classified and time-bounded.

| Field group | Minimum fields |
| --- | --- |
| Control | Profile ID; event; guest; handling dimensions; owner/deputy; status; version; review/expiry |
| Identity / protocol | Verified name, title, direct address, introduction, office/institution and pronunciation |
| Journey / logistics | Arrival, vehicle/contact where justified, entrance, stages, escort, holding, seating and departure |
| Service | Confirmed requirements and preferences with discreet delivery instruction |
| Relationships | Only approved meeting, proximity or separation instructions required for the event |
| Culture / access | Verified cultural, language, briefing, comfort and accessibility requirements |
| Security / privacy | Need-to-know operational controls, visibility, photography/media and access restrictions |
| Contingency / recovery | Likely deviations, fallback action, escalation, recovery authority and communications |
| Evidence / governance | Source, verification, purpose, sensitivity, permitted roles, validity, reuse status and audit |

Not every field should be completed. Empty fields are acceptable when data is unnecessary; curiosity is not a completeness requirement.

# 29. VIP privacy, access and memory

## 29.1 Data-minimisation test

- What specific guest-experience, safety, protocol or operational decision requires this information?

- Can the objective be achieved with a less sensitive instruction or narrower value?

- Is the source legitimate and the information sufficiently reliable?

- Who genuinely needs access, at what stage and for how long?

- Would discreet use make the guest feel cared for rather than watched?

- Should the item be event-only, reusable with review, or not stored at all?

**GOLDEN PRIVACY RULE If the team cannot explain why an item is needed

to serve the guest safely and appropriately, it does not belong in the

VIP system.**

## 29.2 Three information levels, plus General (reconciled, Module 23)

A later module proposed a four-level “Discretion Scale” (General, Operational, Sensitive, Restricted) for guest information generally, distinct in count from this three-level model. Checked against each other, they reconcile cleanly rather than conflicting: General sits below this model entirely — venue, programme and other genuinely public event information with no guest-specific content at all, which this model never covered because it only ever addressed information about a guest. Operational, Sensitive and Restricted map 1:1 onto Levels 1–3 below. General is adopted as an explicit zero-th tier; the three-level structure for guest-specific information remains exactly as it was.

| Level | Typical content | Access rule |
| --- | --- | --- |
| 0 — General (Module 23) | Venue, programme, publicly available event information, not guest-specific | No restriction — this is the tier below guest- specific information |
| 1 — Service | Preferred name, assigned seat, arrival window, confirmed diet/access and role-specific service instruction | Only relevant operational roles; contextual view |
| 2 — Confidential | Private itinerary, sensitive relationship instruction, special departure, non-public preference or coordination | Named senior/event roles; restricted export and notification |
| 3 — Restricted | High-sensitivity security, private contact or personal circumstance where genuinely necessary | Explicit named access; field-level logging; short validity; no general brief |

Classification applies per field or instruction, not merely per guest record. A role-limited brief should reveal the required action without revealing an unnecessary private explanation.

## 29.3 Communication-channel boundary

- The VIP system is the controlled source; messaging groups are not the database.

- General team channels receive only approved, minimum operational instructions.

- Confidential and restricted content must not appear in broad WhatsApp groups, casual chats, screenshots or uncontrolled exports.

- Messages require recipient scope, purpose, sensitivity, expiry and deletion/withdrawal treatment where supported.

- A change is recorded in the source system first and then propagated through approved role-specific notifications.

- Write as if it will be seen (Module 29): any digital communication may eventually be read by someone other than its intended recipient. Record facts and operational requirements, not speculation, insults or personal characterisations — “guest has requested a seating adjustment, please handle discreetly,” never a judgement about the guest. Before sending, the working test is whether the writer would be comfortable explaining the message to the guest it concerns, were the guest to see it.

## 29.4 Reusable VIP memory

| Memory state | Meaning | Treatment |
| --- | --- | --- |
| Event-only | Needed only for the current occasion | Expire/close under event retention policy |
| Candidate | May improve a future experience but not yet approved | Hold for review; do not silently reuse |
| Approved reusable | Validated service preference with continuing legitimate purpose and review date | Use discreetly within defined scope; reconfirm when material |
| Stale / disputed | Validity, source or guest preference is uncertain | Do not apply; request appropriate confirmation |
| Restricted archive | Retention required for authorised security/legal/incident purpose | Separate access and retention; never use for casual personalisation |
| Deleted / anonymised | Purpose ended or retention expired | Remove personal link while preserving approved aggregate learning if appropriate |

**MEMORY BOUNDARY Maison Doclar remembers service, not gossip. Reusable

memory contains what is legitimately needed to serve the person

well—not everything the organisation knows.**

# 30. VIP ownership and lifecycle

## 30.1 One-guest, one-accountable-owner model

Each major VIP has one accountable VIP Owner, supported by many roles and a designated deputy. Accountability is singular; knowledge and execution remain controlled and resilient.

| Owner phase | Accountability |
| --- | --- |
| Before | Validate profile, journey, dependencies, briefs, access, contingencies and guest/representative confirmations |
| During | Maintain situational awareness, anticipate the next need, coordinate handoffs, own exceptions and protect privacy |
| After | Confirm departure/closure, record outcomes, resolve open matters and submit memory/learning candidates for review |

**CONTINUITY SAFEGUARD The one-owner principle must not create a single

point of failure. Every critical VIP has a deputy, takeover trigger,

minimum handover state and command visibility.**

## 30.2 Pre-event intelligence cadence

| Window | Primary control objective |
| --- | --- |
| T-72 to T-14 days | Confirm attendance/role, handling dimensions, protocol/culture/security dependencies and missing authority |
| T-14 to T-3 days | Confirm transport, arrival, seating, diet/access, escort, schedule, privacy/media and contingency design |
| T-24 hours | Reverify changeable facts, release role-limited briefs, confirm owner/deputy and test dependencies |
| Event day | Track expected versus actual journey state, next action, deviation and readiness without unnecessary surveillance |
| After departure | Close journey, recover unresolved issues, review access, classify memory candidates and capture learning |

## 30.3 VIP Pre-arrival Brief

| Question | Required answer |
| --- | --- |
| Who is coming? | Verified identity, role and expected party/entourage |
| Why does handling differ? | Applicable VIP dimensions and event purpose |
| What do they need? | Confirmed critical requirements and discreet service instructions |
| Who receives them? | Named receiving role and fallback |
| Where do they go? | Entrance, route, holding/destination and next transition |
| Who owns the journey? | VIP Owner, deputy and command escalation |
| What should be avoided? | Approved do-not, privacy, media, adjacency and exposure controls |
| When do they leave? | Departure window, vehicle/security readiness and contingency |

## 30.4 Curbside and arrival control

The VIP arrival begins when the vehicle stops. The control must specify recognition, approach, greeting, crowd/photography exposure, belongings assistance, route, receiving readiness, escort, destination and handoff. A successful lobby cannot recover the first impression created by an uncertain curbside.

- Expected and actual arrival state are distinguished.

- Vehicle/driver/security data are restricted to roles that need them.

- Receiving and destination readiness are confirmed before the guest exits where practicable.

- The guest is not required to navigate, repeat identity, find a seat, locate a room or discover speaking/departure arrangements.

- Simultaneous arrival and early/late arrival contingencies are active.

# 31. VIP preferences, relationships and seating

## 31.1 Preference pyramid

| Level | Examples | Control intensity |
| --- | --- | --- |
| 1 — Comfort | Beverage, temperature, seating, lighting | Service-level access; verify material needs |
| 2 — Convenience | Parking, transport, timing, access | Journey/logistics roles only |
| 3 — Experience | Food, music, networking, privacy/visibility | Owner and relevant delivery roles |
| 4 — Personal | Relationships, family dynamics and sensitivities | Confidential; store action rather than narrative where possible |
| 5 — Restricted | Highly sensitive security or personal circumstances | Exceptional necessity; named access and short validity |

## 31.2 Personalisation contract

- Use intelligence to improve the experience, never to demonstrate what Maison Doclar knows.

- State the service offer naturally; do not reveal sensitive reasoning or observation.

- Distinguish preference, requirement, assumption and historical observation.

- A preference can change; stale or surprising personalisation must be reconfirmed.

- The more personal or restricted the item, the fewer people may see it and the stronger the approval/expiry controls.

## 31.3 Relationship intelligence

Record only event-relevant interaction outcomes: meet before dinner, sit near, introduce privately, keep apart or protect a conversation. Where possible, store the operational instruction and sensitivity code rather than a private history. Relationship maps must never become an unauthorised social dossier.

## 31.4 Seating intelligence expansion

| Dimension | VIP seating question |
| --- | --- |
| Protocol | What contextual precedence and ceremonial role applies? |
| Relationship | Whom should the guest meet, sit near or avoid for an authorised purpose? |
| Conversation | What interaction value is intended and consented/appropriate? |
| Comfort | What seat, distance, temperature, noise or access serves the guest? |
| Visibility | Does the guest want prominence, quiet excellence or controlled media exposure? |
| Security | What route, egress, protection or restricted-adjacency requirement applies? |
| Experience | What placement enables the guest to enjoy the event rather than merely occupy the “best” seat? |

# 32. VIP journey variants

| Variant lens | Additional intelligence | Core safeguard |
| --- | --- | --- |
| Quiet / low-visibility VIP | No-announcement, arrival visibility, escort/fuss tolerance, photography, private host interaction | Do not make VIP treatment publicly visible unless required |
| Celebrity | Media/fan/social access, image capture, entrance, holding and security | Never assume visibility is desired |
| Political | Current title/office, representative status, protocol, entourage, media and security | Do not let official presence unintentionally take over a private event |
| Royal | Palace contact, royal party, customary requirements, reception, movement and departure | Never invent palace protocol |
| International executive | Airport/transport, security, language, schedule, local context and cultural briefing | Make confident, not publicly educated or overwhelmed |
| Elder VIP | Walking, access, seating, temperature, noise, communication and departure | Support verified needs naturally, not patronisingly |
| Security-sensitive | Access, route, holding, vehicle, exposure and emergency coordination | Security information remains compartmentalised |

Variants are composable planning lenses, not permanent labels. A guest may require multiple lenses or none, and individual confirmation outranks category assumptions.

# 33. VIP contingency and recovery

## 33.1 Minimum contingency set

- Early or late arrival; vehicle delay or breakdown; route/entrance failure.

- Expanded security detail, entourage or additional guests.

- Immediate/early departure or schedule compression.

- Seat occupied, refused or changed; desired meeting unavailable.

- Privacy request, photography/media conflict or unexpected public attention.

- Owner/escort/receiver unavailable; holding or destination not ready.

- Programme, speech, protocol, cultural or dining requirement changes.

## 33.2 Recovery sequence

| Step | Control |
| --- | --- |
| 1. Recognise | Detect guest friction before complaint where possible |
| 2. Own | VIP Owner or authorised deputy accepts responsibility; no departmental deflection |
| 3. Resolve | Execute the safest, most dignified authorised solution |
| 4. Restore | Return guest to comfort, confidence, privacy and journey continuity |
| 5. Learn | Record outcome and submit reviewed process/memory change—without storing unnecessary personal narrative |

## 33.3 One-step-ahead engine

The live engine asks what the guest is likely to need in the next ten minutes, using the current journey state and verified plan: arrival → reception; receiving → direction; waiting → comfort; seating → orientation; dining → service; networking → authorised introduction; leaving → transport. It anticipates the next material need, not speculative needs far ahead.

# 34. VIP Control Desk and situational awareness

## 34.1 Control Desk scope

- Monitor arrivals, departures, journey state, ownership, vehicles, escorts, seating, protocol, changes and incidents.

- Coordinate Event Command, Protocol, Transport, Security, Guest Experience, Venue and Catering through role-scoped views.

- Maintain one current source and a timestamped decision/change log.

- Escalate exceptions while protecting confidential/restricted detail.

- Close journeys and revoke unnecessary live access after departure/event closure.

## 34.2 VIP Dashboard contract

| Visible operational field | Rule |
| --- | --- |
| Guest display | Approved operational name/identifier appropriate to viewer |
| Status | Expected, en route, arrived, holding, seated, departing, departed or exception |
| Location | Coarse event zone/journey stage only unless finer precision is necessary and authorised |
| Owner | Current accountable person and deputy/availability |
| Next action | Action, owner, deadline/ETA and receiving readiness |
| Alert | Minimal description; restricted detail opens only for authorised roles |
| Freshness | Last confirmed time and stale-state warning |
| Privacy | View watermark/audit where appropriate; no bulk export by default |

**SITUATIONAL-AWARENESS BOUNDARY The ability to answer where priority

guests are must not become continuous personal surveillance. Track only

the operational state necessary to coordinate the event, for the

minimum time and authorised audience.**

## 34.3 Command questions

- Where is each currently active priority guest in the planned journey?

- Who owns each experience and who is the deputy?

- What happens next, by when, and is the receiving stage ready?

- Which profile, dependency, access or contingency is incomplete?

- Which deviation needs executive, protocol, security or host decision?

- Which guest has experienced friction and has comfort been restored?

# 35. VIP intelligence products and readiness

## 35.1 VIP Event Brief

The role-limited VIP Event Brief is shorter than the full intelligence file. It includes only the approved operational fields required by its audience: guest, role, address, arrival, receiver, owner/deputy, journey/destination, seating, service requirements, security instruction, departure, do-not instruction and escalation. Sensitive explanations remain hidden.

## 35.2 VIP readiness gate

| Gate | Pass condition |
| --- | --- |
| Designation | VIP handling dimensions and event purpose approved; no wealth/fame-only classification |
| Data | Minimum necessary file complete; critical facts sourced, verified, classified and current |
| Privacy | Field-level access, brief views, messaging rules, retention and audit configured |
| Ownership | Owner and deputy assigned, capacity checked and handover triggers known |
| Journey | Arrival through departure mapped; receiving stages and one-step-ahead actions defined |
| Dependencies | Protocol, culture, transport, seating, catering, access, privacy/media and security confirmed |
| Contingency | Likely deviations, recovery authority and escalation rehearsed |
| Live command | Dashboard freshness, status vocabulary, communications and Control Desk responsibilities tested |

## 35.3 VIP alerts

- VIP designation lacks an authorised reason or is based only on fame/wealth inference.

- A critical profile item is missing, stale, conflicting, unverified or over-collected.

- Confidential/restricted data appears in a broad message, export, brief or dashboard.

- VIP has no available Owner/deputy or Owner capacity is exceeded.

- Arrival is approaching while receiver, route, holding, seat, vehicle or security is unready.

- Actual journey state is stale, deviates from plan or has no next action.

- A visibility/privacy preference conflicts with media, photography, protocol or host plans.

- A relationship/separation instruction lacks authority, purpose or appropriate access restriction.

- Unexpected entourage, early departure, seat refusal or security expansion requires re-plan.

- A service failure is resolved operationally but guest comfort/confidence has not been restored.

- An event-only item is being promoted into reusable memory without review.

- Live access persists after its operational purpose has ended.

## 35.4 Measurement model

| Measure | Examples | Anti-metric |
| --- | --- | --- |
| Guest effort | Repeated questions, navigation, waiting, unnecessary decisions and information repetition | Amount of visible attention |
| Continuity | Successful handoffs, next-action readiness, owner/deputy availability and plan deviation | Number of staff assigned |
| Discretion | Privacy incidents, over-sharing, unnecessary access, visible fuss and intrusive personalisation | Volume of collected intelligence |
| Readiness | Critical-profile completeness, dependency verification and contingency coverage | Percentage of optional fields filled |
| Recovery | Detection, ownership, resolution, comfort restoration and learning closure | Problem hidden without restoration |
| Host confidence | Host interventions avoided and priority-guest status understood | Spend or décor value |

# 36. Module 5 relationships, exclusions and gaps

## 36.1 Relationship to Modules 1–4

| Existing foundation | Module 5 contribution |
| --- | --- |
| Anticipation / never ask | One-step-ahead VIP engine and verified continuity |
| Personalisation without intrusion | Preference pyramid, purpose/validity and discreet delivery contract |
| Guest journey | Named VIP owner, live state, arrival-to-departure plan and contingencies |
| Dignity floor / protocol | VIP handling dimensions remain separate from human worth and formal precedence |
| Cultural intelligence | Individual confirmation and context override archetype assumptions |
| Invisible choreography | Control Desk coordinates many teams while guest sees one effortless experience |
| Learning governance | Memory candidates require review rather than automatic profiling |

## 36.2 Exclusions applied

Module 5 CEO Exercise and CEO Challenge were excluded. Their operational lessons—design the complete T-24-to-departure journey and re-plan a sudden early departure without degrading the experience—are represented in lifecycle, contingency, recovery and command controls.

## 36.3 Privacy and legal limitation

The source refers to Nigerian data-protection requirements. This specification adopts privacy-by-design controls but does not provide legal conclusions. Before production, qualified review must establish lawful bases, notices/consent where applicable, data-subject rights, processor/vendor obligations, international transfers, retention, breach response and security requirements for each operating jurisdiction.

## 36.4 Explicit gaps identified

- No approved VIP designation policy, service tiers or handling-capacity model has yet been supplied.

- Sensitivity classification requires a detailed field catalogue, harm model and role/access matrix.

- Retention, consent/legal-basis, rights-request, breach and vendor-processing policies require legal/privacy validation.

- The VIP Owner competency standard, maximum portfolio, deputy and takeover rules remain undefined.

- No controlled messaging policy or approved channel list exists for VIP operational information.

- Profile source hierarchy, verification service levels and stale-data thresholds remain undefined.

- Preference taxonomy needs rules for requirement versus preference, confidence, reconfirmation and surprising personalisation.

- VIP memory needs guest identity matching, duplicate resolution, portability, correction and deletion workflows.

- Live journey-state vocabulary, update frequency, location granularity and dashboard access require formal approval.

- Security data architecture and incident response require authorised security specialists.

- Relationship and seating intelligence need privacy-safe coded instructions and dispute/verification workflows.

- Recovery authority, compensation/spend limits, host notification and serious-incident thresholds remain undefined.

- VIP readiness, guest-effort, discretion and host-confidence targets have not yet been calibrated.

- A guest-facing process for correcting preferences or declining VIP treatment is not yet defined.

- The system needs tests for over-collection, stereotype-based designation, access leakage, stale memory and intrusive recommendations.

# 37. Event command operating framework

**CENTRAL COMMAND DOCTRINE One event. One command structure. One source

of truth. One guest experience. Many specialists may execute; one

operational intelligence coordinates their intersections.**

**EVENT COMMAND FORMULA Visibility + ownership + communication +

anticipation + decision**

Event planning defines intended action. Event command maintains live awareness of what is happening, what should happen, what happens next, what differs and what decision or intervention is required.

## 37.1 Visible and invisible worlds

| Guest-visible experience | Command-controlled machinery |
| --- | --- |
| Welcome, beauty, staff, food, music, ceremony, speeches, lighting and seamless movement | Timelines, radios, vendor dependencies, technical tests, security briefings, transport state, contingencies, staff positioning, issues and decisions |

The guest experiences the visible result. Maison Doclar controls both worlds while preventing internal complexity, blame or negotiation from leaking into the guest experience.

## 37.2 Configurable command structure

| Layer | Accountability | Boundary |
| --- | --- | --- |
| CEO / Executive Command | Brand, client, strategic/commercial decisions, reputation and critical escalations | Does not routinely bypass Event Director or become operational bottleneck |
| Event Director | Live operational command, coordination, timeline, vendors, staff and event-day decisions | Escalates reserved decisions and respects specialist safety authority |
| Functional Commands | Protocol, Guest Experience, Operations, Security, Transport, Venue, Production, Catering and other event-specific functions | Each has named lead/deputy, scope, dependencies and escalation |
| Vendor / Team Leads | Contracted/function deliverables and their staff | Do not independently control cross-functional guest experience |
| Frontline / Specialists | Execute assigned actions and report exceptions | Resolve only within training and delegated authority |

**AUTHORITY SAFEGUARD Event command coordinates the ecosystem but does

not replace qualified medical, emergency, security, structural,

electrical, venue or public-authority command where specialist or legal

authority applies.**

## 37.3 CEO and Event Director decision split

| CEO questions | Event Director questions |
| --- | --- |
| Is the host confident? Are principals protected? Is safety/reputation threatened? Is the Maison Doclar standard being delivered? Is executive intervention required? | What is happening? What should be happening? What is about to happen? What could fail? What needs an operational decision? |

The CEO leads the standard and reserved executive decisions. The Event Director leads the operation. Routine upward bypass is a command defect unless emergency or protected escalation policy requires it.

# 38. Command Centre and source of truth

## 38.1 Command Centre capability

- Secure, quiet, connected and operational workspace with controlled access.

- Current master timeline, floor plans, guest/VIP role views, vendor and transport schedules, seating, programme and contingency state.

- Radio/communications, emergency contacts, command board, issue/decision log and document-version register.

- Named controller, Event Director/deputy access and specialist liaison capability.

- Backup power/connectivity, alternative command location and continuity procedure proportionate to event risk.

- (Module 16) The Command Centre is for decision and control, not discussion — it is not a meeting room, and routine issues are not talked through there merely because people are present.

## 38.2 Programme, Run of Show and Master Timeline

| Artefact | Audience / purpose | Control requirement |
| --- | --- | --- |
| Programme | Guest-facing sequence and experience | Approved public truth; omit internal machinery |
| Run of Show | Production/event execution cues | Detailed cue, duration, owner, asset and dependency control |
| Master Event Timeline | Whole-organisation coordination from setup through closure | Planned/actual time, owner, dependency, readiness, status, contingency and version |
| Specialist plan | Security, transport, catering, protocol, medical/emergency or venue detail | Controlled by authorised owner and linked to master milestones |

## 38.3 Operational document control

Every material operational artefact carries document name, event, version, release date/time, owner, approver, effective time, change summary and superseded version. Role-specific views derive from the current released source rather than independent copies.

- Draft, approved, released, superseded and withdrawn states are distinct.

- Material changes identify affected people, dependencies, views and acknowledgement requirements.

- Superseded paper, message, spreadsheet and local copies are withdrawn or visibly invalidated.

- Offline continuity is supported by controlled snapshots with synchronisation and expiry rules.

- No operator should execute from an old WhatsApp message or unapproved personal schedule.

## 38.4 Event Command Board

| Panel | Question answered |
| --- | --- |
| NOW | What is happening and which actual state differs from plan? |
| NEXT | What must occur within the next 15 minutes and is the receiving state ready? |
| LATER | Which approaching milestones require preparation now? |
| RISK | What may fail, with what impact, owner, action, trigger and deadline? |
| VIP / PRINCIPAL | Which active priority journeys require attention without overexposing private data? |
| DECISION | What approval is required, by whom and by what deadline? |
| STALE | Which critical status has exceeded its freshness threshold? |

# 39. Vendor and dependency command

## 39.1 Vendor command contract

| Field | Required answer |
| --- | --- |
| Lead / deputy | Who is accountable and who assumes responsibility if unavailable? |
| Scope | What exactly is and is not controlled by the vendor? |
| Deliverables | What observable outputs/evidence must be produced? |
| Deadline / milestones | When must each state be achieved? |
| Dependencies | Which upstream/downstream people, inputs, access or systems affect delivery? |
| Inputs from Maison Doclar | What decisions, assets, access or information must be supplied? |
| Readiness proof | What demonstrates readiness beyond a verbal “yes”? |
| Escalation / recovery | Who is contacted, when, and what guest-protecting fallback exists? |

**INTERSECTION RULE Vendors control their specialist scope. Maison

Doclar controls how scopes intersect and how vendor performance

becomes—or does not become—the guest experience.**

## 39.2 Readiness questioning

Do not ask only “Is it ready?” Ask what is ready, what is incomplete, what is at risk, what evidence exists, what input is missing, what happens if it is not supplied, who owns recovery and by what deadline.

## 39.3 Dependency intelligence

Every critical timeline item and deliverable links to upstream inputs, downstream consumers, acceptance evidence, fallback and receiving owner. A dependency change automatically re-evaluates affected readiness, timeline, handoffs and contingencies.

# 40. Status, priority and escalation

## 40.1 Evidence-based RAG

| State | Meaning | Minimum record |
| --- | --- | --- |
| Green | On track against defined readiness/time/quality criteria | Current evidence, owner and next verification time |
| Amber | Potential or developing issue; recovery still feasible without immediate critical impact | Impact, action, owner, deadline, trigger for Red and contingency readiness |
| Red | Immediate intervention or decision required; critical outcome threatened or failed | Containment, decision authority, recovery action, communications and update cadence |
| Unknown | No reliable current evidence | Treat according to risk; request verification and flag stale/unknown explicitly |

A five-step version of the same progression (Normal -> Watch -> Prepare -> Intervene -> Escalate) has been proposed more than once as a finer- grained alternative. It is not a second model: Normal is Green; Watch and Prepare are Amber at different maturity within the same state (a developing issue still being monitored versus one now being actively prepared for); Intervene and Escalate are Red, distinguishing action taken within existing authority from action requiring the next 76.2 ladder level. Teams wanting this finer granularity may use it as a subdivision of Amber/Red; Green/Amber/Red/Unknown remains the canonical four-state model.

RAG cannot be a subjective colour chosen without criteria. Every status expires when evidence becomes stale and must never default to Green merely because no problem has been reported.

## 40.2 Priority model

| Priority | Treatment |
| --- | --- |
| 1 — Life / safety / emergency | Immediate qualified response, containment and escalation; overrides ordinary hierarchy |
| 2 — Principal / critical VIP | Immediate continuity and dignity protection after safety obligations |
| 3 — Ceremony / programme | Protect essential meaning, timing and dependencies |
| 4 — Guest experience | Prevent or recover material friction, confusion, discomfort or reputation impact |
| 5 — Operations | Restore supporting process and capability |
| 6 — Aesthetics | Resolve after higher-impact needs unless aesthetic failure itself creates safety, dignity or material experience harm |

## 40.3 Five-minute ownership rule

For a non-emergency important issue: if it can be safely resolved within five minutes and within authority, resolve and confirm. Otherwise assign one owner, action, deadline and escalation. “We are looking into it” without ownership is not a status. The heuristic never delays medical, safety, security or other immediate specialist escalation.

## 40.4 Escalation ladder

| Level | Default authority | Escalation condition |
| --- | --- | --- |
| 1 | Trained team member | Cannot resolve safely/within authority, deadline or service threshold |
| 2 | Function/Department Lead | Cross-functional, repeated, material or resource decision required |
| 3 | Event Director | Event-wide, principal, programme, material recovery or reserved operational decision |
| 4 | Executive Command / CEO | Strategic, host/client, reputation, major commercial or reserved authority |
| Specialist override | Qualified medical, emergency, security, venue or public authority | Immediate safety/legal/specialist threshold regardless of ordinary level |

**ESCALATION MESSAGE CONTRACT State the situation, verified impact,

action already taken, owner, deadline/trigger, proposed decision and

exact approval required. Escalation without a proposed action is

incomplete unless immediate danger prevents formulation.**

# 41. Communication and closed-loop control

## 41.1 Command message format

| Element | Required content |
| --- | --- |
| Address | Named role/call sign and intended recipients |
| Situation | Short verified fact with location/time |
| Impact | What guest, milestone, safety or dependency is affected |
| Action | What is being done and by whom |
| Timing | ETA, deadline or next update |
| Trigger / request | When escalation occurs or exact approval needed |
| Acknowledgement | Receiver repeats/accepts critical instruction and ownership |
| Closure | Outcome confirmed and command state updated |

## 41.2 Channel architecture

- Separate Event Command, Security, Production, Guest Experience, Transport and other channels according to event need.

- Not everyone hears everything; access follows role, sensitivity and operational necessity.

- A quiet leadership channel supports CEO, Event Director, Protocol and Security or other designated leads without flooding frontline channels.

- Every primary channel has fallback technology/procedure, call signs, radio checks and loss-of-comms protocol.

- Sensitive VIP, security, medical or personal detail is compartmentalised and never broadcast casually.

## 41.3 Handoff and closed loop

Every critical transition defines sender, receiver, subject, planned time, readiness, message, acknowledgement, acceptance and completion evidence. Sent is not received; received is not accepted; accepted is not completed.

| Handoff state | Meaning |
| --- | --- |
| Planned | Sender/receiver, time and acceptance criteria exist |
| Released | Sender confirms person/item/action is leaving their control |
| Acknowledged | Receiver confirms message understood |
| Accepted | Receiver confirms readiness and assumes control |
| Completed | Destination state/outcome verified |
| Exception | Delay, refusal, missing readiness or mismatch has an owner and escalation |

# 42. Pre-open stabilisation and go-live

## 42.0 Extended readiness rhythm (Modules 16, 21)

For larger events, two earlier checkpoints precede the T-60 sweep below rather than replace it: T-180 (full readiness review across every domain in 42.1) and T-120 (vendor and venue check specifically). Both use the same evidence discipline as T-60/T-15 — named owner, current state, not a verbal assurance — just at a wider horizon. Smaller events may compress T-180/T-120 into the T-60 sweep; the rhythm scales to event size rather than being mandatory at every scale.

A further checkpoint precedes all of these by a full day rather than hours: T-24 hours, the final operational review across seven domains — People, Place, Product, Programme, Protocol, Protection, Participants — plus an explicit Problems domain naming what is currently unresolved. The discipline this checkpoint enforces: discover problems at T-24, resolve them by T-12, execute the plan at T-3 — event day itself is for executing a plan, not discovering that basic planning was incomplete. T-24 is a new, earlier addition to this rhythm (measured in hours before the day, not minutes before doors open); T-180 through T-0 remain as already defined.

## 42.1 Event-day leadership briefing

- Today’s objective and promised experience

- Host/principals and critical journeys

- Programme and master milestones

- Top risks and active contingencies

- VIP/protocol/cultural requirements at role-appropriate detail

- Security/emergency instructions from authorised leads

- Communication channels and reporting lines

- Escalation/delegated authority

- Non-negotiables and stop-work conditions

## 42.2 T-60 readiness sweep

| Domain | Evidence question |
| --- | --- |
| Venue / flow | Spaces, routes, access, signage, toilets and bottlenecks ready? |
| Technical | Lighting, sound, power, backup and production tests passed? |
| Catering | Kitchen/access, food/service sequence, staffing and timing ready? |
| People | Staff positioned, briefed, identifiable and supervised? |
| Security / emergency | Qualified lead confirms access, routes, communications and response readiness? |
| Transport / VIP | Vehicles, arrivals, receiving, holding, escorts and departure controls current? |
| Comfort | Temperature, seating, accessibility and guest-support points ready? |
| Command | Centre, timeline, board, radios, documents, owners, deputies and contingencies live? |

## 42.3 T-15 stabilisation

**FREEZE RULE Fifteen minutes before opening, stop unnecessary changes.

Permit only changes required because something is unsafe, incorrect,

missing or materially damaging to the experience, through the defined

change authority.**

A permitted late change must identify impact, dependencies, rollback/fallback, approver, affected views and acknowledgement. Stability is a designed operational state, not resistance to necessary correction.

## 42.4 Go-live transition

When the first guest arrives, the team shifts from planning/design mode to control mode. Go-live requires critical readiness gates, accepted residual risks, active command roles, current source documents, functioning communications and confirmed emergency/specialist authority.

# 43. Live command and guest-experience loops

## 43.1 Event Director loop

- Observe actual state.

- Compare with current approved plan.

- Identify meaningful variance.

- Prioritise by impact and urgency.

- Act within authority or escalate with proposal.

- Confirm that intervention produced the intended outcome.

- Update command state and repeat.

## 43.2 Guest Experience control loop

Guest Experience monitors queues, confusion, empty service states, discomfort, lost guests, congestion, noise, toilets, signage, delayed service and VIP dissatisfaction. Observed behaviour is a signal to investigate, not proof of emotion or cause.

## 43.3 Crowd-as-data safeguards

| Observation | Possible hypothesis | Required validation |
| --- | --- | --- |
| Guests standing near entrance | Seating, orientation, arrival-flow or social-choice issue | Check staff/guest questions, seating readiness and zone flow |
| Repeated watch-checking | Timing, transport or personal schedule issue | Compare programme variance and direct feedback; do not infer impatience as fact |
| Early departures | Service, timing, transport, fatigue or planned schedule | Check departure plans, service data and appropriate feedback |
| Crowd at one entrance | Capacity, signage, security or attraction issue | Measure flow and inspect alternative routes |
| Repeated same question | Communication, signage or staff-knowledge failure | Count topic, identify source and issue consistent guidance |
| VIP appears uncomfortable | Many possible causes | VIP Owner makes discreet, non-leading check; no permanent inference |

Crowd monitoring must be proportionate, privacy-respecting and designed around operational observations. Facial/emotion recognition, covert tracking or identity inference is not authorised by this module.

## 43.4 Flow and bottleneck control

Map arrival, security, registration, reception, seating, ceremony, dining, networking and departure flows. For every likely bottleneck—entrance, parking, lift, corridor, toilet, buffet, bar, photo area or vehicle collection—record capacity, expected demand, threshold, intervention, alternative route and owner before opening.

# 44. Contingency, recovery and vendor failure

## 44.1 Three-layer contingency contract

| Plan | Meaning | Required fields |
| --- | --- | --- |
| A | Approved ideal operating scenario | Dependencies, owner and verification |
| B | Likely disruption response | Trigger, activation authority, resources, guest impact and communications |
| C | Major failure/continuity response | Safety/specialist authority, relocation/substitution, command continuity and recovery objective |

## 44.2 Trigger specification

A decision trigger contains metric/observation, authoritative source, threshold, observation window, confidence, decision deadline, activation owner, required consultation, action consequence, affected artefacts, guest communication and reset/closure rule. “Let’s see” is not a trigger.

## 44.3 Event recovery sequence

| Step | Command objective |
| --- | --- |
| Identify | Establish verified failure and affected outcomes |
| Contain | Protect life, safety, dignity, critical assets and spread of impact |
| Resolve | Apply authorised repair, substitution or re-plan |
| Communicate | Send minimum calm instructions to the right roles/guests; prevent rumour |
| Recover | Restore continuity, comfort and confidence; confirm outcome |
| Review | Preserve evidence, vendor accountability and learning after the live event |

## 44.4 Vendor-failure separation

**RECOVERY RULE Never let a vendor failure automatically become a

guest-experience failure. Maison Doclar owns immediate continuity and

recovery; vendor responsibility remains documented for contractual,

commercial and learning action.**

Alternative execution may change programme, timing, supplier, service sequence or guest activity, but it must respect safety, host/principal intent, protocol/culture, authority limits and communications control.

# 45. Event Command intelligence products and readiness

## 45.1 Command readiness gate

| Gate | Pass condition |
| --- | --- |
| Authority | Event Director/deputy, executive and specialist authorities named with scopes |
| Source of truth | Released master timeline and linked current views; superseded versions controlled |
| Ownership | Every critical function, vendor, issue, handoff and contingency has an accountable owner/deputy |
| Evidence | RAG statuses use objective current evidence; Unknown/stale states visible |
| Dependencies | Critical inputs, receiving readiness and fallback paths verified |
| Communication | Channels, call signs, radio checks, quiet channel, acknowledgement and backup tested |
| Safety / emergency | Qualified owners confirm plans, routes, contacts and stop/override authority |
| Guest/principals | Journey, VIP, protocol, culture, accessibility and host-protection controls ready |
| Contingency | Plan B/C triggers, activation authority, resources and communications tested |
| Stabilisation / go-live | T-60 sweep complete, late-change policy active and residual risks accepted |

## 45.2 Command alerts

- No named Event Director/deputy or conflicting command authority.

- Different teams are using different or superseded schedules, plans or guest lists.

- Critical RAG status lacks evidence, owner, action, deadline or freshness.

- A dependency or receiving stage is unready while upstream release is approaching.

- A critical message has been sent but not acknowledged/accepted.

- Issue exceeds five minutes without owner/deadline—or is safety-critical and not immediately escalated.

- Late change after T-15 lacks material exception, authority or propagation.

- Plan B/C threshold is reached without activation decision, or trigger data is unreliable.

- Vendor failure has no guest-continuity response.

- Host is being asked to coordinate vendors or solve operational issues.

- Command data is stale, communications have failed or command-centre continuity is impaired.

- Crowd behaviour is being treated as emotional fact or used for unauthorised surveillance.

## 45.3 Command measures

| Dimension | Measures |
| --- | --- |
| Visibility | Critical-state freshness, Unknown duration, variance-detection time and board completeness |
| Ownership | Unowned issues, owner acceptance time, deputy coverage and missed deadlines |
| Communication | Acknowledgement time, closed-loop completion, misrouted messages and channel failures |
| Decision | Decision latency, trigger compliance, authority fit and late-change propagation |
| Handoff | Planned/accepted/completed rates, failed handoffs and receiving-readiness exceptions |
| Recovery | Containment, resolution, guest continuity, comfort restoration and recurrence |
| Host protection | Host operational interventions and vendor questions redirected/avoided |
| Guest experience | Queue/flow thresholds, repeated questions, material friction and visible disruption |

# 46. Module 6 relationships, exclusions and gaps

## 46.1 Relationship to Modules 1–5

| Existing foundation | Module 6 contribution |
| --- | --- |
| Invisible choreography | Turns preparations into a live command system while machinery stays backstage |
| Guest journey transitions | Adds closed-loop handoff states, receiving readiness and command visibility |
| Friction / anticipation | Adds live variance, crowd signals, bottlenecks and next-15-minute control |
| Protocol / culture | Integrates specialist authorities without letting operations invent requirements |
| VIP ownership | Connects VIP Control Desk to whole-event command and escalation |
| Host confidence | Formalises the Maison Doclar shield between host/guest and operational complexity |
| Learning governance | Adds decision, incident, recovery, vendor and after-action evidence |

## 46.2 Exclusions applied

The Module 6 CEO Master Exercise was excluded. Its operational lessons—simultaneous power, catering and transport issues before opening—are represented in RAG, priority, ownership, pre-open, contingency, host-communication and escalation controls.

## 46.3 Safety and specialist limitation

This module provides coordination architecture, not medical, emergency, security, engineering, fire, crowd-safety or regulatory procedures. Those require qualified professionals, venue/public-authority requirements and jurisdiction-specific plans. Event command must surface and support their authority rather than improvise or override it.

## 46.4 Explicit gaps identified

- No event complexity/risk model defines when a Command Centre or each command role becomes mandatory.

- Command span-of-control, deputy, handover, fatigue and shift standards remain undefined.

- No approved decision-rights matrix separates CEO, Event Director, function, vendor and specialist authority.

- Master Timeline, Run of Show, Programme and specialist-plan schemas need field-level release/change rules.

- RAG criteria, freshness thresholds and readiness evidence are not calibrated by domain.

- The priority pyramid needs formal severity/urgency definitions and ties to incident categories.

- The five-minute rule, update cadence and escalation deadlines require event-risk calibration.

- Radio/channel plans, licensing/equipment, call signs, backup communications and data sensitivity need specialist policy.

- T-60, T-15 and go-live gates need event-type templates, acceptance authority and stop/open criteria.

- Crowd-flow capacity, bottleneck thresholds and privacy-respecting observation standards require qualified crowd-safety input.

- Contingency triggers need authoritative data sources, confidence treatment and simulation/rehearsal methods.

- Emergency, medical, security, fire, weather, power and venue-failure plans require qualified specialist modules.

- Vendor recovery, evidence, service credits, replacement authority and post-event accountability need contract integration.

- Offline resilience, device loss, power/connectivity failure and command-centre relocation procedures are undefined.

- After-action review, incident preservation, corrective action and knowledge-promotion workflows need formal ownership.

- No validated command dashboard, alert-volume, false-alarm or human-factors evaluations have yet been designed.

# 47. Vendor and supplier operating doctrine

**CORE RULE Vendors deliver components; Maison Doclar owns the

integrated experience. Supplier behaviour, timing, resilience and

discretion are therefore brand-performance variables.**

| Doctrine | Executable meaning |
| --- | --- |
| Capability before category | Define the outcome/capability required before searching for a company label |
| Evidence before promise | Evaluate comparable delivery, operating team, capacity, dependencies and recovery—not sales presentation alone |
| Alignment before access | Brief and acknowledge service, conduct, privacy, command and guest-facing rules before deployment |
| One accountable lead | Each supplier names one operational lead/deputy and receives instructions through one Maison Doclar contact |
| Control dependencies | Record both what each vendor needs and who/what relies on its output |
| Inspect before exposure | “Finished” is not accepted until objective guest-ready evidence passes |
| Recover first; review later | Contain guest impact and activate continuity without public dispute; preserve accountability evidence |
| Memory with context | Performance becomes reusable intelligence only with event scope, evidence, limitations and review state |

**MODULE 13 ADDENDUM Total cost, not headline price, governs

comparison (48.4); good vendors also select their clients — Maison

Doclar should be the kind of client excellent suppliers want to work

with (clear briefs, fair terms, proper payment, respected contracts),

since this affects who is available to appoint at all.**

**MODULE 18 ADDENDUM Never promise a client a change (“of course we

can do that”) before operations has confirmed it is actually

deliverable — credibility, once promised, is Maison Doclar’s to keep

or lose, not the vendor’s.**

# 48. Supplier intelligence, classification and appointment

## 48.1 Intelligence file

The reusable Supplier Intelligence File contains identity, ownership, contacts, specialisation, operating history, relevant portfolio, capacity, equipment, people, commercial position, availability, required credentials, safety capability, backup, subcontracting, terms, performance evidence, strengths, limitations, risks, relationship status and last review. Claims and verified facts remain separate.

## 48.2 Two classifications that must not be confused

| Classification | Purpose | Rule |
| --- | --- | --- |
| Relationship class | A strategic partner; B core supplier; C specialist; D support | Sets governance effort; does not guarantee appointment |
| Approval state | Preferred; approved; conditional; suspended; do not use | Controls eligibility and exceptions |
| Event appointment | Proposed; due diligence; selected; contracted; briefed; ready; active; closed | Tracks one event and one defined scope |

(M13-D02, resolved) Module 13’s “Vendor Pyramid” is not a third classification. Its tiers map onto Approval State: Strategic Partners and Preferred Suppliers -> Preferred; Approved Suppliers -> Approved; Probationary/New -> Conditional. Relationship Class already carries the “strategic partner” distinction within Preferred where relevant.

## 48.3 Due-diligence decision flow

- Define the guest-facing capability, acceptance standard and failure consequence.

- Set the due-diligence tier from criticality, safety/regulation, substitution difficulty, scale, data access and reputation exposure.

- Verify the legal/trading party, actual operational lead, capacity/resources, subcontractors, relevant credentials and conflicts.

- Test recent comparable evidence and references, asking how failures were owned and recovered.

- Assess dependencies and a credible backup—not “we have never had a problem.”

- Compare candidates across quality, reliability, alignment, resilience, discretion and commercial fit.

- Record recommendation, exceptions, approvals and expiry; appointment is not final until commercial and operating readiness gates pass.

**ANTI-BIAS CONTROL Price, prestige, founder charisma, friendship and

attractive portfolio material may inform context but cannot substitute

for comparable evidence and delivery controls.**

## 48.4 Due-diligence diagnostic techniques (Module 13)

Module 13 (“Vendor & Supplier Mastery”) is, in large part, a worked restatement of Module 7’s doctrine rather than a new domain — its central principle (“you can outsource execution; you cannot outsource responsibility”) is the same core rule already stated at Section 47, and most of its structures (vendor file, brief, dependency graph, readiness gate, failure sequence, scorecard) already exist here in more executable form. Where Module 13 adds genuine value is in supplying concrete diagnostic technique for the abstract due-diligence steps at 48.3:

- Portfolio test: do not accept “can you do luxury events” as evidence; require three comparable events the candidate personally delivered, and examine quality, scale, consistency, finishing, staffing and guest environment directly rather than through marketing material.

- Vendor interview protocol: a structured conversation covering experience, maximum comfortable capacity, who is actually on site, preparation process, contingency, communication point of contact, self-quality-checking method, and — the most revealing question — a real account of a major problem and how it was solved. A candidate who claims to never have problems is a weaker signal than one who can describe a recovery.

- Total cost of failure: extends the 48.3 candidate-comparison step

  - with an explicit economic frame — a cheaper vendor’s true cost includes replacement cost, time, staff stress, client confidence, guest impact and reputational damage if they fail; comparison should weigh total risk, not headline price.

These techniques attach to due-diligence step 68 (comparable evidence and references) and step 69 (candidate comparison) and do not change the due-diligence flow itself.

## 48.5 The vendor partner code (Module 13)

Sections 47–51 repeatedly reference a vendor “code” (the 51.2 readiness gate requires “current brief and code acknowledged”) without ever specifying its content. Module 13 supplies that content, and it is adopted here as the Maison Doclar Partner Code:

| Domain | Standard |
| --- | --- |
| Presence | Arrive early; look presentable (uniform, grooming, identification); no unkempt crew, casual eating in guest areas or excessive phone use in guest sightline |
| Conduct | Know your role; do not argue in front of guests; do not create noise; do not block guest flow; leave the venue clean |
| Confidentiality | Do not discuss who attended, what was spent, family matters, disputes or VIP requests outside the command structure (“no gossip”); protect confidentiality as part of the job, not a favour |
| Command | Escalate problems through the designated channel rather than improvising or accepting instructions outside it; follow the command structure and respect protocol |
| Content | No photography/recording or posting beyond what the event’s photography and content-rights terms (cross-reference 85.1) permit |

This code is the content that the existing “Brief/conduct” gate (51.2) and Vendor brief “Boundaries” domain (49.1) already require to be acknowledged; it does not add a new data object, but it removes a previously open content gap.

## 48.6 Vendor removal criteria (Module 13)

A single failure does not necessarily change a supplier’s Approval State (48.2); a pattern of poor reliability, dishonesty, repeated lateness, quality inconsistency, unsafe behaviour, confidentiality breach or unprofessional conduct is grounds for reassessment or removal. This partially resolves the Section 53.4 gap noting that preferred/approved/suspended states lacked review/appeal rules — it supplies the trigger condition, though authority, process and appeal rights remain undefined (M13-D04).

## 48.7 Vendor maturity model — folded into Approval State, not a new dimension (Module 18)

Module 18 proposes a five-level “Vendor Maturity Model” (Untested -> Approved -> Proven -> Preferred -> Strategic). This is the same pattern already resolved once at M13-D02, when Module 13’s four-tier “Vendor Pyramid” was folded into the existing Approval State field rather than kept as a competing classification. The same resolution applies directly here, on precedent, without a new decision: Untested sits below Conditional (no due-diligence history yet); Approved and Proven both map to the existing Approved state, with “Proven” simply meaning the Supplier scorecard history (48.1) has accumulated enough events to support it — no new state is needed for that, since it is what the scorecard history already shows; Preferred maps to Preferred; Strategic maps to Preferred combined with Relationship Class A (strategic partner, 48.2), which already exists for exactly this purpose. No third or fourth vendor classification dimension is created.

## 48.8 The no-surprise principle — partial resolution of the subcontractor-visibility gap (Module 18)

Section 53.4 already flagged that “subcontractor visibility, approval and inherited briefing/credential requirements are incomplete.” Module 18’s no-surprise principle — Maison Doclar should never discover on event day that a vendor subcontracted a component, changed key personnel, or substituted equipment without this being permitted and communicated — is adopted directly as the operating rule this gap was missing: any such change is treated as a scope change and must pass through the existing change state machine (49.3) before it happens, not be discovered after. This does not fully close the gap (a formal subcontractor-approval and inherited-credential process is still undefined), but it supplies the governing principle.

# 49. Brief, conduct, scope and change control

## 49.1 Released vendor brief

| Brief domain | Required content |
| --- | --- |
| Intent | Event/client context, promised experience and success definition |
| Guests | Minimum necessary profile, VIP/service instructions, privacy and visibility restrictions |
| Delivery | Aesthetic, service standard, deliverables, milestones, venue/access constraints and acceptance evidence |
| Integration | Dependencies, receiving teams, command contact, communication and escalation |
| Boundaries | Non-negotiables, branding/phone/social-media/photography rules, conduct and specialist authority |
| Continuity | Backup, failure triggers, replacement path, breakdown/departure and incident evidence |
| Control | Version, recipient operational lead, questions, acknowledgement and supersession |

## 49.2 Scope and commercial control

A scope must answer what, how much, when, where, to what standard, by whom and what happens if delivery changes or fails. It also records exclusions, price/payment, overtime, cancellation, damage, material ownership, weather/force-majeure treatment where applicable, change authority and acceptance evidence. Contract terms require appropriate commercial/legal review; this specification is not a contract template.

### 49.2.1 Mock-up / first-article approval (Module 18)

For design-heavy or high-volume deliverables (décor, floral, signage, printed materials, table settings, guest gifts), the scope should include an explicit design/mock-up approval milestone before mass production or full installation: one representative finished example is approved, then the vendor is instructed to replicate that approved standard. This sits earlier in the milestone sequence than the existing guest-ready checkpoint (51.1) — it is a production-stage gate, not a setup-stage one — and is adopted as a new milestone type rather than a new object, since Scope of work (Section 5) already carries a milestones field.

### 49.2.2 Commercial authority ladder — resolved in structure (M13-D03)

First flagged under Module 7, restated by Module 13 and Module 18 without resolution. Resolved in structure, reusing the 76.2 escalation ladder rather than inventing a separate financial-authority model:

| Ladder level * | *Spend authority** |
| --- | --- |
| 1 — Frontline | Small guest-recovery gestures within the delegated limits already established at 104.3 (complimentary refreshments, seating adjustment, small amenities); no new mechanism, this section only confirms it sits on the same ladder as every other level below |
| 2 — Supervisor | Activating a pre-priced backup resource already named in that vendor’s contingency plan (51.2) — this is not new spend, since the cost was already contemplated and approved when the contingency was first approved |
| 3 — Department/ Function Lead | Scope changes within an existing vendor category (e.g. additional catering for a confirmed guest- count increase), following the existing Change state machine (49.3) through to its Approved state |
| 4 — Event Director | Like-for-like emergency vendor replacement, up to the value of the original failed vendor’s contract, is Event Director authority regardless of amount — this protects a commitment already made to the client rather than creating a new one, and should not wait on a percentage threshold. Net-new spend (anything beyond replacing a failure at comparable cost) is capped at an event-specific percentage of total event budget, set per event on the Master Event File |
| 5 — CEO | Any net-new spend above the Event Director’s percentage cap; any change to client billing or contract terms; any commitment not already contemplated in the approved event budget |

The distinction at Level 4 matters: replacing a failure is not the same decision as adding scope, and treating them identically (both gated behind the same percentage threshold) would either make emergency recovery too slow or make budget creep too easy. Separating them fixes both.

What is deliberately left as an event-specific parameter, not a global default: the exact percentage caps at Levels 4 and 5. This specification recommends the shape of the ladder; the actual percentages should be set against Maison Doclar’s real event-budget ranges and cash-flow position, which this document does not have visibility into — consistent with how weather and other operational thresholds are already left venue/event-specific rather than defaulted globally (83.3). Until set per event, Level 4’s net-new-spend cap and Level 5’s floor default to CEO approval required, i.e. the safer direction when the number is unset.

### 49.2.3 Payment-milestone structure — resolved in structure (M13-D03)

Payment releases are tied to the same milestone chain already established across 49.2.1, the vendor clock (Module 8) and the readiness gates (51.1–51.2), rather than to elapsed time or informal assurance:

- Booking: secures the date/resource commitment.

- Mock-up/first-article approval (49.2.1): released only after design sign-off, never before — this is the payment structure’s direct enforcement mechanism for that gate; a vendor has no financial incentive to skip it if payment depends on passing it.

- Delivery/installation sign-off (51.1–51.2): released once the guest-ready checkpoint is passed for that vendor’s deliverable, not on “installed” alone (13.30’s installed-versus-operational distinction applies directly to payment timing, not only to readiness assessment).

- Final retention, released on Supplier scorecard completion: a final tranche is deliberately withheld until the post-event Supplier scorecard (52.5) is filed — this is the enforcement mechanism behind the existing “payment should not replace performance review” principle (18.70): if the review never happens, the vendor is not fully paid, which gives the review itself real teeth instead of being an optional afterthought.

The specific percentage split across these milestones is, like 49.2.2, an event/vendor-category-specific parameter this specification does not default globally — but the structure (deposit, gated production release, gated delivery release, review-linked retention) is now canonical and closes the structural half of M13-D03. Exact commercial terms remain subject to appropriate legal/commercial review per supplier agreement (49.2).

## 49.3 Change state machine

| State | Required evidence |
| --- | --- |
| Requested | Requester, reason, desired result and deadline |
| Assessed | Scope, cost, time, quality, safety, guest and dependency impact |
| Approved / rejected | Correct authority, conditions and timestamp |
| Communicated | Vendor lead and every affected owner acknowledge released instruction |
| Implemented | Completion and acceptance evidence; affected artefacts updated |
| Closed | Commercial consequence and learning recorded |

Family, host, CEO and client-nominated supplier requests are routed through the designated command path. Respect for relationship authority does not permit contradictory live instructions or unrecorded commitments.

# 50. Vendor dependency, arrival and setup control

## 50.1 Dependency graph

Each critical deliverable records upstream inputs, downstream consumers, latest safe handoff, receiving readiness, verification owner, failure signal and fallback. The system should calculate likely cascade impact when access, venue, power, kitchen, production, transport or another shared dependency moves.

Guest, principal, protocol, service, production and information movement are each already tracked individually across this specification. Overlaying them on one map specifically to spot where they collide — a guest route crossing a production load-in path, a protocol procession timed against a service window — is a deliberate practice, not a separate data source: it reads the same dependency graph and positioning maps (65.1, 102.3) from more than one flow at once rather than one at a time.

## 50.2 Controlled arrival and zones

| Control | Minimum evidence |
| --- | --- |
| Arrival plan | Gate, arrival window, contact, vehicle/parking/loading, restrictions and departure |
| Check-in | Company, accountable lead, authorised roster, identification, vehicles, equipment and actual arrival |
| Zone assignment | Setup, storage, holding, waste and guest-route restrictions |
| Milestones | Load-in → setup → test → ready → lock, each with owner and evidence |
| Access exception | Reason, security/operations authority, affected schedule and expiry |

## 50.3 Pre-event coordination

For significant events, the system schedules and records the vendor conference and physical walkthrough. Attendance and acknowledgement are required from relevant operational leads. Guest routes, VIP routes, loading, parking, power, kitchen, backstage, storage, toilets, emergency exits and production positions are validated with their qualified owners.

## 50.4 Critical path (Module 13)

The 50.1 dependency graph already models upstream inputs, downstream consumers and cascade impact; the critical path is that graph’s longest unbuffered chain (e.g. venue access -> stage -> production -> technical test -> rehearsal -> ceremony) — the sequence whose delay delays everything downstream. It is named here as an explicit derived output of the existing dependency graph, not a new object, and should receive monitoring priority over non-critical-path dependencies of equal individual risk score.

# 51. Quality, readiness and live vendor control

## 51.1 Checkpoints and acceptance

| Checkpoint | Decision |
| --- | --- |
| Arrival | Correct team, equipment, access and timing? |
| Setup | Scope, location, dependencies and emerging defects controlled? |
| Technical test | Function and backup evidenced by competent owner? |
| Guest-ready | Appearance, function, cleanliness, safety, position, timing, staff, branding, guest impact and backup accepted? |
| Breakdown | Departure, venue protection, waste, assets, incidents and closeout complete? |

Safety in the ten-point inspection is a routing and gate field, not a claim Maison Doclar’s generalist staff or AI may certify. Electrical, structural, fire, medical, security, food-safety and other regulated matters require competent, jurisdiction-appropriate acceptance.

### 51.1.1 Inspection techniques for the guest-ready checkpoint (Modules 13, 21)

Four concrete methods for exercising the “guest-ready” checkpoint above: the Final Walk (walk the venue as if a guest, before guests enter, looking for exposed cables, boxes, staff congestion, unfinished décor, dirty areas, blocked routes); the five-metre test (stand back and note what catches the eye first); the guest-eye test (repeat the walk in the perspective of an elderly guest, a VIP, an international guest, a first-time guest and a guest arriving alone, since each notices different failures); and the First Guest Test (Module 21: an uninvolved person, not briefed on the event, physically walks the guest journey while staff watch where they hesitate — genuinely unbiased, unlike the first three, which staff perform on themselves). These are techniques for applying the existing checkpoint, not a new gate.

## 51.2 Vendor readiness gate

| Gate | Pass condition |
| --- | --- |
| Appointment | Approved party and event-specific scope; exceptions visible |
| People | Named operational lead/deputy, roster and required competence/credentials verified |
| Brief / conduct | Current brief and code acknowledged; minimum necessary information released |
| Scope / commercial | Deliverables, milestones, standards, dependencies, contingency and change authority agreed |
| Access / setup | Arrival, check-in, zones, restrictions, test and lock times confirmed |
| Dependencies | Upstream inputs and downstream handoffs accepted with fallback |
| Inspection | Required checkpoints passed or residual exception accepted by the right authority |
| Backup | Failure trigger, substitute resource/vendor, activation owner and time-to-recover credible |
| Command | One instruction channel, communications check and escalation path active |

## 51.3 Live failure sequence

| Step | System action |
| --- | --- |
| Contain | Protect safety, dignity, privacy and prevent guest-visible spread |
| Assess | Verify severity, capability loss, cascade, recovery window and specialist authority |
| Activate | Deploy approved backup/replacement and update dependent plans |
| Inform | Notify only relevant command/commercial/specialist roles; give guests calm service information where needed |
| Recover | Restore promised outcome, continuity and confidence; verify acceptance |
| Document | Preserve times, evidence, decisions, cost and contractual facts |
| Review | Score performance, decide corrective action/status and propose controlled learning |

Module 13’s “Vendor Failure Response” (Identify -> Contain -> Substitute -> Communicate -> Recover -> Review) describes the same sequence as the table above with different labels and one step short (it has no explicit Document step). This table remains canonical because it already includes evidence preservation; Module 13 contributes no new failure- handling logic here.

### 51.3.1 The recovery ladder (Module 18) — what “Activate” actually chooses between

The Activate step above says to deploy an approved backup or replacement without specifying which kind of response that should be. Module 18’s five-level recovery ladder fills that gap directly, ordered by increasing severity/cost: (1) correct internally (the vendor fixes it themselves, no escalation needed); (2) deploy backup resource (equipment or personnel, same vendor); (3) reconfigure the service (change scope or method to work around the failure); (4) replace the supplier/service (activate a second-source vendor, 48.3); (5) escalate to client/CEO (per the 76.2 ladder, when impact exceeds operational authority). This is adopted as the menu Activate selects from, not a new escalation model — level 5 is simply a pointer to the existing 76.2 ladder rather than a duplicate of it.

# 52. Vendor intelligence, alerts and recommendations

## 52.1 Intelligence products

- Capability coverage and single-supplier concentration map

- Evidence freshness and due-diligence exception report

- Candidate comparison and appointment recommendation with confidence

- Brief/acknowledgement, code and privacy-readiness view

- Scope, milestone, dependency and change-impact monitor

- Arrival/check-in/setup-zone exception dashboard

- Guest-ready inspection and defect closure report

- Backup credibility and replacement-time analysis

- Event scorecard and context-aware partner-network review

- Corrective action, suspension/reapproval and institutional-learning proposal

## 52.2 Alerts

- Critical capability has no approved supplier or credible fallback.

- Supplier is preferred generally but not approved/ready for this event scope.

- Capability evidence, credentials, insurance or review state is missing/expired where required.

- Sales contact is confirmed but actual operational lead/deputy is not.

- Subcontractor, equipment ownership or capacity differs materially from the appointment basis.

- Released brief/scope/code is unacknowledged or teams use conflicting versions.

- Vendor has received an instruction outside its designated channel.

- Milestone or dependency threatens the latest safe handoff or guest-ready time.

- Vendor has arrived with unapproved people, vehicles, equipment or access route.

- Inspection defect remains open at lock/go-live or safety acceptance is absent.

- Scope change lacks impact assessment, authority, communications or commercial record.

- Backup cannot meet the recovery window, or replacement activation is overdue.

- Supplier dispute, branding, phone/social-media, privacy or conduct issue is guest-visible.

- Score average masks a critical safety, privacy, integrity, reliability or guest-harm failure.

## 52.3 Recommendation boundaries

The system may recommend shortlist, due-diligence tier, missing evidence, inspection priority, contingency activation and relationship review. It must explain sources, context, confidence, material exceptions and authority. It must not autonomously appoint, contract, pay, blacklist, disclose allegations, waive a safety gate or share restricted guest intelligence.

## 52.4 The Six-P Test — a qualitative frame, not a new scorecard (Module 18)

Promise -> Preparation -> Presentation -> Performance -> Recovery -> Professionalism. This is adopted as a qualitative evaluation lens for briefing and coaching conversations with a vendor — did they deliver what was promised, prepared properly, presented correctly, performed under load, recovered well from any issue, and behaved professionally throughout. It organises the questions to ask about a vendor the same way the people/place/information/reputation frame (Module 17, 120.2) organises risk categories, and does not compete with the canonical Supplier scorecard (52.5) as a scored record.

## 52.5 Vendor scorecard — resolved (M18-D01)

Module 18 proposed its own supplier scorecard (Quality, Reliability, Communication, Timeliness, Presentation, Guest interaction, Problem solving, Flexibility, Value, Overall — scored /10), different in both field set and scale from the canonical Supplier scorecard already resolved at M13-D01. Presentation and Guest interaction mapped to existing fields under different names (professionalism, guest impact) and were not added. Resolved: Communication, Timeliness and Flexibility are added as three new canonical fields (Section 5), the scale is standardised to /10 across every field, and the field set is now closed to further proposals absent a new CEO decision.

## 52.6 Supplier Intelligence File — field enrichments (Module 18)

Module 18’s supplier-database field list (geographic coverage, pricing band, typical lead time, failure patterns, recovery ability) adds real detail to the existing Supplier Intelligence File (48.1) rather than proposing a new object; these fields are folded into that file’s content list.

# 53. Module 7 relationships, geography, exclusions and gaps

## 53.1 Relationship to Modules 1–6

| Existing foundation | Module 7 contribution |
| --- | --- |
| White-glove promise | Makes external delivery quality, conduct and discretion measurable brand controls |
| Guest journey | Maps suppliers to owned touchpoints, transitions and guest-visible failure consequences |
| Protocol / culture | Requires relevant vendors to receive verified, minimum necessary ceremonial and cultural instructions |
| VIP intelligence | Restricts vendor access while ensuring operationally necessary service, privacy and visibility requirements |
| Event Command | Deepens Vendor Matrix, dependencies, RAG, handoffs, contingency, guest recovery and after-action evidence |
| Learning governance | Builds contextual supplier memory without turning claims or isolated impressions into doctrine |

## 53.2 Global and Lagos treatment

The capability, evidence, briefing, scope, dependency, inspection, change, recovery and scoring logic is globally reusable. Lagos/Nigeria context packs may hold locally verified supplier-market categories, venue/access patterns, traffic and weather exposure, power/connectivity resilience, payment/currency practice, locally applicable licences/insurance/regulatory requirements and replacement lead times. These are event facts or maintained context—not permanent assumptions about any supplier or city.

## 53.3 Exclusions applied

The “Follow the Guest” activity and CEO Master Exercise were excluded as exercises. Their operational value is represented through journey ownership, supplier-to-touchpoint mapping, capability coverage, due diligence, failure recovery and readiness controls.

## 53.4 Explicit gaps and contradictions

- The A–D vendor classes and preferred/approved/suspended states need formal definitions, owners, expiry and appeal/review rules.

- No risk-tier model defines due-diligence depth by capability, scale, safety/regulation, data access, spend, reputation or replacement difficulty.

- The illustrative scorecard weights are unvalidated and conflict with the 1–5 overall score unless aggregation, evidence and critical-failure overrides are specified.

- Capability thresholds for catering scale, fleet, power/production redundancy, staffing and simultaneous service require category-specific expert standards.

- Required licences, insurance, health/safety, food, transport, security, medical, labour, tax and contracting controls vary by jurisdiction and need specialist/legal ownership.

- Supplier privacy, reference checking, performance allegations, retention, access, response rights and do-not-use records need a fair and lawful governance policy.

- No conflict-of-interest, gifts, commissions, related-party, bribery or procurement-integrity policy is defined.

- Commercial authority limits, deposits, cancellation, overtime, damage, service credits, emergency spend and replacement approval remain undefined.

- Client-nominated/friend vendor exception, indemnity and refusal/escalation rules need contractual alignment.

- Vendor code enforcement, breach levels and immediate removal/stand-down authority need approval.

- Subcontractor visibility, approval and inherited briefing/credential requirements are incomplete.

- Acceptance evidence and “guest ready” standards need category templates and separation from regulated/safety certification.

- Preferred status must not create complacency; reassessment frequency, event-specific fit and concentration risk need rules.

- Vendor score calibration, reviewer bias, sample-size context, dispute resolution and audit/evaluation methods are not yet defined.

- Replacement network availability, response times and offline/contact resilience need Lagos and destination-specific evidence.

- No supplier portal, evidence-upload, acknowledgement, access-control or data-migration design has yet been validated.

- (Module 13, RESOLVED) Three different vendor scorecard category/weight sets now exist in this specification. This module’s original scorecard (quality, reliability, professionalism, responsiveness, guest impact, problem-solving, commercial discipline) is canonical, with value added as an eighth field per M13-D01. Module 13’s weighted model (quality 25%, reliability 20%, experience 15%, communication 10%, presentation 10%, contingency 10%, value 10%) and its second scorecard list (quality, reliability, communication, presentation, flexibility, problem-solving, guest impact) are both retired; the underlying concepts they raised (experience, flexibility, presentation) can be considered within “quality” and “professionalism” rather than as separate scored fields.

- (Module 13, RESOLVED) The Vendor Pyramid (Strategic Partners / Preferred / Approved / Probationary) overlaps two existing classification dimensions. The Pyramid is retired as an independent model. Its four tiers are folded into the existing Approval State field (48.2): Strategic Partners and Preferred Suppliers both map to Preferred (the Relationship Class A–D field already distinguishes strategic-partner-level suppliers within that state); Approved Suppliers maps to Approved; Probationary/ New maps to Conditional. No new field is created.

- (Module 13, resolved in structure) Commercial authority limits, deposits and emergency payment/replacement approval remained undefined. Resolved via the commercial authority ladder and payment-milestone structure (49.2.2-49.2.3); exact percentages remain an event-specific parameter (M13-D03).

- (Module 18, resolved in structure) Commercial authority limits and payment-milestone structure were restated a third time without new specifics. Same resolution applies (49.2.2-49.2.3); this was the most-repeated unresolved item in the vendor domain before being closed structurally.

- (Module 18, resolved) A fourth vendor scorecard proposal diverged from the canonical one on both field set and scale. Communication, Timeliness and Flexibility added; scale standardised to /10 (52.5, M18-D01).

# 54. Ceremony architecture doctrine

**CORE RULE Ceremony is a controlled sequence of human movements that

communicates honour, belonging, dignity and authority. The visible

programme is only one view of the operating system beneath it.**

| Layer | System responsibility |
| --- | --- |
| Public ceremony | What guests see: procession, introductions, speeches, prayer, presentation, music and photographs |
| Protocol operation | People, positions, routes, holding, seating, microphones, cues and movement control |
| Invisible intelligence | Readiness, next-state prediction, waiting people, dependencies, equipment and variance kept outside guest attention |

Every important moment is specified by who, where, when, how and why. “Why” records the intended meaning and prevents the system from optimising timing at the expense of dignity or authority.

# 55. Ceremony spine, principal and movement model

## 55.1 Ceremony spine

The ceremony spine is the approved sequence of protected moments. It is created only after identifying required people, positions, governing authority, intended message and dependencies. Optional detail is attached to the spine; it does not define it.

## 55.2 Principal model

| Element | Required control |
| --- | --- |
| Principal identity | One, joint or phase-specific principal; protected purpose and authority confirmed |
| Route | Vehicle → arrival → receiver → holding → ceremony → seat/position → photography/reception → departure |
| Experience protection | Visibility, comfort, privacy, security, timing, information and recovery requirements |
| Ownership | Movement Lead plus deputies and closed-loop handoffs at every transition |
| Exception | Early/late/unexpected movement options and approval authority |

## 55.3 Ceremonial movement matrix

For every principal, dignitary, speaker, elder or ceremonial participant, the matrix links arrival window, receiver, entrance type, route, holding, position/seat, speaking/presentation/photo obligations, departure, owners and contingencies. Authority is contextual: formal, traditional and social/personal hierarchies remain separate, with the governing hierarchy named per moment.

# 56. Run-of-show, cue and clock control

## 56.1 One content model, four views

| View | Audience and purpose |
| --- | --- |
| Master Event Timeline | Whole-event ecosystem, dependencies, vendors and operational milestones |
| Run of Show | Internal ceremonial sequence: time/window, duration, action, location, owner, cue, dependencies and next |
| Cue Sheet | Role/department-specific precise triggers, actions, equipment/content and acknowledgements |
| Guest Programme | Elegant public summary with no backstage mechanics or sensitive data |

## 56.2 Critical cue contract

A cue contains trigger, authoritative source, prerequisites, GO/HOLD state, cue giver, recipient, action, acknowledgement, execution evidence, expiry and cancellation/recovery path. Critical movement cannot begin merely because it “looks like time.”

## 56.3 GO/HOLD and stop authority

| State | Meaning | Authority treatment |
| --- | --- | --- |
| Not ready | Prerequisite or evidence missing | Do not cue; owner resolves or escalates |
| HOLD | Movement is actively prevented | Named Cue Caller/Event Director; specialist stop overrides |
| GO | All required gates passed and movement authorised | One clear cue through the approved channel |
| Executed | Recipient confirms action and receiving stage confirms outcome | Record actual time and exception |
| Cancelled / recovered | Cue no longer valid or fallback used | Update dependent items and released views |

## 56.4 Ceremonial clock

All operational views use one designated event time source with synchronisation checks, tolerance, drift alert and fallback. Planned time, arrival window, predicted time, cue time and actual time remain distinct fields.

# 57. Arrival, holding, receiving and departure

## 57.1 Arrival window logic

Each protected arrival has earliest acceptable, ideal and latest acceptable times, plus holding capacity, receiver readiness, route status, ceremony dependency and hold/continue decision logic. An early arrival triggers welcome, privacy, refreshment and an appropriate representative; a late arrival triggers a cascade assessment rather than automatic ceremony stoppage.

## 57.2 Holding and receiving readiness

| Control | Pass condition |
| --- | --- |
| Holding | Correct area, access, privacy/security, comfort, capacity, information, liaison and release route ready |
| Receiving line | Approved order/positions, spacing, greeting duration, photo rule, flow/queue threshold and exit route |
| Handoff | Vehicle/security/protocol/host/escort/seat receiving owners acknowledge readiness |
| Dignity | Mobility, age, comfort, cultural/protocol and visibility needs protected without unwanted spectacle |

## 57.3 Departure protocol

Departure is a protected final transition: time/window, vehicle and driver readiness, route, escort, farewell person, belongings, security, privacy, interaction with other departures and impact on the remaining programme are controlled and acknowledged.

# 58. Speakers, MC, stage and photography

## 58.1 Speaker and MC control

Every speaker receives a versioned brief covering purpose/topic, approved introduction, title/pronunciation, slot/window, minimum/target/maximum duration, holding location, cue owner, microphone, position, exit and content sensitivities. The MC is the public voice, not the protocol or command authority; improvisation boundaries are explicit.

## 58.2 Stage and position governance

Stage, standing, seat, table and receiving-line positions encode meaning. Protocol/Seating authorities reconcile the governing hierarchy with host intent, relationships, access, mobility, sightlines, security, conversation and photography; visual balance alone is insufficient.

## 58.3 Photographic protocol

| Control | Required decision |
| --- | --- |
| Movement zones | Where photographers may stand/move and when |
| Restricted moments | Privacy, cultural, religious, security and publication limitations |
| Formal groups | Named Group A/B/C membership, order, positions, assembly owner and release |
| Timebox | Target/maximum duration and escalation; “90 seconds” is a design objective, not a universal rule |
| Priority | Ceremony and guest dignity govern; photography does not independently redirect principals or guests |

# 59. Transitions, buffers and ceremony recovery

## 59.1 Transition contract

Every transition specifies origin/destination, participants, movement/route, owner, cue, duration/window, receiving readiness, bridge option, fallback and guest-facing continuity. Dead air is treated as an exception in transition design—not as a demand for constant entertainment.

## 59.2 Programme resilience

| Class | Meaning | Live treatment |
| --- | --- | --- |
| Non-negotiable | Protected outcome/act must occur | Preserve scope/order unless reserved authority approves change |
| Flexible | May shorten, expand or move within bounds | Use approved minimum/maximum and dependency rules |
| Removable | May be omitted under defined conditions | Named authority removes; affected participants/vendors/views are updated |

(Module 16) Module 16’s “Essential/Important/Optional” programme classification is the same three-tier model under different labels (Essential=Non-negotiable, Important=Flexible, Optional=Removable). The table above remains the one canonical taxonomy.

## 59.3 Delay-cascade analysis

When a forecast or actual variance exceeds the item’s tolerance, the system traces seating, introductions, speakers, photography, catering, entertainment, transport, venue deadlines, staff/vendor commitments and guest comfort. It recommends hold, continue, bridge, shorten, remove or resequence options with time recovered, new risks, dignity/protocol consequences and approval requirements.

**RECOVERY RULE Recover the promised ceremony, not merely the clock.

Never save minutes by casually damaging dignity, sacred meaning, formal

obligation, safety or the principal’s protected experience.**

# 60. Ceremony readiness, intelligence and alerts

## 60.1 Ceremony readiness gate

| Gate | Pass condition |
| --- | --- |
| Purpose / authority | Host intention, principal(s), governing hierarchies and reserved authorities confirmed |
| Architecture | Approved spine, moments, movement matrix and control sheet |
| Source of truth | Released Run of Show; Cue Sheets and guest Programme derived/current; superseded versions withdrawn |
| People / positions | Required participants, receivers, speakers, MC, owners/deputies, holding and positions confirmed |
| Protocol / culture | Precedence, titles, pronunciation, introductions, acts, gestures and international guidance verified |
| Routes / spaces | Arrival, holding, receiving, stage, guest movement, photography and departure routes accepted |
| Cues / clock | Authoritative clock, cue matrix, GO/HOLD authority, channels and acknowledgements tested |
| Production / vendors | Music, microphones, lighting, video, photography, transport and relevant dependencies ready |
| Resilience | Windows, buffers, bridges, flexible/removable decisions and late/early/recovery options approved |
| Safety / dignity | Qualified specialist gates passed; privacy, access, comfort and principal protection ready |

## 60.2 Alerts and recommendations

- Ceremonial moment lacks purpose, owner, position, cue, next state or governing authority.

- Principal route or protected movement has an unready handoff, blocked path or no deputy.

- Critical cue is GO while a prerequisite, recipient acknowledgement or receiving stage is unready.

- Different teams use conflicting Run-of-Show or cue versions, or the clock is unsynchronised.

- Arrival is outside its window without an approved early/late handling path.

- Holding area capacity, privacy, comfort, access or release control is inadequate.

- MC/speaker introduction, title or pronunciation is unverified or differs from the released sheet.

- Speech duration threatens protected acts, meal/transport/venue deadlines or guest-comfort tolerance.

- Photographer or stage instruction conflicts with ceremony, privacy, protocol or movement authority.

- Transition has predicted dead air and no acceptable bridge/receiving readiness.

- Delay cascade reaches a protected dependency without a hold/continue/recovery decision.

- Proposed shortening/removal/resequencing affects a non-negotiable or reserved authority.

- VIP/principal departure is approaching without vehicle, escort, route and farewell readiness.

## 60.3 Measures

| Dimension | Measures |
| --- | --- |
| Readiness | Gate completion, unresolved assumptions, rehearsal/test coverage and stale evidence |
| Cue control | Ready-at-GO rate, acknowledgement latency, missed/duplicate/late cues and unauthorised movement |
| Timing | Planned-versus-actual, variance duration, buffer use, time recovered and downstream cascade |
| Movement | Handoff/route completion, holding duration, queue/receiving flow and positioning exceptions |
| Continuity | Dead-air duration, bridge effectiveness, transition readiness and guest-visible disruption |
| Dignity / accuracy | Title/pronunciation/precedence incidents, forced participation, privacy breach and correction quality |
| Experience | Principal/host confidence, speaker/guest effort, comfort impact and departure readiness |

# 61. Module 8 relationships, geography, exclusions and gaps

## 61.1 Relationship to Modules 1–7

| Existing foundation | Module 8 contribution |
| --- | --- |
| White-glove / journey | Makes seamless movement, never-ask transitions and invisible choreography executable |
| Protocol / culture | Turns verified hierarchy, meaning and authority into contextual position, order, introduction and movement |
| VIP intelligence | Protects principal/VIP routes, visibility, privacy, comfort, arrival and departure without conflating status dimensions |
| Event Command | Adds ceremony-specific state, cue, clock, GO/HOLD, role views, variance and recovery logic |
| Vendor management | Coordinates MC, production, transport, photography, entertainment and other suppliers through accepted cues and dependencies |
| Learning governance | Captures actual timing, interventions and dignity outcomes as evidence—not automatic doctrine |

## 61.2 Global and Lagos treatment

Ceremony architecture, moment/cue contracts, clock control, role-specific views, transition design and recovery logic are globally reusable. Lagos/Nigeria context packs may contain verified institutional, royal/traditional, religious and family authority sources; local title/pronunciation records; venue/traffic/power/transport constraints; customary arrival/holding expectations; and destination-specific vendor/replacement times. Context packs never create universal Nigerian hierarchy or behaviour assumptions.

## 61.3 Exclusions applied

The Module 8 CEO Master Exercise was excluded. Its operational lessons—multiple authority systems, a late dignitary, a long speaker, photography pressure and international-guest dignity—are represented in contextual authority, arrival windows, delay cascades, programme classification, photographic protocol, briefing and recovery controls.

## 61.4 Explicit gaps and contradictions

- The module overlaps Modules 3, 4 and 6; one canonical precedence, cultural-authority, timeline and change model must prevent duplicate records and conflicting ownership.

- “Principal” assumes singularity in places; joint principals, couples, families, institutions and phase-specific principals need a formal model.

- No ceremony complexity/risk classification defines when Ceremony Architect, Stage Manager, Cue Caller, rehearsal or formal control artefacts are mandatory.

- Formal, traditional and social/personal authority are described but rules for moment-specific conflicts and approval escalation remain incomplete.

- The content relationship, release ownership and propagation between Master Timeline, Run of Show, Cue Sheets, Control Sheet and guest Programme need field-level schemas.

- GO/HOLD authority, emergency stop, cue cancellation, lost communications, false GO and recovery procedures require detailed policy and rehearsal.

- Clock source, synchronisation method, allowable drift and offline fallback are undefined.

- Arrival-window calculation, hold/continue conditions and latest-safe-time thresholds need event-specific calibration.

- Holding-area capacity, privacy, accessibility, welfare, safeguarding and security requirements need venue/specialist standards.

- Speaker content review, time warnings/cutoff, consent, political/religious sensitivity and public-embarrassment safeguards are not defined.

- MC improvisation boundaries and emergency/guest-safety announcement authority need explicit distinction.

- Stage/position decisions need structural, fire, accessibility, sightline and security acceptance outside general protocol authority.

- The “90-second photo rule” and “10-minute rule” are heuristics; they must not become universal hardcoded thresholds.

- Photography grouping, image consent, publication, minors, restricted guests and cross-border privacy/data rules need a dedicated media-governance module.

- Programme-item classification and live shortening/removal/resequence authority need approval and audit rules, especially for sacred, official or contracted acts.

- Bridge content rights, availability, cultural fit and fallback need owner and vendor integration.

- No rehearsal model defines tabletop, cue-to-cue, route, technical and full-dress evidence requirements.

- Ceremony metrics need baselines and human-factors testing so precision does not create rigidity or excessive alerting.

# 62. White-glove service doctrine and standards system

**OPERATING OBJECTIVE The CEO designs the standard; the event plan

makes it applicable; staff receive only what they must perform;

evidence proves whether it was met; the guest experiences care without

carrying the operation.**

| Knowledge type | Module 9 treatment |
| --- | --- |
| Doctrine | Observe → anticipate → act → disappear; one request → one resolution; dignity, discretion, ownership and recovery |
| Standard | A testable behaviour or condition with applicability, owner, evidence, checkpoint and exception authority |
| Heuristic | A useful starting target requiring calibration: the 5-second acknowledgement target (resolved, M14-D01), one-metre test and final ten minutes |
| Example language | Approved intent/pattern; adapt naturally without robotic scripts or unauthorised promises |
| Playbook | Sequenced response such as request escalation or LISTEN → ACKNOWLEDGE → OWN → SOLVE → FOLLOW UP |

## 62.1 Executable standard contract

Every hardcoded standard record contains: stable ID and version; short staff-facing title; domain and rationale; requirement and prohibited behaviour; applicability conditions; mandatory/advisory state; affected journey stages/zones/roles; preconditions/resources; owner/deputy; planning evidence; briefing/training content; verification method/checkpoint; pass/fail/not-applicable logic; severity; corrective action; exception authority; Lagos/global scope; source; approval and review history.

## 62.2 Event standards lifecycle

| State | Meaning | Required action |
| --- | --- | --- |
| Candidate | Potentially relevant from event facts/template | System explains applicability and requests confirmation |
| Applicable — unplanned | Required but no sufficient control/evidence | Assign owner, control, checkpoint and resources |
| Planned | Control and owner exist | Brief, rehearse/test and verify readiness |
| Ready | Pre-event evidence passed | Monitor live trigger/checkpoint |
| Met | Required event evidence accepted | Retain event result and context |
| Failed | Evidence shows breach | Correct/recover/escalate and recheck |
| Exception accepted | Authorised deviation with rationale/residual risk | Monitor conditions and expiry |
| Not applicable | Authorised reason recorded | Do not count as met; revisit if event facts change |
| Unknown | No current evidence | Visible risk; never silently treat as passed |

# 63. CEO and staff standards experience in the app

## 63.1 CEO Standards Library

- Search/browse by guest journey, zone, behaviour, service domain, role, event type or risk.

- Show the concise rule first, then rationale, good/poor examples, source, owner, version and related standards.

- Provide “What must I remember?” cards for doctrine and non-negotiable principles.

- Display whether a threshold is approved, provisional or event-configured so heuristics are never mistaken for universal law.

- Allow CEO-controlled approval, supersession and commentary without silently rewriting history.

## 63.2 Event Standards Plan

For each event, the app generates an applicability review. The CEO/Event Lead can see every applicable standard grouped by service moment, its owner, planned control, required evidence, verification time and current state. Filters expose unplanned, unknown, failed, excepted and readiness-blocking items. A standard cannot be marked met merely because a task was ticked.

## 63.3 Staff delivery views

| View | Content boundary |
| --- | --- |
| Role briefing card | Only applicable behaviours, zones, language, restrictions, escalation and guest-safe instructions |
| Supervisor checklist | Coverage, staff competence, checkpoints, defects, request ownership and coaching |
| Five-minute huddle | Purpose, principal/VIPs, changes, sensitivities, standards, restrictions, emergency/escalation and open-question prompt |
| Live staff view | Current zone, requests owned, promised updates, alerts and approved phrases/actions |
| Post-shift reflection | Observed gaps, recoveries and learning candidates; no unauthorised guest profiling |

# 64. Core guest-facing behaviour standards

## 64.1 Presence, courtesy and composure

- Remain alert and approachable without hovering, blocking, staring or creating visual clutter.

- Acknowledge an approaching/waiting guest within approximately 5 seconds (resolved canonical target, M14-D01) through an appropriate greeting, eye contact or nod; this is the starting default and event targets may still be recalibrated where venue/context evidence justifies it.

- Use upright, open, calm body language; no aggressive pointing, leaning, chewing/eating, visible frustration or social phone use in guest areas.

- Phones remain silent and operational only where necessary; no scrolling or divided attention when guest-facing.

- Be warm, confident and respectful—not artificial, pretentious, fearful or servile.

## 64.2 Service language

| Avoid | Approved intent |
| --- | --- |
| “I don’t know.” | “Let me confirm that for you.” |
| “That’s not my department.” | Own the request and connect it through a formally accepted handoff |
| “You can’t / that’s not allowed.” | Explain the relevant boundary calmly and offer an approved alternative |
| Long, flowery or servile speech | Short, precise, respectful and natural language |
| Argument or internal blame | Acknowledge impact, solve what can be solved and review facts privately later |

## 64.3 Discretion and personalisation

- Never discuss attendance, attire, conversations, relationships, movements or requests in guest areas or outside authorised purpose.

- Use names/titles only from verified, role-visible information and only where recognition feels natural.

- Use personal information to improve service, never to demonstrate how much Maison Doclar knows.

- Respect quiet/anonymous VIP preferences: minimal greeting, private route/seat, no photography and discreet departure where approved.

- Never embarrass a guest through correction, assistance, denial, dietary delivery, recovery or visible escalation.

# 65. Service zones, coverage and ownership

## 65.1 Zone plan

| Zone | Required capability |
| --- | --- |
| Entrance / arrival | Recognition, welcome, orientation, protocol/escort and exception routing |
| Reception / registration | Identity/response assistance, information, queues and handoff |
| Ballroom / ceremony | Ushering, seating, wayfinding, comfort and protected movement awareness |
| Dining | Table ownership, rhythm, water, dietary intelligence, clearing and escalation |
| VIP / principal | Dedicated discreet owner, privacy, comfort, route and command connection |
| Restrooms | Wayfinding, accessibility, attendant/inspection, supplies and hazard escalation |
| Departure | Transport status, belongings, escort/farewell, route, privacy and recovery |

Coverage is planned from journey demand, line of sight, route distance, crowd flow, staff capability, breaks, communications and backup. The one-metre test remains a walkthrough question—“can a guest readily find help?”—not a literal universal staffing radius.

## 65.2 Ownership and formal transfer

| State | Required evidence |
| --- | --- |
| Received | Guest acknowledged; request and immediate risk understood |
| Owned | One named person accepts responsibility and sets next action/update |
| Transfer proposed | Correct destination and minimum information identified |
| Transfer accepted | Receiving person explicitly accepts ownership and deadline |
| Resolved | Practical outcome delivered and affected operations updated |
| Followed up | Guest-safe confirmation or observation checks outcome where appropriate |
| Closed | Closure reason/evidence recorded; unresolved dissatisfaction is not disguised as success |

**SERVICE VACUUM ALERT No guest-facing issue is permitted to sit

between departments. “I told someone” is not a completed handoff.**

# 66. Greeting, escort, seating and social care

## 66.1 Interaction pattern

Greeting combines recognition, welcome and orientation. Escorting is preferred where route complexity, dignity, premium handling, mobility, attire or protocol warrants it. Staff match the guest’s pace, offer assistance without imposing it and never make a person announce a need publicly.

## 66.2 Accessibility and assistance boundary

- Plan accessible parking/drop-off, routes, ramps/lifts, toilets, seating, distances and trained assistance before the event.

- Ask respectfully before physical assistance unless immediate safety requires action; never assume incapacity from age or appearance.

- Follow the guest’s stated preference and approved accessibility plan; do not diagnose or record unnecessary medical detail.

- Escalate unsafe/inaccessible conditions to the qualified venue/safety/accessibility owner.

## 66.3 Social bridging

Staff may offer an introduction where context, guest preference and appropriate relationship information support it. Use name + relevance + connection, avoid “Do you know each other?”, create opportunity rather than obligation, and never label a guest as lonely from appearance alone.

# 67. Dining, dietary, restroom and comfort assurance

## 67.1 Dining rhythm and table ownership

- Define service waves, target ranges and dependencies rather than relying on an unsequenced menu.

- Assign table/area owners for water, replenishment, clearing, glassware, table condition and escalation.

- Balance attentiveness with non-intrusion; an empty glass may be a signal, not automatic permission to interrupt.

- Deliver VIP or special service discreetly without announcing status or requirement.

## 67.2 Dietary and allergy control

**SAFETY RULE Never guess whether food is safe. If an allergy or

ingredient status is uncertain, stop service to that guest, verify

through the designated food-safety/catering owner and offer a confirmed

alternative.**

The closed-loop chain is: verified requirement → approved alternative → kitchen/catering confirmation → labelled/controlled handoff → correct table/guest delivery → service confirmation → incident escalation if any. Staff see only the actionable instruction needed for delivery.

## 67.3 Restroom assurance

Each applicable restroom has a named owner, inspection cadence and trigger-based rechecks for cleanliness, tissue, soap, water, towels, waste, odour, floor condition, lighting and accessibility. Wet floors and other hazards escalate immediately; maintenance remains discreet.

## 67.4 Comfort intelligence

Teams monitor objective signals related to heat/humidity, crowd density, seating/standing duration, water access, sound, sightlines and fatigue. Observations prompt a respectful offer or environmental action, not an inferred medical or emotional diagnosis. Lagos heat, humidity, rainfall and heavy formal/traditional attire are context considerations requiring live evidence.

# 68. Service recovery, compensation and final touch

## 68.1 Recovery playbook

| Step | Observable completion |
| --- | --- |
| Listen | Guest is allowed to explain without interruption or public challenge |
| Acknowledge | Specific impact is recognised without blame or invented admission |
| Own | Named person accepts resolution/escalation and sets expectation |
| Solve | Authorised practical remedy is delivered; dependencies updated |
| Follow up | Outcome is checked respectfully; remaining issue escalated |
| Learn | Evidence and systemic cause enter post-event review, not an unauthorised permanent guest label |

## 68.2 Compensation boundary

The system recommends apology, replacement, priority treatment, upgrade, personal intervention, follow-up or other approved remedy based on impact and authority. Compensation is never automatic; financial/material remedies require delegated limits and audit. Guest confidence—not “buying forgiveness”—is the objective.

## 68.3 Final-touch controls

The departure plan verifies vehicle/driver, route, belongings, escort, farewell, protocol/security and privacy. “Protect the final ten minutes” is an experience-design principle; the event configures the actual protected window from journey and transport facts.

## 68.4 Lost property

Found items enter a secure chain of custody with minimal access, timestamp/location, finder, custodian, owner-verification method, logged handover and approved retention/disposal. Sensitive, dangerous or high-value items follow specialist escalation rather than ordinary storage.

# 69. Training, briefing and standards assurance

## 69.1 Competency model

Training targets demonstrated behaviour—not slogan acknowledgement. Event qualification may require practice of greeting, escorting, seating, dietary escalation, restricted-area requests, VIP reception, protocol correction, upset guests, service recovery and emergency escalation. Assessment records demonstrated, needs coaching or not qualified, with reassessment and expiry.

## 69.2 Readiness gate

| Gate | Pass condition |
| --- | --- |
| Applicability | Every candidate standard reviewed; applicable/not-applicable rationale approved |
| Plan | Every mandatory standard has control, owner/deputy, resources, checkpoint, evidence and contingency |
| Coverage | Every guest-facing stage/zone has capable staff, supervisor, breaks and backup; service vacuums addressed |
| People | Roster checked in; uniforms/identification appropriate; briefing acknowledged; required competencies demonstrated |
| Guest intelligence | Only minimum current role-specific names/titles, needs, dietary instructions, VIP/privacy and restrictions released |
| Requests / escalation | One-case ownership, accepted-transfer, update, specialist and executive paths tested |
| Environment | Wayfinding, seating, dining, water, restrooms, comfort, accessibility and departure controls inspected |
| Recovery | Frontline remedies, compensation limits, complaint/privacy handling and follow-up authority understood |
| Assurance | Independent verification assigned where required; mandatory failures/exceptions visibly accepted before opening |

## 69.3 Live and post-event assurance

Live checkpoints capture evidence with the lightest safe interaction: inspection, timestamp, count/duration, handoff acknowledgement, service outcome or guest-safe follow-up. After the event, standards performance is analysed by context, false/missed alerts, corrective action and guest effort. Outcomes may propose revised standards but cannot autonomously change them.

# 70. Module 9 intelligence, relationships and gaps

## 70.1 Intelligence and alerts

- Applicable mandatory standard is unplanned, ownerless, unknown, failed or supported only by a generic tick.

- Service zone/stage lacks coverage, capable staff, supervisor, break cover or reachable backup.

- Staff member is assigned without current briefing, acknowledgement or required demonstrated competency.

- Waiting/approaching guest is not acknowledged within the configured target, or service-vacuum signals recur.

- Guest request has no owner, rejected transfer, missed promised update or closure without resolution evidence.

- Staff language, body language, phone use, visible dispute or internal blame risks embarrassment or loss of confidence.

- Name/title is unverified, private information is over-shared or personalisation reveals unnecessary knowledge.

- Dietary/allergy chain lacks verification, correct handoff or food-safety owner.

- Restroom or comfort checkpoint is stale, failed or indicates an urgent hazard.

- Service recovery lacks acknowledgement, owner, authorised solution or follow-up.

- Compensation/recovery exceeds authority or is being used automatically without impact assessment.

- VIP anonymity, photography, private route or discreet-dining preference is at risk.

- Departure/final-touch control is incomplete as guest movement approaches.

- Lost property lacks secure custody, owner verification or logged handover.

## 70.2 Relationship to Modules 1–8

| Foundation | Module 9 contribution |
| --- | --- |
| White-glove philosophy | Converts anticipation, discretion and ownership into observable behaviours and event assurance |
| Guest journey / friction | Maps service coverage, standards and request ownership to every stage/touchpoint/transition |
| Protocol / culture | Uses verified address, respectful correction and cultural humility without letting staff improvise authority |
| VIP intelligence | Operationalises recognition, anonymity, preferences and continuity with minimum disclosure |
| Event Command / ceremony | Routes live requests, zones, cues, recovery and departure through one command structure |
| Vendor management | Applies Maison Doclar standards, training, evidence and scoring to vendor guest-facing staff |

## 70.3 Global and Lagos treatment

Courtesy, discretion, ownership, non-embarrassment, request continuity, verification and recovery are globally reusable. Greeting forms, titles, assistance etiquette, language, dining practice, restroom operations, climate/comfort controls, staffing norms and response targets require event and local context. Lagos packs may surface heat/humidity/rain, traffic/departure, power/water and venue/service-market risks, but live evidence and verified event facts govern.

## 70.4 Exclusions applied

The Module 9 CEO Master Exercise was excluded. Its operational lessons—triage, delegation, guest/VIP criticality, CEO intervention and hiding operational complexity—are represented in standards severity, ownership, escalation, recovery and executive-reserved decisions. Role-play remains retained as a staff competency method rather than a CEO exercise.

## 70.5 Explicit gaps and contradictions

- The source offers many principles and examples but not a formal standards catalogue with IDs, mandatory levels, applicability, evidence, owners or revision control.

- (Acknowledgement target resolved, M14-D01) The 5-second acknowledgement target is now canonical. The one-metre test and final-ten-minute rules remain useful but unvalidated heuristics; event-specific targets and measurement methods are still required for those two.

- No staffing-demand model defines zone coverage, supervisor ratios, breaks, shift length, capability mix or backup by attendance/flow/venue.

- Observable service signals must be distinguished from inferred disability, medical condition, emotion, loneliness, status or intent to avoid unsafe profiling.

- Accessibility standards, reasonable adjustments, physical assistance, safeguarding and emergency procedures require qualified and jurisdiction-specific ownership.

- Dietary/allergy collection, verification, cross-contact, labelling, kitchen control and incident response require food-safety expertise and applicable law.

- Children’s service requires safeguarding, guardian authority, photography, lost-child, food/allergy and access-control policies—not a generic hospitality checklist.

- Restroom inspection intervals, hygiene standards, accessible facilities, waste and wet-floor/hazard response need venue and regulatory calibration.

- Temperature, humidity, noise, standing, water and comfort thresholds need event/venue evidence and specialist input where health/safety is implicated.

- Service language examples require natural-language, local-language and cultural variants; scripts should not create robotic or misleading promises.

- Guest-request priority, response/update/resolution targets and specialist routing are undefined by severity and zone.

- Frontline remedy and compensation authority, cost limits, admissions/liability language and client/vendor recovery need commercial/legal policy.

- Service recovery follow-up must avoid pressuring guests to report satisfaction or turning complaints into permanent negative profiles.

- Lost-property retention, disposal, data access, identity verification, sensitive items and law-enforcement handoff need jurisdiction-specific policy.

- Staff observation, performance assessment, vendor-worker data, fairness, coaching, disciplinary boundaries and retention require HR/privacy governance.

- No standard-testing method yet proves that an item is understandable, observable, non-duplicative, useful, resistant to box-ticking and safe under live workload.

- The CEO quick-reference, event standards plan, staff briefing and assurance dashboard need user testing at desk, mobile and live-event pace.

- Standards may conflict: speed versus accuracy, visibility versus discretion, recognition versus anonymity, ownership versus specialist authority and anticipation versus privacy need explicit precedence rules.

# 71. Canonical reconciliation with Module 6

**CANONICAL TREATMENT Module 10 does not introduce a second Event

Command system. It reinforces Module 6 and adds an explicit

intelligence pipeline, multi-lens operational picture, configurable

look-ahead, CEO information filter and evaluation controls.**

| Module 10 concept | Canonical specification treatment |
| --- | --- |
| Event Control Centre | Same Command Centre entity and continuity requirements |
| Single source of truth | Controlled state store generating current role views; not one spreadsheet/chat/document |
| Event Board / dashboard | Role-scoped presentation of the operational picture |
| RAG / escalation / closed loop | Existing Module 6 models refined; five-level escalation adopted |
| Incident sequence | Module 6 recovery sequence extended with assess and formal record states |
| 15/60-minute look-ahead | Configurable horizons plus latest-safe-action reasoning |
| Human command + AI intelligence | New signal → interpretation → recommendation → decision → action → verification contract |

Where the earlier consolidated role table refers to CEO Level-4 escalation, Module 10 supersedes that label: CEO/Executive is Level 5. Event Director is Level 4. Qualified safety, security, medical, fire, venue or public authorities may intervene immediately and are never delayed by ladder position.

# 72. Operational picture and command lenses

## 72.1 Operational picture contract

A live snapshot answers: where are we, what is happening, what is next, who is involved, are receiving stages ready, what could stop the next protected outcome, what actions/decisions are open and how fresh/trustworthy is the evidence. Every field retains domain owner, source, event time, update time, freshness and confidence/verification state.

## 72.2 Multi-lens status

| Lens | Primary question |
| --- | --- |
| CEO / executive | Does this protect client intent, people, guest experience and brand—and is my decision required? |
| Event Director | Is the whole event controlled across now, next and recovery? |
| Guest Experience | What are guests experiencing, and where is effort/dignity/comfort at risk? |
| Protocol / culture | Are verified authority, precedence, meaning and respectful execution protected? |
| Operations / vendors | Can venue, infrastructure, suppliers and logistics deliver? |
| Production / ceremony | Can current and next cues/movements execute correctly? |
| Security / medical / safety | Are people protected, and is specialist intervention required? |
| Transport | Can arrivals, routes, vehicles and departures move on time? |

## 72.3 State integrity

- Green/Amber/Red always includes objective criterion, evidence, owner and expiry; Unknown and stale are visible states.

- Conflicting reports remain visible until reconciled; the system records both sources and the resolution.

- A dashboard summary links to evidence and cannot overwrite domain records.

- Role views redact information but may not falsely imply that hidden/unknown risk is Green.

- Every material correction and released snapshot is auditable.

# 73. Look-ahead and predictive operations

## 73.1 Horizons

| Horizon | Use |
| --- | --- |
| NOW | Current protected activity, active incident, variance and immediate ownership |
| NEXT | Configurable near horizon—often 5–15 minutes—for prerequisites and receiving readiness |
| LATER | Beyond immediate execution; preparation and resource conflicts |
| Strategic look-ahead | Often 30–60 minutes for movement, weather, service, vendor and venue dependencies |
| Latest safe action | Calculated deadline after which prevention becomes recovery or an option disappears |

Fifteen and sixty minutes are useful defaults, not universal rules. A VIP route clearance, rain move, meal service, power changeover or emergency response may require a different horizon. Each look-ahead item works backward from the outcome through prerequisite durations, uncertainty and buffers.

## 73.2 Conflict and cascade intelligence

The engine compares time windows, routes, spaces, people, vehicles, equipment, authority, capacities and dependencies. A conflict is raised only when requirements overlap within uncertainty/tolerance, with time-to-impact, affected promises, confidence and prevention choices. It must show alternative explanations rather than narrating coincidence as causation.

# 74. Signal-to-action intelligence model

## 74.1 Command loop

| Stage | System obligation | Human obligation |
| --- | --- | --- |
| Observe | Ingest timestamped sourced signals; flag stale/conflicting/missing data | Provide truthful updates and validate material observations |
| Interpret | Apply approved rules/models; show assumptions, alternatives and confidence | Review context, protocol/culture/relationships and specialist facts |
| Decide | Present options, consequence, urgency, authority and expiry | Named authority chooses, rejects or requests more evidence |
| Act | Route released instruction to the responsible role and dependencies | Recipient accepts and performs within authority |
| Verify | Seek completion and receiving/outcome evidence; reopen on failure | Confirm real-world result and remaining exposure |

(Module 16) Module 16’s “Observe -> Interpret -> Decide -> Act -> Verify -> Observe again” event-day control loop is this same command loop; the cycle-back to Observe is implicit here and is worth stating explicitly as the operating rhythm during any live critical period. No new model.

## 74.2 Intelligence states

| State | Meaning |
| --- | --- |
| Raw signal | A report/measurement/observation not yet interpreted |
| Validated fact | Source and evidence meet the domain’s verification requirement |
| Assertion | Reasoned interpretation with supporting/contradicting evidence |
| Forecast | Probabilistic future state with horizon, range and assumptions |
| Recommendation | Proposed action with authority, alternatives and expiry |
| Decision | Authorised choice with rationale and consequences |
| Verified outcome | Evidence of real-world completion/effect, including residual risk |

**TRUTH RULE The system must never collapse “reported”, “inferred”,

“predicted”, “recommended”, “decided” and “done” into one status.**

# 75. CEO intelligence filter and dashboard

## 75.1 CEO situation report

| Field | Executive content |
| --- | --- |
| Status | Current event position and overall/lens state with freshness |
| Issue | One factual material variance or threat—not a stream of backstage detail |
| Impact | Affected people, promise, safety, ceremony, reputation, time and confidence |
| Action | Owner, containment/prevention/recovery underway and next update |
| Decision | Exact question/options/deadline requiring CEO authority—or “none” |
| Residual exposure | What remains uncertain or could still worsen |

The CEO view filters routine detail but never filters bad news, uncertainty, accepted risk, material dissent or specialist stop authority. Drill-down is permission-scoped and audited.

## 75.2 Dashboard domains

- Event overview and live timeline

- VIP/principal movement with restricted detail

- Guest/service standards issues

- Vendor/dependency readiness

- Protocol/culture and ceremony

- Transport and weather

- Production/power/technical state

- Security/medical/safety summary with specialist-controlled detail

- Incidents and recoveries

- Risks/leading indicators

- Pending decisions and closed-loop actions

- Contacts and offline continuity status

# 76. Communication, priority and escalation

## 76.1 Message contract

Each operational message is classified as information, instruction, decision or escalation; uses role identifiers; states WHO, WHERE, WHAT, WHEN and ACTION; carries routine/priority/critical handling; and records acknowledgement, acceptance, completion and sensitivity. Radio brevity must not remove essential safety or identity clarity.

## 76.2 Canonical five-level ladder

| Level | Normal owner | Boundary |
| --- | --- | --- |
| 1 | Frontline staff | Approved routine resolution; escalate inability, risk or exception |
| 2 | Supervisor | Zone/team coordination and bounded remedy |
| 3 | Department/Function Lead | Cross-team/domain decision within delegated scope |
| 4 | Event Director | Whole-event operational trade-off, contingency and material incident |
| 5 | CEO / Executive | Client/principal/reputation/strategy/material exception or reserved executive decision |

The ladder does not delay immediate containment or qualified specialist action. Communication priority is separate from escalation level, and RAG is separate from both.

## 76.3 Consequence prioritisation

Life and safety always outrank schedule and aesthetics. Beyond that, the system considers urgency, severity, affected population, vulnerability, irreversibility, dignity/protocol, recoverability, cascade, confidence and legal/specialist duties. Principal/VIP status does not automatically outrank another person’s safety or serious need.

# 77. Risk, incident, contingency and recovery intelligence

## 77.1 Separate objects

| Object | Definition | Typical action |
| --- | --- | --- |
| Risk | Credible possible future harm | Monitor indicator, prevent, prepare response |
| Issue | Current variance requiring ownership | Correct/escalate before it becomes an incident |
| Incident | Verified event entering formal response | Identify, contain, assess, act, communicate, recover, record |
| Backup | Replacement resource | Test availability, compatibility and activation time |
| Contingency | Alternative operating plan | Define trigger, authority, resources, communications and reset |

## 77.2 Domain intelligence boundaries

- Weather: use authoritative/local source, event location/horizon, uncertainty and action thresholds; rain test covers guests, principal/VIPs, ceremony, equipment, vehicles and accessibility.

- Power: track load, source, fuel/runtime, technical owner, test/changeover evidence and failure consequence; qualified electrical/production authority governs action.

- Security: integrate movement/access/route signals while Security Lead controls tactics, restricted detail and incident authority.

- Medical: safety overrides programme; qualified responders and emergency services govern assessment and treatment.

- Crowd/flow: use capacity/queue/throughput observations and qualified crowd-safety limits; do not infer mood or intent from movement alone.

## 77.3 Recovery and visibility

Maison Doclar aims to absorb disruption before it becomes guest experience, but invisibility never justifies concealing safety-relevant facts, misleading the client, suppressing mandatory reporting or preventing affected people from making informed decisions.

# 78. Intelligence assurance, failure modes and readiness

## 78.1 Intelligence quality gate

| Gate | Pass condition |
| --- | --- |
| Source | Named authorised source and acquisition method |
| Time / freshness | Event time and update time known; domain-specific expiry visible |
| Verification | Reported/observed/confirmed state and corroboration requirement met |
| Context | Location, domain, affected entity and governing event version linked |
| Uncertainty | Confidence/range, assumptions and alternative explanations stated |
| Materiality | Consequence and time-to-impact justify attention |
| Authority | Reviewer, decision owner and specialist reservation identified |
| Actionability | Recommended owner/action/deadline/alternatives and expected outcome clear |
| Closure | Decision, action, verification and residual exposure recorded |
| Evaluation | Prediction/alert usefulness and false/missed outcome review enabled |

## 78.2 Alerts

- Operational picture contains stale/Unknown material lens or conflicting unreconciled reports.

- Protected NOW/NEXT activity lacks owner, prerequisites, receiving readiness or latest-safe-action margin.

- Forecast conflict/cascade is approaching while prevention decision remains unowned.

- Dashboard presents an inference/prediction as confirmed fact or hides its source/uncertainty.

- RAG state lacks objective evidence, or Red/Amber is being used inconsistently across domains.

- Critical instruction is unacknowledged, accepted but incomplete, or completion lacks outcome verification.

- Issue is routed to CEO without a precise executive decision—or withheld despite reserved executive impact.

- Radio traffic broadcasts restricted detail, panic, personal names unnecessarily or ambiguous instruction.

- Risk indicator crosses threshold without preventive action; backup exists but contingency/activation authority does not.

- Incident lacks commander, containment, specialist authority, next update or evidence record.

- AI recommendation is stale, outside authority, repeatedly ignored, harmful, duplicate or producing alert fatigue.

- Digital/communications failure has no controlled offline picture, backup clock/channel or reconciliation owner.

## 78.3 Measures and evaluation

| Dimension | Measures |
| --- | --- |
| Visibility | Picture completeness/freshness, Unknown duration and conflict-reconciliation time |
| Anticipation | Detection lead time, latest-safe-action margin and prevented cascades |
| Prediction | Calibration, error/range, false positives/negatives and missed material events |
| Decision | Correct authority, decision latency, option quality and expired recommendations |
| Execution | Acknowledgement, acceptance, completion and verified-outcome rates |
| Communication | Message clarity, priority fit, restricted-data incidents and channel continuity |
| Recovery | Containment/recovery time, continuity, residual exposure and recurrence |
| Human factors | Alert volume, deduplication, ignored alerts, workload, trust and automation bias |
| Executive value | CEO interruptions avoided, material decisions surfaced and withheld-bad-news incidents |

# 79. Module 10 relationships, geography, exclusions and gaps

## 79.1 Relationship to Modules 1–9

Module 10 consumes event/journey, protocol, culture, VIP, vendor, ceremony and service states and turns their time-sensitive interactions into a shared operational picture, forecasts, conflicts, recommendations and verified actions. It does not own the substantive specialist truth in those domains; their authorised owners remain the source.

## 79.2 Global and Lagos treatment

Command authority, source-of-truth discipline, signal provenance, look-ahead, closed-loop execution, incident states and intelligence assurance are globally reusable. Lagos/Nigeria context packs may encode verified weather exposure, traffic/route variability, grid/generator dependencies, connectivity, venue access, public/emergency contacts, supplier response times and local regulatory/specialist requirements. They must be maintained facts and ranges—not assumptions that every Lagos event will fail in the same way.

## 79.3 Exclusions applied

The Module 10 CEO Master Exercise was excluded. Its lessons—RAG triage, ownership, near-term action, guest visibility, executive filtering and Event Director authority—are fully represented in the canonical command and intelligence controls.

## 79.4 Explicit gaps and contradictions

- Module 10 repeats much of Module 6; existing section labels, schemas and code must be migrated to one canonical vocabulary rather than implemented twice.

- The prior consolidated role table labels CEO as Level 4 while Module 10 defines CEO as Level 5; Module 10 supersedes the number and migration is required.

- No event complexity model defines when physical/virtual Control Centre, Operational Picture Controller, Intelligence Analyst, Radio Controller or each dashboard domain is mandatory.

- The operational source-of-truth state model, write authority, correction/reconciliation workflow and snapshot/version semantics need field-level design.

- NOW/NEXT/LATER and 15/60-minute horizons need event templates, latest-safe-action logic and uncertainty propagation.

- No live-data integration contracts exist for weather, traffic, transport, guest check-in, power, production, radios, vendors or venue systems.

- Signal provenance, corroboration, confidence, stale thresholds and conflict resolution require domain-specific policy.

- Forecast/conflict models require calibration data; no live events exist yet, so predictions must initially be rules/ranges and clearly provisional.

- The priority pyramid can mislead if interpreted rigidly: safety is absolute, but other issues require consequence, vulnerability and legal/specialist context.

- RAG state, radio priority, incident severity, escalation level and guest-impact severity are distinct taxonomies and need explicit mappings without collapse.

- Radio licensing, equipment, channel plans, recording, privacy, security, call signs, failure and backup procedures require specialist/local policy.

- Weather source, alert thresholds, lightning/wind/heat/rain criteria and decision authority need qualified event/venue/safety input.

- Power load, fuel/runtime, switching, earthing/electrical safety and generator operation require competent technical standards.

- Crowd flow test examples (100/200/300 in five minutes) are scenarios, not safe capacities; qualified calculations and venue limits govern.

- Medical, security, fire, safeguarding, evacuation and public-emergency command cannot be generated by general AI or event staff.

- CEO filtering needs a rule against optimistic summarisation, suppression of dissent and “no guest impact” claims without evidence.

- Dashboard access, sensitive movement data, device/session loss, screenshots/exports, offline caches and retention need security/privacy architecture.

- Alert deduplication, correlation, escalation, snooze/suppression, human workload and false/missed-alert evaluation are not yet designed.

- No simulation or shadow-mode validation plan exists for testing recommendations before the AI influences live command.

- Post-event evaluation needs ground-truth reconciliation, reviewer ownership and a controlled path from evidence to model/rule changes.

# 80. Module 11 — canonical knowledge extraction

Source: “Event Risk, Crisis & Service Recovery.” Status: approved foundation, subject to the CEO decisions listed in Section 11.10. This module deepens rather than replaces Module 10’s Section 77 objects (Risk, Issue, Incident, Backup, Contingency): it supplies the scoring method, the incident-versus-crisis test, and the recovery discipline that those objects assume but do not themselves define.

**DEFINITION Luxury is tested not when everything goes right, but when

something goes wrong and the guest never feels the difference.**

## 80.1 Risk philosophy

Four governing verbs: Anticipate (identify before occurrence), Prepare (create a response), Contain (stop it spreading), Recover (return to normal). The goal is not eliminating risk — that is impossible — but preventing foreseeable risk from becoming visible failure.

## 80.2 Incident versus crisis

An incident is a problem containable within normal operational authority (missing table number, late supplier, microphone failure). A crisis materially threatens safety, the principal/VIP, event continuity, reputation, security, legal exposure, public confidence or the client relationship. Not every incident is a crisis, but every crisis begins as something that must be recognised correctly — this is the module’s central operating risk.

## 80.3 Crisis escalation test

Five questions applied at the moment of recognition: (1) Is anyone in danger? (2) Is the principal/VIP materially affected? (3) Can the event continue normally? (4) Could this become publicly/reputationally damaging? (5) Does this exceed the Event Director’s authority? A significant “yes” to any question escalates. This test is the practical trigger for the 76.2 five-level ladder and the 11.57 crisis scale below — it decides when to move up the ladder, not what the ladder itself is.

## 80.4 Risk categories

Guest, VIP, Venue, Production, Power, Weather, Transport, Catering, Security, Protocol, Reputation, Vendors, Technology, Programme. Every major event decision in any category should be tested with: “what could interrupt the intended experience?”

# 81. Risk identification, scoring and the register

## 81.1 Risk Walk and the four-part question

Risk identification is physical, not documentary: a Risk Walk covers entrance, parking, VIP route, guest route, stage, dining, restrooms, backstage, kitchen, power, emergency exits, security points and departure. For every major activity: what can go wrong? How likely is it? How serious would it be? What will we do about it?

## 81.2 Risk scoring

Probability (1 rare – 5 almost certain) x Impact (1 negligible – 5 severe) = Risk score. Scoring exists to make resource allocation defensible: resources follow consequence, not anxiety, so a low-impact risk (wrong napkin colour) never draws the same attention as a high-impact one (VIP transport failure, power failure) regardless of how visible or emotionally salient it feels in the moment.

## 81.3 The risk register and ownership

Minimum register fields: risk, probability, impact, score, owner, prevention, contingency. A risk without a named owner is a concern, not a managed risk — “the team knows” is not an answer to “what are we doing about this.” Prevention (stop it happening) and contingency (what we do if it happens anyway) are distinct and both required for every material risk.

## 81.4 The decision trigger

A contingency is only real if it specifies IF (a defined condition), THEN (a defined action) and BY (a specific decision time). “We’ll monitor it” is not a contingency; “if the equipment is not restored by 7:15 PM, we activate the backup system” is. The decision trigger is the mechanism that converts a prevention/contingency pair into something a system — human or AI-assisted — can actually watch for and alert on.

# 82. Early warning, live response and safety override

## 82.1 Warning horizons

Command teams work three shrinking horizons: the 30-minute warning (“what could become a problem in the next 30 minutes?”), the 10-minute warning (shorter horizon, more specific response), and, on actual incident, the 60-second response — WHAT? WHERE? WHO? IMPACT? ACTION? — which exists to prevent the first minute of an incident being spent in debate.

Answering “what could become a problem” means reading signals before they become incidents — obvious ones (a VIP arrives, rain begins, power fails) and subtler ones a queue forming, staff beginning to look uncertain, a host disappearing from an expected location, photographers repositioning unprompted, catering staff moving unusually quickly. A queue or an unexpectedly empty space is diagnostic information in either direction, not merely an occupancy count — both are interpreted against what should be happening at that moment, not read at face value.

## 82.2 Stabilise first, diagnose second

The first rule of crisis response: restore function before investigating cause. Restore communication before diagnosing the microphone; protect the VIP before investigating the vehicle. Root-cause work (Section 87) happens after stabilisation, never instead of it or concurrent with it at the expense of it.

## 82.3 Safety overrides schedule

Fire, medical emergency, dangerous crowding, structural concern or serious weather make the programme secondary without exception. This is a non-negotiable override on the RAG/priority model in Section 40 and the consequence-prioritisation rule in 76.3: life and safety outrank schedule and aesthetics, and this module supplies the trigger list that activates that override in practice.

# 83. Domain-specific incident protocols

## 83.1 Medical

Fixed chain: staff identifies issue -> trained responder notified -> area cleared -> assistance provided -> Event Director informed -> security supports movement -> emergency services contacted if required -> incident recorded. Crowding around a medical incident is itself a failure mode: create space, limit observers, direct guests away, protect dignity. White-glove discretion applies inside emergencies, not only outside them.

## 83.2 Security and VIP movement

Security incidents activate the qualified Security Lead; untrained staff are never encouraged to intervene directly (consistent with the Module 10 domain-intelligence boundary at 77.2). Sensitive-guest information is shared need-to-know only — movements, private locations, security arrangements and vehicle details are not broadcast. A VIP movement crisis (e.g. a departure vehicle failing minutes before a scheduled window) is resolved by activating Transport, Protocol, Security and Guest Experience together and establishing a controlled departure window; it is never improvised publicly, and the VIP’s own experience should register nothing unusual.

## 83.3 Weather

A weather decision point is set before the event, not discovered during it: GREEN (manageable, continue), AMBER (increasing discomfort, prepare transition), RED (safety concern, activate contingency). Exact thresholds are venue- and professional-advice-specific and are not fixed by this module (see open decision M11-D06).

## 83.4 Power and critical loads

Power failure planning requires a primary source, backup, technical lead, changeover procedure, fuel monitoring and a pre-agreed critical load priority (emergency lighting, security, communications, essential production, critical refrigeration, VIP systems). The operative question is not “do we have a generator” but “how quickly can we restore critical operations.”

## 83.5 Catering and vendor failure

Catering failures (delay, wrong dietary meal, shortage, cold food, missing VIP meal, bottleneck) must never surface to the guest as attributable blame (“the kitchen messed up”). Vendor failure generally follows the same principle: the guest experiences Maison Doclar, not the vendor’s failure. Critical-vendor contingency requires a named backup resource, replacement equipment or alternative personnel, an escalation contact and a decision deadline — “we’ll fix it” is followed by “by when?” and “what is Plan B if you don’t?”

# 84. Service recovery and guest complaints

## 84.1 The recovery sequence

LISTEN -> ACKNOWLEDGE -> OWN -> SOLVE -> FOLLOW UP is the Maison Doclar recovery standard, extending the Module 9 recovery playbook (68.1) with an explicit closing step: recovery is not complete until someone verifies the guest is now comfortable, not merely that the operational fix was applied.

## 84.2 Complaint types and the angry guest

Three complaint types, all requiring professional treatment: valid (genuine failure occurred), misunderstood (event is correct, guest lacks information), unreasonable (request conflicts with operational/safety/protocol requirements). An angry guest is met with “I understand your concern, let me take care of this for you,” not emotional response or public correction; a guest who is factually wrong is redirected with dignity preserved and the correct boundary held (“that area is reserved for the official delegation, but let me arrange a more comfortable alternative”).

## 84.3 The recovery paradox and its limit

Exceptionally handled recovery can create stronger loyalty than an uneventful interaction, because the guest sees how seriously their experience is taken. This must never become licence to manufacture problems in order to demonstrate recovery — prevention remains the primary objective; recovery is the fallback, not the strategy.

# 85. Reputational risk and crisis communication

## 85.1 Reputational exposure

An event can become public within minutes. Exposure sources include guest disputes, inappropriate staff behaviour, security incidents, protocol mistakes, poor service, insensitive cultural handling, and photographs posted without permission. The operating test is “could this become a story?” — and, where sensitive guests (dignitaries, traditional rulers, private families, celebrities, international guests) are present, a defined photography/social-media policy governs before the event, not reactively. The photographer is treated as part of the event operation, not merely “the person taking pictures,” given their capacity to block entrances, interrupt ceremonies, crowd VIPs or enter restricted spaces.

## 85.2 The one-voice principle

For significant incidents: one authorised internal operational truth, one authorised external channel. This extends the Module 10 message contract (76.1) to crisis conditions specifically — never speculate, never invent information, never assign blame publicly, never allow multiple uncoordinated explanations to circulate.

## 85.3 Client communication

The client hears serious problems from Maison Doclar first — never from a guest, WhatsApp, Instagram or a vendor — but not every minor issue reaches them; relevance plus impact plus solution governs what is escalated. The client briefing formula: “There is an issue with X. It affects Y. We have activated Z. At present, the guest experience remains unaffected. We will update you by [time].” This communicates awareness, control, action and confidence in one structure.

## 85.4 Don’t transfer anxiety

Team, client and guest anxiety are not resolved by pretending nothing happened; they are resolved by demonstrating understanding, active management and a plan. This is a leadership behaviour requirement as much as a communication template.

# 86. Crisis command and the escalation scale

## 86.1 CEO crisis leadership

Crisis behaviour is observed and imitated: a CEO who panics, shouts, blames or reverses decisions destabilises the team; a CEO who listens, prioritises, decides, communicates and delegates stabilises it. Emotional control is treated as an operational asset, not a personality trait. On notification of a serious event, the CEO’s five questions are: is anyone unsafe; what is the immediate impact; who owns the response; what decision is required; when is the next update — then the CEO stops and lets the system work, using an update clock (e.g. “update me in five minutes, then ten”) to prevent constant interruption.

## 86.2 The Maison Doclar crisis scale

Resolved (M11-D03). The 76.2 five-level escalation ladder is the one canonical mechanism for who owns a response. This crisis scale is not a second model — it is the severity label applied to crisis-track items on that same ladder, and the table below is the single mapping rule between the two: a rule engine should evaluate 76.2 for ownership and use this table only to select the classification word shown to a human (Minor/Operational/Significant/Major/Critical). Crisis-track items skip Ladder Level 3 deliberately (a crisis is, by definition, escalated past department/function-lead scope), and Level 5 adds the external-authority detail (safety, security, legal, regulatory) that 76.2 itself does not spell out but does not contradict.

| Level | Classification * | *Owner (76.2 ladder level)** |
| --- | --- | --- |
| 1 | Minor | Frontline team (Ladder Level 1) |
| 2 | Operational | Supervisor (Ladder Level 2) |
| 3 | Significant | Event Director (Ladder Level 4 — Level 3 is deliberately skipped for crisis-track items) |
| 4 | Major | CEO/executive (Ladder Level 5) |
| 5 | Critical | Ladder Level 5 plus external authorities (safety, security, legal, regulatory) |

## 86.3 The Crisis Command Centre and log

During a significant incident, the Event Control Centre (38.1) becomes the Crisis Command Centre: it controls information, decision-making, communication, documentation and coordination, and access is deliberately restricted — not every person may enter. A crisis log (time, event, decision, owner, status) is maintained contemporaneously and prevents the confusion that comes from relying on memory after the fact. The crisis command principle: when pressure rises, the number of people making decisions goes down, not up — a crisis is not the moment to create consensus process.

# 87. Post-incident learning

## 87.1 After-action review

Never conducted while the event is still running: stabilise, then document, then analyse, then improve, in that order. Standard questions: what worked, what failed, what nearly failed, what did we miss, what did we learn, what should change — with “what almost became a crisis” treated as the single most valuable question, since near misses are free intelligence about a failure mode that has not yet cost anything.

## 87.2 Root cause and the five whys

Analysis does not stop at the first cause offered (“the driver was late”); it repeats “why” until it reaches a system-level cause (a route closure with no prepared alternative reveals a transport contingency-planning gap, not a driver failure). The objective is recurrence prevention, not identifying someone to blame — consistent with the AI-boundary rule in 8.1 against recording individual blame in risk, incident or after-action data.

## 87.3 The service recovery ledger

For every meaningful guest issue: guest, issue, time, department, response, resolution, follow-up, root cause, preventive action. This ledger is the accumulating evidence base that lets recovery performance, not just individual incidents, be measured and improved over time.

## 87.4 The Maison Doclar recovery loop

DETECT -> ASSESS -> CONTAIN -> ESCALATE -> DECIDE -> ACT -> VERIFY -> RECOVER -> RECORD -> IMPROVE. This is the module’s complete lifecycle and the frame every domain protocol in Section 83 is an instance of.

**STANDARD The objective is not “nothing went wrong” — that is

unrealistic. The objective is “nothing that went wrong was allowed to

become the guest’s problem.”**

# 88. Decisions supported by Module 11

Module 11 supplies: the incident-versus-crisis distinction and its five-question test; probability x impact risk scoring and the prevention/contingency/decision-trigger discipline; domain-specific protocols for medical, security/VIP, weather, power, catering and vendor failure; the LISTEN-ACKNOWLEDGE-OWN-SOLVE-FOLLOW UP recovery sequence and complaint-type taxonomy; the one-voice and client-briefing communication disciplines; the crisis command principle and the reconciled five-level crisis scale; and the after-action/root-cause/near- miss learning cycle.

## 88.1 Decisions outside Module 11 authority

Exact weather/power/crowd-safety thresholds, qualified medical/security/ fire/evacuation command, legal and regulatory reporting obligations, insurance and liability positioning, and the specific external authorities engaged at Crisis Scale Level 5 all require specialist, legal or regulatory authority beyond this module and remain open decisions (Section 11.10).

# 89. Module 11 relationships, exclusions and gaps

## 89.1 Relationship to Modules 1–10

Module 11 does not introduce new Risk/Issue/Incident/Backup/Contingency objects — it supplies the scoring method, ownership discipline and crisis-classification test that Module 10’s Section 77 objects and Section 78 quality gate assume. It reconciles with, rather than replaces, the 76.2 five-level escalation ladder (Section 86.2), extends the Module 9 service-recovery playbook (68.1) with an explicit follow-up-verification close, extends the Module 10 message contract (76.1) to crisis conditions, and treats the Module 10 Event Control Centre (38.1) as the physical home of the Crisis Command Centre rather than proposing a separate space.

## 89.2 Global and Lagos treatment

Globally reusable: the four-verb risk philosophy, incident/crisis test, scoring model, decision-trigger discipline, recovery sequence, one-voice principle and after-action/five-whys method. Lagos/Nigeria-context- dependent: the worked heavy-rain risk-score example, and the general observation that weather risk is “especially important for outdoor Nigerian events” — the module does not supply Lagos-specific probability baselines, drainage/flood behaviour, grid power reliability data or local emergency-service response benchmarks; these remain required inputs, not module content.

## 89.3 Exclusions applied

The CEO Master Exercise (nine-issue chieftaincy-celebration scenario) is excluded from canonical extraction, consistent with the standing exclusion of CEO exercises, challenges and master exercises. It remains valuable as a training/evaluation scenario and is a candidate for the AI-assurance shadow-mode testing gap already identified at Section 79.

## 89.4 Explicit gaps identified

- No calibrated probability/impact baseline exists for Lagos-specific risks (rainy-season probability by month, grid outage frequency, typical road-closure patterns); the 1–5 scale in 81.2 is a method, not a dataset.

- Weather GREEN/AMBER/RED thresholds (83.3) are explicitly left venue- and professional-advice-dependent; no default thresholds are proposed here.

- The relationship between the Module 11 crisis scale (86.2) and the 76.2 ladder is reconciled conceptually but not yet expressed as a single machine-evaluable rule; a system could still receive conflicting level assignments from the two models without an explicit mapping rule.

- No defined legal/regulatory notification triggers (insurance, liability, mandatory incident reporting) are specified; 88.1 flags this as outside module authority but the gap itself is unresolved.

- Client communication approval latency is undefined — the module requires a single approved external message but does not state how quickly a Client Communication Lead must be reachable during a live incident.

- Compensation authority during service recovery is referenced only indirectly via Module 9’s compensation boundary (68.2); Module 11 does not itself define who may approve a compensatory gesture during an active recovery.

- Staff/team welfare during extended incidents (11.47’s “incident fatigue”) is named as a risk category but no rotation, rest or supervision standard is specified.

# 90. Module 12 — canonical knowledge extraction

Source: “The Maison Doclar Event Operating System.” Status: approved foundation, subject to the CEO decisions listed in Section 11.11. Module 12 is integrative, not a twelfth specialist discipline: it names the system that Modules 1–11 have been components of, and in doing so it forces two direct reconciliations with the architecture already built in Sections 2 and 6 (Section 91) and surfaces one genuine, previously unaddressed gap: institutional memory that persists across events (Section 95).

**DEFINITION A luxury event should never depend on one person’s

memory, personality or ability to improvise. Maison Doclar should be

SYSTEM-DEPENDENT, HUMAN-LED.**

## 90.1 Person-dependent versus system-dependent

The founder/CEO remains important in the system-dependent model, but the organisation does not collapse in their absence: it already knows what to collect, what to ask, what to prepare, who owns each responsibility, what happens next, and what must be documented. This is a doctrine-level statement, not a new mechanism — Sections 1–2’s knowledge states, change discipline and hardcoding boundary are the mechanism that already makes this possible.

## 90.2 The Maison Doclar Event Equation

INTELLIGENCE + DESIGN + PEOPLE + SYSTEMS + COMMAND = EXPERIENCE, with DISCIPLINE as the multiplier: without it the system produces paperwork; with it, performance. This restates, at the whole-system level, the Section 2 system equation (knowledge + event data + context -> intelligence -> human decision or authorised action).

## 90.3 The control triangle

Guest (what are they experiencing), Event (what is happening) and System (what is controlling it) must remain aligned; disconnection between any two degrades quality. This is a diagnostic frame for command, not a new data object — it is answered by reading the existing Operational picture, Guest journey and Command-board state entities together.

## 90.4 The gold standard

Know the guest, host, culture and protocol; know what must happen and who owns it; know what could go wrong and the response; know the intended guest feeling; and learn from every event. This is a summary of Modules 1–11 plus the cross-event learning capability that Section 95 identifies as not yet built.

# 91. Reconciling the MD-EOS Delivery Lifecycle and control-layer models

Naming fix (M12-D03, resolved). Module 12’s fourteen-part sequence is renamed the MD-EOS Delivery Lifecycle, and its parts are called phases, not stages, specifically to stop it being confused with Module 2’s fourteen-stage Guest Journey. The two are never the same object: the Guest Journey is a per-guest record of what one guest experiences; the MD-EOS Delivery Lifecycle is a per-event record of what Maison Doclar does to produce that experience for everyone. Same count (fourteen), different word (phase vs. stage), different owner (per-guest vs. per-event) — that distinction should now be unambiguous in any implementation.

Module 12 proposes two structures that describe the whole system at a level Modules 1–11 did not: the fourteen-phase MD-EOS Delivery Lifecycle and a five-layer control model. Both overlap materially with structures already approved earlier in this specification. Per the change discipline (1.2), neither silently supersedes the other; both are reconciled here.

## 91.1 MD-EOS Delivery Lifecycle versus the Section 6 application lifecycle

The MD-EOS Delivery Lifecycle (Client -> Discovery -> Event Intelligence -> Event Architecture -> Guest Intelligence -> Protocol & Cultural Intelligence -> Vendor & Resource Architecture -> Production & Logistics -> Command & Control -> Live Event -> Guest Departure -> Follow-up -> Post-Event Intelligence -> Knowledge) is the institutional-resolution view of the same journey the Section 6 application lifecycle already describes at knowledge-application resolution (Discovery -> Data sufficiency -> Experience design -> Friction audit -> Invisible choreography -> Readiness review -> Live orchestration -> Post-event learning). Section 6 remains the authority for how knowledge is applied within any one phase; the fourteen MD-EOS phases are adopted as the canonical organisational-lifecycle envelope that Section 6 sits inside, roughly: Discovery=Discovery; Data sufficiency+Experience design=Event Intelligence/Architecture/Guest Intelligence/Protocol & Cultural Intelligence; Friction audit+Invisible choreography=Vendor & Resource Architecture/Production & Logistics; Readiness review=Command & Control (pre-open); Live orchestration=Live Event; Post-event learning=Guest Departure/Follow-up/Post-Event Intelligence/Knowledge. This mapping itself is provisional (M12-D01).

## 91.2 Five control layers versus the Section 2 knowledge architecture

Module 12’s five control layers (Intelligence, Design, Operations, Command, Learning) answer a different question from Section 2’s six knowledge layers (Doctrine, Decision knowledge, Configuration, Event data, Derived intelligence, Outcomes and learning). Section 2 answers “where does this knowledge live”; Module 12 answers “what phase of work is this.” They are not competing models of the same thing and neither supersedes the other, but a rule or product should be describable in both axes simultaneously (e.g. a Protocol Brief is Derived intelligence, produced in the Design control layer). No cross-index between the two currently exists (M12-D02).

## 91.3 Guest Journey versus MD-EOS Delivery Lifecycle

Module 2’s fourteen-stage canonical Guest Journey (13.1) is guest-facing — it describes what one guest experiences. The fourteen- phase MD-EOS Delivery Lifecycle is organisation-facing — it describes what Maison Doclar does to produce that experience, for every guest, plus the client, vendor and knowledge work around it. Both are retained; per the naming fix above, “stage” is now reserved for the Guest Journey and “phase” for the MD-EOS Delivery Lifecycle, so the two cannot be conflated in implementation or conversation.

# 92. The Master Event File and event-protection principles

## 92.1 Master Event File as an aggregating object

The Master Event File is genuinely new: nothing in Modules 1–11 proposed a single controlled object that aggregates the event’s sub-records (guest intelligence, VIP intelligence, protocol, cultural intelligence, seating, programme, vendor, production, risk, contingency, command, live operations, incident log, departure, follow-up, review, lessons) under one identifier and one owner. Every module so far produced its own well-specified data domain (Section 5) but not the container that proves they belong to the same event and are mutually consistent in version and status.

## 92.2 The Master Event ID

A unique internal identifier (e.g. MD-2026-023) is attached to every document, communication, guest record, vendor file and report belonging to one event. This is the join key that section 92.1’s aggregation and Section 95’s cross-event knowledge base both depend on — without it, “which venues have poor VIP parking” cannot be answered across events, because there is no common key linking a Venue record in one event to the same venue’s record in another.

## 92.3 Event-protection principles

The “must never happen” list (e.g. principal never kept waiting, VIPs never queue, sensitive family matters remain private, protocol never improvised) is a new first-class object: a small set of explicit, named non-negotiables for one event, distinct from the general doctrine in Sections 3–4 and from the risk register (Section 81) because a protection principle is not scored by probability x impact — it is simply never traded off. It should be visible to command at all times, not buried in a risk register alongside recoverable, gradable risks.

# 93. Client, principal and guest intelligence integration

## 93.1 Client intelligence layer

Family structure, decision-makers, communication preferences and prior event experience, captured only where it improves the experience (an explicit anti-collection instruction: “information is only valuable when it improves the experience”). This directly reinforces the Module 5 data-minimisation test (29.1) and should reuse it rather than create a second minimisation standard.

## 93.2 Principal Profile is not automatically a VIP Intelligence File

The Principal Intelligence File (name, preferred address, role, family structure, key relationships, schedule, communication style, decision authority, privacy requirements) is a new, event-scoped object distinct from the Module 5 VIP Intelligence File (28.3). Every principal needs one; not every principal will meet Module 5’s VIP-classification threshold, and Module 5’s AI-boundary rule against classifying someone VIP from status alone (8.1) still applies to the principal. Resolved (M12-D04): where the principal also meets VIP criteria, the two files share a common person identifier rather than duplicating fields — the Principal Profile record carries a “linked VIP file reference” field (Section 5) that is populated only when a VIP file actually exists for that person, and updates to shared fields (name, preferred address, privacy requirements) should be made once and read by both files rather than entered twice.

## 93.3 Event objective and experience intent

A single primary objective stated as an outcome, not an aesthetic (“create an intimate and dignified celebration that honours the principal’s new traditional position…”) plus primary/secondary/hidden objective layers and an explicit experience-intent sentence (“when the guest leaves, we want them to feel…”). This gives the Section 6 Discovery stage a required, checkable output it did not previously have a named template for.

## 93.4 Guest segmentation and the priority matrix

A first-class guest segmentation taxonomy (Principal, VIP, Dignitary, Royal/Traditional, Family, International, Elder/Senior, General Guest, Staff/Crew), explicitly overlapping (a guest may be Royal + VIP + Elder), feeding a Guest Priority Matrix (status, experience need, protocol need, mobility, security, owner). This is new as a first-class, explicit taxonomy: Modules 3–5 already carry the underlying assessment logic (precedence, cultural authority, VIP dimensions, accessibility needs) but had not previously been assembled into one guest-facing routing table that tells command, at a glance, which specialist modules apply to which guest and who owns them.

# 94. Dependency mapping, programme and command integration

## 94.1 Event-wide dependency map

Module 7 already defines vendor-to-vendor dependency intelligence (39.3, 50.1) scoped to vendor readiness. Module 12’s Event Dependency Map (venue access -> decor -> stage -> production -> lighting -> ceremony -> photography) is the same concept promoted to event-wide scope: it chains vendor, production, ceremony and command dependencies together, not only vendor-to-vendor ones. This is a genuine widening, not a new concept, and the existing Vendor command record and Transition entities (Section 5) should gain an explicit predecessor/successor link rather than only a free-text “dependencies” field, to make the map queryable (M12-D05).

## 94.2 Programme and Run of Show fields

Event time, activity, owner, location, participants, cue, dependency, duration, contingency. This matches the existing Master Timeline item and Run of Show / cue / clock model already established in Module 8 (Section 56) — no new object required; Module 12 simply confirms these fields as the minimum acceptable programme record at the operating- system level, not only the ceremony level.

## 94.3 Touchpoint quality test

Clarity, ease, personalisation, dignity, timing, discretion. This extends, and should be reconciled with, Module 2’s seven-question and never-ask journey tests (3.8, 10.2) rather than operating as a separate quality standard; the two should be applied together at every touchpoint (M12-D06).

## 94.4 Event status model and decision register

GREEN/AMBER/RED at the whole-event level is the same evidence-based RAG model already defined at 40.1/76.2 — not new. The Decision Register (time, decision, made by, reason, impact) is the same object as the existing Command decision entity (Section 5); Module 12 does not add a new data domain here, only confirms that every event should maintain a visible, chronological log of it rather than treating it as an optional record.

# 95. Departure, follow-up, reporting and the knowledge base

## 95.1 Departure as hospitality, not logistics

Departure sequencing, transport readiness, assistance, gifts, luggage and confirmed-safe principal departure are folded into the guest journey’s existing end boundary (13.1/13.2) rather than treated as a separate operational afterthought. “A beautiful event can end badly in a car park” is the operating risk this closes.

## 95.2 Follow-up layer and client debrief

Thank-you, photographs, feedback, personal and host follow-up, planned before the event rather than improvised after it. The Client Debrief (summary, guest feedback, outcomes, incidents, lessons, recommendations, media status, outstanding matters) and the Event Report (executive summary through recommendations) are new named intelligence products: Modules 1–11 produced situation reports and outcome records but no standard closing report template for the client and no standard internal event report template.

## 95.3 The cross-event knowledge base — the genuine gap

This is the most significant finding of Module 12’s integration. Section 2’s knowledge architecture is built, correctly, around a single event: Event data, Derived intelligence and Outcomes and learning are all scoped to one Master Event File. Module 12’s “Maison Doclar Event Memory” — answering questions like which venues have poor VIP parking, which caterers perform best above 300 guests, which transport providers are most dependable, which seating configurations work best, which protocol issues recur — requires knowledge that persists and aggregates across Master Event Files, keyed by venue, vendor, guest, protocol pattern and risk type rather than by event. No such cross-event index, ownership model or query capability exists anywhere in Sections 1–11. This is not solved by simply retaining more per-event Outcome records; it requires a new layer (M12-D07).

(Reinforced by Modules 15 and 16, resolved at Section 123.) Two later modules independently asked for the same missing capability without knowing it had already been flagged: Module 15’s feedback loop (“feeds into guest profiles, vendor evaluation, service standards, event design and training,” 116.2) and Module 16’s “Maison Doclar Event Intelligence Record” and “event intelligence company” concept (16.63–16.65) both describe exactly this cross-event layer. That three separate modules converged on the same unbuilt capability from different angles was corroborating evidence that raised its priority; it is resolved in full at Section 123.

# 96. SOP library and system readiness

## 96.1 Standard Operating Procedures as a new knowledge type

An SOP (e.g. the eleven-step VIP Arrival SOP) is distinct from both a Rule (Section 12.1’s minimum executable rule contract — conditional, machine-evaluable) and a Playbook (already present in the repository tree — multi-branch response guidance). An SOP is a fixed, ordered, human-executed procedure that becomes canonical only after repeated successful use. It needs its own promotion path: repeated event evidence -> proposed SOP -> approval -> versioned SOP library entry, following the same Proposed/Approved/Provisional/Superseded/Rejected states as any other knowledge item (Section 1.1).

## 96.2 System readiness versus event readiness

“Is the system ready?” (people, information, guests, protocol, venue, vendors, production, transport, security, contingencies, command all ready) is a meta-check that the readiness gates already defined in Modules 3, 4, 5, 7, 8, 9 and 10 have each actually been run and passed for this Master Event File — it is not a new gate itself, but the aggregation point that should refuse to show “ready” if any one specialist gate is missing, stale or failed (M12-D08).

## 96.3 The Known Unknowns register

Distinct from the Section 81 risk register: a risk is a credible possible harm with a probability and impact; a Known Unknown (final VIP arrival time, final guest count, speaker confirmation, traffic conditions) is a fact that is not yet available but will become available before or during the event, and does not necessarily carry negative consequence. Making unknowns visible, rather than letting them default silently to an assumption, is the operative discipline; this reinforces rather than duplicates the AI-boundary rule against inventing absent facts (8.1).

# 97. Decisions supported by Module 12

Module 12 supplies: the Master Event File aggregation model and Event ID join key; event-protection principles as a distinct non-negotiable object; the Principal Profile and guest-segmentation/priority-matrix routing layer; the event-wide dependency map; standard Client Debrief and Event Report templates; the SOP promotion path; the system-readiness aggregation check; and the Known Unknowns register. It also supplies two necessary reconciliations (MD-EOS Delivery Lifecycle with Section 6; control layers with Section 2) and surfaces the cross-event knowledge base as an unbuilt layer.

## 97.1 Decisions outside Module 12 authority

The specific technical design of a cross-event knowledge index (data model, privacy segregation between clients, retention policy) is an engineering and privacy-governance decision beyond this module’s authority; Module 12 establishes that the layer is required, not how it is built.

# 98. Module 12 relationships, exclusions and gaps

## 98.1 Relationship to Modules 1–11 — direct answer to the readiness question

Assessed against the question of whether the data and knowledge base required for Module 12 already existed: mostly yes, with four specific exceptions. Every domain-level fact Module 12 references (guest, VIP, protocol, cultural, vendor, production, command, risk) was already modelled in Section 5 by Modules 1–11, and every specialist process it invokes (readiness gates, RAG, dependency intelligence, the guest journey, the escalation ladder) already existed and needed only confirmation or reconciliation, not new design. The four genuine additions were: (1) the Master Event File/Event ID as the object that proves all those domains belong to one governed event; (2) event-protection principles as a non-negotiable object distinct from scored risk; (3) SOPs as a knowledge type distinct from rules and playbooks; and (4) the cross-event knowledge base, which is the one capability Module 12 assumes (“if the lessons are stored properly, the organisation becomes progressively smarter across 10, then 50, then 100 events”) that nothing in Sections 1–11 actually provides yet, because the entire architecture to this point is correctly but exclusively single-event scoped.

## 98.2 Global and Lagos treatment

Globally reusable: MD-EOS structure, the fourteen-phase Delivery Lifecycle, the Master Event File concept, guest segmentation, dependency mapping, SOP promotion path and the control triangle. Lagos/Nigeria-context- dependent: the worked chieftaincy-celebration example only; no Lagos-specific venue, vendor or transport-reliability data is supplied by the module itself (that population of the cross-event knowledge base is future operational work, not module content).

## 98.3 Exclusions applied

The CEO Master Assignment (400-person Lagos chieftaincy celebration, fifteen-part build exercise) is excluded from canonical extraction, consistent with the standing exclusion of CEO exercises and master exercises. It is a strong second candidate, alongside Module 11’s exercise, for formal AI shadow-mode/end-to-end evaluation once that capability is built (Section 79’s assurance gap).

## 98.4 Explicit gaps identified

- No cross-event knowledge base/index exists (95.3) — the single largest gap this module surfaces.

- The MD-EOS Delivery Lifecycle and Section 6 application lifecycle mapping (91.1) is proposed, not approved.

- No cross-index exists between the five control layers and the six knowledge-architecture layers (91.2).

- No data model links a Principal Profile to a VIP Intelligence File when the same person qualifies for both (93.2).

- Dependency links remain largely free-text within existing entities rather than a queryable predecessor/successor structure (94.1).

- No promotion workflow, ownership or versioning scheme is specified for SOPs beyond “document it after repeated success” (96.1).

- No privacy/segregation model is defined for what cross-event knowledge (95.3) may be shared between different clients’ events — this is a material risk given Module 5’s VIP-discretion and data-minimisation doctrine, and should be resolved before any cross-event index is built, not after.

- No named owner exists yet for the Master Event File itself as a governance role (who may open, close, merge or archive one).

# 99. Module 14 — canonical knowledge extraction

Source: “Staffing, Service Culture & the Maison Doclar White-Glove Team.” Status: approved foundation, subject to the CEO decisions listed in Section 11.13. Module 14 opens a genuinely new domain — the organisational/HR layer that puts capable people in front of the standards Module 9 already defined — while its guest-facing behaviour content substantially overlaps Module 9 and is reconciled rather than duplicated (Section 103).

**DEFINITION Luxury service is delivered by people. The environment

creates the impression; the people create the experience. Every

visible employee is a brand ambassador.**

## 99.1 Staffing follows function, not headcount

The wrong question is “how many ushers do we need.” The right sequence is guest functions needed -> roles -> responsibilities -> coverage -> staffing level. This is the organisational-design principle Module 9’s 65.1 zone plan already applies to coverage; Module 14 extends it upstream to how the roles themselves get defined and filled.

## 99.2 The white-glove team attributes

Observant, anticipatory, discreet, composed, polished, respectful, responsive, and invisible when necessary. This is a hiring and training target, not a new behaviour standard — it restates, at the person level, what Module 9’s doctrine (observe -> anticipate -> act -> disappear) already requires of behaviour.

# 100. Team architecture, ownership and escalation

## 100.1 Team architecture

Executive leadership; Event Command (Event Director, Operations Lead, Guest Experience Lead, Protocol Lead); specialist functions (VIP Manager, Guest Relations, Transport/Hospitality/Production/Catering/ Security Leads); front-of-house (concierge, reception, ushers, guest assistants); back-of-house (runners, logistics, support, cleaning). This is new: nothing in Modules 1–13 laid out the organisational chart itself, only the command authority structure (Module 6) and the service standards staff must deliver (Module 9). The chart changes per event and is not itself a data object beyond the existing Master Event File’s people/roster references.

## 100.2 One owner, and RACI for larger events

Every important function has one accountable owner — “everyone watches VIP arrivals” means nobody does. For larger events, RACI (Responsible/ Accountable/Consulted/Informed) makes this explicit per task. This directly implements the “one accountable lead” doctrine already stated for vendors (Section 47) and generalises it to Maison Doclar’s own staff.

## 100.3 The staff escalation matrix — reconciled with 76.2

Module 14’s four-level staff escalation matrix (Self-resolve -> Team Lead -> Event Director -> Executive/CEO) is the same pattern already resolved for the crisis scale at 86.2: it is not a second escalation model, it is the staff-facing simplified view of the existing 76.2 five-level ladder, skipping Ladder Level 3 (Department/Function Lead) for ordinary staff-initiated escalations the same way the crisis scale skips it for crisis-track items. 76.2 remains the one canonical mechanism.

# 101. Recruitment, selection and hiring for character

## 101.1 Character before cosmetics

Emotional intelligence, self-control, respect, reliability, observation, humility, communication and judgement are the hiring criteria — not appearance alone. This is genuinely new: no module before this one addressed how Maison Doclar’s own people get selected, only how they must behave once deployed (Module 9) or how vendors are selected (Module 7).

## 101.2 Diagnostic interview techniques

Three situational prompts and what they reveal: the upset-guest test (does the candidate approach calmly and offer help without forcing public explanation, versus simply asking “what’s wrong”); the proactive-service test (does the candidate recognise and approach an unattended VIP, versus waiting for a supervisor); and the discretion test (does the candidate treat a recognised celebrity/dignitary professionally, with no staring, selfies, gossip or social media, versus treating them as a spectacle). These are hiring-stage diagnostics for the same discretion and anticipation standards Module 9 already requires operationally — the techniques are new, the standard being tested for is not.

# 102. Deployment: briefing, role cards and positioning

## 102.1 Staff briefing content

Event purpose, client, guest profile, experience intent, special guests, protocol, service standard, programme, risks, escalation, communication, dress and conduct. This is the pre-deployment version of Module 9’s existing “five-minute huddle” staff delivery view (63.3), which already specifies purpose/principal/VIPs/changes/sensitivities/standards/ restrictions/escalation content; Module 14 supplies the fuller one-time-at-shift-start briefing that the huddle then refreshes.

## 102.2 Role cards

A concise per-person card: role, reports to, location, responsibilities, explicit “do not” list, and escalation triggers. This is the same object as Module 9’s existing “role briefing card” (63.3) — Module 14 contributes a fully worked example (VIP Arrival Assistant) rather than a new object, and the explicit “do not” list is a useful addition worth folding into the 63.3 card content: discuss guest details, photograph guest, leave post without replacement are now adopted as standard “do not” fields on every role card, not just the worked example.

## 102.3 Staff positioning map and the Floating Concierge

Deploying “10 ushers” without a zone allocation is rejected in favour of an explicit per-zone headcount (entrance, reception, main hall, VIP, dining, floating concierge). This is the staffing-level output of Module 9’s existing zone plan (65.1), which defined what capability each zone needs but not how many people — Module 14 closes that gap directly. The Floating Guest Concierge (no fixed station, scans for confusion, isolation, discomfort, queues, elderly/child needs, VIP movement) is a genuinely new named role that operationalises Module 9’s “comfort intelligence” (67.4) and “observation zone” concept as a person rather than a passive monitoring function.

# 103. Service language, presence and body language — reconciled with Module 9

Module 14’s presence/courtesy standards, body-language guidance and the “avoid X, say Y” service-language table are, with minor wording differences, the same content already canonical at Module 9 Sections 64.1–64.2. No new standard is created here; Module 9’s table and behaviour list remain authoritative. Two points from Module 14 do add real value and are folded in directly:

- The three-step frontline response (Acknowledge -> Own -> Resolve) is adopted as the simplified, staff-trainable version of Module 9’s full five-step recovery playbook (Listen -> Acknowledge -> Own -> Solve -> Follow up, 68.1). Frontline staff train on the three-step version for everyday requests; the full five-step version remains the standard for a formal service-recovery event.

- The warm handoff (“allow me to introduce you to our concierge, who will assist you” plus physical hand-over) is a concrete behavioural instantiation of Module 9’s existing ownership-transfer states (65.2: Transfer proposed -> Transfer accepted) and is adopted as the approved script pattern for that transition.

Resolved (M14-D01). Module 9 had flagged its own acknowledgement- time heuristics (“approximately 3 seconds, 5 seconds… unvalidated,” 70.5) as needing calibration, and Module 14 added a third candidate — the “10-second rule.” The CEO has set 5 seconds as the single canonical acknowledgement target (now reflected at 64.1 and in the 62.0 heuristic table). The 3-second and 10-second variants are retired.

# 104. Culture, recognition, accountability and correction

## 104.1 How culture is built

Recruitment -> training -> modelling -> reinforcement -> recognition -> accountability -> repetition, until behaviour becomes automatic. This is new: it is the mechanism by which Module 9’s standards stop requiring active supervision and become self-sustaining — Module 9 defined what good behaviour is and how to verify it; Module 14 defines how an organisation gets people to do it without being watched.

## 104.2 Recognition and accountability

Recognise exceptional observation, discretion, problem-solving, guest care, calmness and initiative; and apply real consequences for ignoring guests, gossiping, disrespect, repeated lateness, confidentiality breaches or refused instructions. Correction happens in private — “praise publicly, correct privately” — protecting both guest experience and staff dignity. This is new operational doctrine; Module 9’s 70.5 gap list already flagged that “staff observation, performance assessment… fairness, coaching, disciplinary boundaries… require HR/privacy governance” — Module 14 supplies the doctrine and behavioural triggers but not the formal HR process itself, which remains open (Section 107.4).

## 104.3 Empowerment and discretionary service-recovery authority

Authorised staff may resolve small matters (complimentary refreshments, seating adjustment, transport assistance, small amenities) without escalating every minor issue. This is a concrete instantiation of Module 9’s existing compensation boundary (68.2), which already requires delegated limits for any remedy — Module 14 supplies example categories of what a small delegated limit looks like; the actual thresholds remain event/client-defined, as 68.2 already states.

## 104.4 The five levels of staff maturity

Instruction -> Competence -> Awareness -> Anticipation -> Judgement. A new development framework for training and assessment, distinct from Module 9’s Met/Failed/Exception competency states (69.1) — that model scores whether one standard was demonstrated; this model describes a person’s overall developmental stage across all standards, and is best used for coaching and career conversations rather than event readiness gating.

# 105. Staff wellbeing, communication and confidentiality

## 105.1 Staff wellbeing as operational planning

Breaks, water, meal arrangements, rotation, rest and relief coverage are planned, not improvised, because a stressed team creates guest-visible failure even when the physical event is perfect. This directly responds to the staff-welfare gap identified under Module 11 (M11-D08, “incident fatigue” — no rotation/rest/supervision standard specified): Module 14 supplies the planning categories but still no numeric standard (shift length, break frequency, rest ratio), so M11-D08 remains open, now with concrete categories to build a standard from rather than a bare gap.

## 105.2 Staff communication protocol

Brief, clear, professional radio discipline; never broadcast sensitive guest information (“VIP movement approaching” rather than naming a principal). Optional internal code words (VIP 1, Principal, Vehicle 2) for highly sensitive events. This is the staff-communication-specific instantiation of the existing need-to-know principle already established for VIP security (83.2) and the message contract (76.1); no new mechanism, direct application to internal radio traffic specifically.

## 105.3 Staff confidentiality and social media

Staff should never discuss who attended, what was spent, family matters or VIP requests, and should never photograph/post without express authorisation. This applies the same confidentiality and content-rights discipline already established for vendors under the Module 13 Partner Code (48.5) and for photography generally (85.1) to Maison Doclar’s own employees — a parallel extension across the workforce, not a new policy shape.

# 106. Decisions supported by Module 14

Module 14 supplies: the organisational team architecture and RACI model; character-based hiring criteria and diagnostic interview technique; pre-deployment briefing content and the role-card “do not” field; the staffing-level output (headcount per zone) for Module 9’s zone plan and the Floating Concierge role; the culture-building mechanism (recruitment through repetition) that makes Module 9’s standards self-sustaining; recognition/accountability doctrine; the five-level staff maturity model; and staff-specific wellbeing, communication and confidentiality practice.

## 106.1 Decisions outside Module 14 authority

Recruitment sourcing and vetting, employment classification and labour law, formal training curriculum design and certification tracking, ongoing performance management and career progression, formal HR disciplinary/grievance process, safeguarding policy for minors/ vulnerable guests, staff personal-data privacy, compensation/payroll/ overtime, staff insurance and liability, and work-authorisation for international deployment are all HR, legal and regulatory matters outside this module’s authority (Section 107.4).

# 107. Module 14 relationships, exclusions and gaps

## 107.1 Relationship to Modules 1–13

Module 14 is genuinely new where it addresses the organisational/HR layer (team architecture, hiring, culture-building, staff wellbeing) and substantially overlapping where it addresses guest-facing behaviour, which remains governed by Module 9 (Section 103). It directly reuses, rather than re-proposing, the 76.2 escalation ladder (100.3) and the 68.2 compensation boundary (104.3), and it supplies concrete content for two gaps Module 9 already flagged rather than closing them fully: staff performance/disciplinary governance (104.2) and staffing-demand modelling (102.3, still no supervisor-ratio or shift-length standard).

## 107.2 Direct answer to “are we set up without blind spots?”

What is now covered: organisational structure and one-owner discipline; RACI for complex events; character-based hiring criteria and interview diagnostics; pre-deployment briefing and role clarity; zone-by-zone staffing levels and the Floating Concierge; the mechanism for turning standards into self-sustaining culture; recognition and behavioural accountability; a staff development/maturity framework; wellbeing planning categories; and staff-specific communication and confidentiality discipline.

What is still a genuine blind spot even after this module — none of the following exist anywhere in Sections 1–14, and Module 14 does not supply them:

- Recruitment sourcing and vetting — where candidates come from, reference checks, background/criminal checks, right-to-work verification.

- Employment classification and labour law — staff vs. contractor vs. agency status, contracts, statutory entitlements, working-time law.

- Formal training curriculum and certification tracking — Module 9 already flagged this gap (70.5); Module 14 describes what good training produces but not a curriculum, delivery method, or a system that tracks who is certified in what and when it expires.

- Ongoing performance management and career progression — Module 9’s competency model and Module 14’s maturity model both operate within one event; neither addresses performance review cadence, promotion, retention or compensation growth over time.

- Formal HR disciplinary and grievance process — “there must be consequences” (104.2) states the principle; there is no defined process, appeal right, or documentation standard.

- Safeguarding policy for minors or vulnerable guests — Module 9 already flagged this gap (70.5: “children’s service requires safeguarding, guardian authority… not a generic hospitality checklist”); Module 14 does not address it either.

- Staff personal-data privacy — staff are data subjects too; nothing in Sections 1–14 governs how staff performance observations, background-check results or personal details are stored, accessed or retained.

- Compensation, payroll and overtime — not addressed by any module to date.

- Staff insurance and liability — injury, third-party harm caused by staff, and indemnity are not addressed.

- Work authorisation for international deployment — relevant given the international-guest and destination-event context already established elsewhere in the specification, but never addressed for Maison Doclar’s own staff.

- Diversity, equity and inclusion in hiring — not addressed.

All of the above require HR, legal and/or regulatory ownership beyond this specification’s authority and are logged as open decisions (Section 11.13) rather than assumed.

## 107.3 Exclusions applied

The Module 14 CEO Master Assignment (400-person Lagos chieftaincy celebration staffing design) is excluded per the standing rule on CEO exercises and master exercises.

## 107.4 Explicit gaps and unresolved conflicts

- (Resolved, M14-D01) A third, uncalibrated acknowledgement-time number (“10-second rule”) had been added alongside Module 9’s already-flagged “3 seconds, 5 seconds” heuristics. CEO set 5 seconds as the single canonical acknowledgement target; 3-second and 10-second variants retired (64.1, 62.0).

- All eleven items listed in 107.2’s blind-spot list.

- No staffing-demand model yet exists (headcount by attendance/flow/ venue/supervisor ratio) despite Module 14 supplying the format (positioning map) — this restates and does not close the Module 9 gap at 70.5.

- No formal linkage is defined between the Module 14 maturity model (104.4) and Module 9’s per-standard competency states (69.1) — an implementation could score both without any rule connecting a person’s maturity level to which standards they are trusted to self-resolve.

# 108. Module 15 — canonical knowledge extraction

Source: “Guest Communication, Concierge & the Art of Personalisation.” Status: approved foundation, subject to the CEO decisions listed in Section 11.14. Module 15 fits almost entirely inside disciplines this specification already carries — the Communication and Touchpoint data model (Module 2, 13.5), the VIP data-minimisation and channel-boundary rules (Module 5, 29.1/29.3), the pre-event intelligence cadence (Module 5, 30.2), the service-language table (Module 9, 64.2) and the recovery playbook (Module 9, 68.1). Its genuine new contribution is guest-facing correspondence itself as a first-class subject: invitation, RSVP, the concierge channel, and the specific discipline of turning administrative information into reassurance.

**DEFINITION Communication is not administration. Communication is

hospitality. A guest should never have to work hard to understand what

happens next.**

## 108.1 The four qualities

Clear, Considered, Calm, and Personal. This extends Module 2’s communication-intelligence discipline (13.5, “every message must have a purpose, audience, approved content version…”) with the tone standard that discipline assumed but never stated.

## 108.2 The guest should never have to wonder

At every journey stage, anticipate the guest’s next question before they ask it. This is the communication-specific form of Module 1’s anticipation-levels doctrine (3.4) and Module 9’s “observe -> anticipate -> act -> disappear” (62.0) — applied to what is said rather than what is done.

# 109. Communication journey, cadence and version control

## 109.1 The communication journey, reconciled with the cadence models

Module 15’s journey (Invitation -> RSVP -> Acknowledgement -> Confirmation -> Pre-event information -> Reminder -> Arrival support -> Live concierge -> Departure -> Follow-up) is the general-guest expression of cadence already defined at two other resolutions: Module 2’s Communication intelligence (13.5, the what every message must carry) and Module 5’s VIP pre-event intelligence cadence (30.2, the windowed T-72/T-14/T-24/ event-day/after-departure schedule for VIPs specifically). Rather than maintaining an independently-timed general cadence, the general guest communication schedule adopts Module 5’s window boundaries (T-14 to T-3 days = “pre-event information,” T-24 hours = “reminder,” event day = “arrival support”) so a single cadence engine serves both tiers, with VIP communication carrying additional intelligence-gathering content at each window that general guest communication does not.

## 109.2 One source of truth — reconciled, not new

Conflicting information (“the invitation says 5:30, the driver says 5”) is prevented by the same mechanism already defined for operational documents generally: the existing Operational document version entity (Section 5: type, event, version, owner, approved at/by, effective time, supersedes, withdrawal) and the Master Event File (92.1) that anchors every document to one event. Guest-facing correspondence templates (invitation, confirmation, reminder, concierge scripts) are simply another document type under that existing control — no new version-control mechanism is created here.

# 110. Personalisation, guest data and channel governance

## 110.1 Personalisation versus surveillance

“We have arranged a private vehicle for your arrival” (good) versus “we know you prefer a Mercedes S-Class and dislike traffic” (intrusive unless the guest explicitly shared that preference for service purposes) is a direct application of Module 5’s data-minimisation test (29.1) and golden privacy rule (“if the team cannot explain why an item is needed to serve the guest safely and appropriately, it does not belong in the system”) to guest-facing correspondence specifically, rather than a new privacy standard.

## 110.2 The concierge channel is a governed channel, not an exception

Module 5’s communication-channel boundary (29.3) already restricts confidential/restricted content to controlled channels rather than broad messaging groups. The WhatsApp/digital concierge channel Module 15 proposes is a guest-facing application of that same boundary: the concierge works from the controlled source (the guest’s Level 1 service information, 29.2), never becomes a second database, and confidential/ restricted-level content is never dropped into an unstructured guest chat thread. This is a direct extension of an existing rule to a new channel, not a new rule.

# 111. Invitation, RSVP and confirmation

These are genuinely new objects — nothing in Modules 1–14 modelled the pre-arrival guest correspondence lifecycle itself.

- Invitation: the first service touchpoint, not merely an announcement — it establishes event character, status, expectation, tone and formality, and should be evaluated by the same “does the guest feel expected, is the RSVP effortless, is anything ambiguous” test the module proposes.

- RSVP: the beginning of guest intelligence, not merely headcount — captures attendance, plus-ones, special requirements, arrival needs, dietary/accessibility needs and protocol relevance, feeding directly into the existing Guest and Guest journey data domains (Section 5) rather than a separate system.

- Confirmation: answers are-you-confirmed / what / when / where / what-happens-next immediately on RSVP receipt, with additional private content for VIPs per the existing three-information-level model (29.2).

- Reminders: each message adds new value rather than repeating the last one (confirmation -> practical information -> final reassurance -> arrival support), aligned to the cadence in 109.1.

# 112. The concierge function — three variants, one discipline

Three concierge-type roles now exist across the specification, and they are complementary functions, not competing definitions of the same job: the Floating Guest Concierge (Module 14, 8.0.7) is a physical, on-site, no-fixed-station role that scans for unmet need during the live event; the Cultural Experience Concierge (Module 4, 24.1) is a specialist who briefs culturally unfamiliar guests and liaises with cultural authorities; and Module 15’s digital/WhatsApp Concierge is a correspondence-channel role spanning before, during and after the event. On a smaller event the same person may hold all three; on a large event they are typically separate people coordinating through the normal command structure. None of the three has authority the others lack — all operate within the delegated limits already defined at 104.3 and escalate through 76.2.

## 112.1 The concierge intelligence pack

Before the event, the concierge (whichever variant) requires: event schedule, venue map, guest services, parking, transport, seating information, VIP protocol, dress guidance, dietary information, emergency contacts and escalation contacts. This is a role-scoped extraction from the Master Event File (92.1) and existing data domains (Section 5) — a delivery format, not a new data source.

# 113. Language, tone and the communication hierarchy

Module 15’s “avoid harsh phrasing, use gracious alternatives” guidance and its worked examples (“for your convenience, guest parking is available at…” rather than “you cannot park here”) are additional approved-language examples within Module 9’s existing service-language table (64.2), which remains the canonical object — no new table is created. Two points are new and are adopted directly:

- Clarity before ornament: an over-polished message that never tells the guest where to park has failed regardless of how elegant its prose is — a direct check against the four qualities (108.1) over-indexing on “Considered” at the expense of “Clear.”

- The communication-priority hierarchy: Action, then Time, then Location, then Context, then Detail — a concrete ordering rule for drafting any guest message, adopted as the default structure for Invitation, Confirmation and Reminder content (Section 111).

# 114. Difficult guests, complaints and escalation — reconciled

## 114.1 The recovery sequence remains Module 9’s

Module 15’s “Listen -> Acknowledge -> Clarify -> Solve” (for difficult guests, 15.35) is a variant of the canonical five-step recovery playbook (Listen -> Acknowledge -> Own -> Solve -> Follow up, 68.1), substituting “Clarify” for “Own” and dropping “Follow up.” Rather than adopt a fourth competing sequence — after the three-second/five-second/ten-second pattern already resolved once this cycle — Clarify is folded into the canonical sequence as an optional sub-step between Acknowledge and Own, used when the complaint’s cause is not yet understood; Own, Solve and Follow up remain mandatory and unchanged. The 68.1 table remains the one canonical object.

## 114.2 Complaint types — already exist

Module 15’s difficult-guest categories (angry, impatient, demanding, confused, entitled) sit under the three complaint types already defined at Module 11 (84.2: valid, misunderstood, unreasonable) and the same response — “I understand your concern, let me take care of this for you,” never arguing, dignity preserved while holding the correct boundary — already established there. No new taxonomy is created.

## 114.3 Communication escalation — reconciled with 76.2

Module 15’s four-level communication escalation (Concierge resolves -> Team lead -> Event Director -> CEO/client principal) is, per the pattern already resolved for Module 14’s staff escalation matrix (100.3), the communication-facing simplified view of the same 76.2 five-level ladder, not a third escalation model. No new decision is required; this is integrated directly.

## 114.4 The service recovery message — the verbal layer

Module 15’s four-part message template (Acknowledgement, Ownership, Action, Reassurance) is not a competing action sequence — it is the script for the Acknowledge and Own/Solve steps of the canonical recovery playbook: what staff actually say while performing those steps. Adopted as the approved phrasing pattern for service-recovery communication specifically.

# 115. Family authority, guest-decision conflicts and international guests

## 115.1 Family authority conflicts — resolved (M15-D04)

“One family member says move this guest, another says they must sit here” is a genuinely new scenario this specification had not addressed: Module 3’s precedence conflict-resolution sequence (16.5) governs formal/ ceremonial precedence disputes, and the VIP one-guest-one-accountable- owner model (30.1) governs who owns a VIP’s experience, but neither named who has final say when family hierarchy itself is contested for an ordinary (non-VIP, non-ceremonial) guest-experience decision like seating.

Resolution. This is not a new authority model — it is the existing 49.3 rule (“family, host, CEO and client-nominated supplier requests are routed through the designated command path”) extended explicitly from vendor instructions to guest-experience decisions generally. Two layers apply:

- Pre-event (default and preferred): the Principal/host names one Family Decision Owner for guest-experience matters as part of the Principal Profile (Section 5, field added). This is an event-only designation, not a permanent role — it may be the principal themselves, a spouse, an eldest child, or whoever the principal designates. Once named, only that person’s instruction on guest-experience matters is actioned; other family members are received respectfully but their instructions are not executed without the Family Decision Owner’s confirmation, exactly as 49.3 already requires for supplier instructions.

- Live fallback (if no owner was named, or the Family Decision Owner is unreachable): authority defaults to the Event Director, per the 76.2 ladder’s Level 4 scope (“whole-event operational trade-off”). The Event Director does not adjudicate family politics — they apply the existing guest-experience and protocol rules (dignity preserved, correct boundary held, per 84.2/17.5) and hold that decision unless it meets the crisis- escalation test (86.2/11.3), in which case it escalates further.

Staff are trained, as part of the pre-deployment briefing (Section 102.1) and role card “do not” field (Section 5), never to action a guest-experience instruction from an undesignated family member. This closes M15-D04.

## 115.2 International guest communication — resolved (M15-D05), companion to Module 4

Module 15’s international-guest content (airport, visa, transport, hotel, currency, weather, dress, timing, local customs, security) is practical/logistical; Module 4’s existing International Guest Cultural Brief (24.2) is meaning/etiquette (greeting, dress meaning, titles, ceremony, religion, photography, dining/gifts). Resolved: these merge into a single International Guest Brief with two sections — Logistics (this module’s content) and Culture (Module 4’s 24.2 content, unchanged) — using the same progressive-disclosure delivery already specified at 24.2 (one-page essentials, optional deeper context, named human guide). It is delivered as one document, at one time, by whichever concierge variant (Section 112) is assigned, rather than two separately- timed briefs. Module 4’s 24.2 table and 24.1 Cultural Experience Concierge role are otherwise unchanged; this only changes the delivery packaging.

# 116. Client communication, post-event follow-up and the feedback loop

## 116.1 The no-surprise principle — reconciled

“Bad news should arrive early… the client should never discover a problem from a guest, WhatsApp, Instagram or a vendor” restates Module 11’s client-briefing formula and one-voice principle (85.3) and the don’t-transfer-anxiety doctrine (85.4) verbatim in effect. No new object; this reinforces existing doctrine and is folded into it rather than duplicated.

## 116.2 Post-event communication and feedback

Thank-you, feedback, photographs, next steps and lost property follow-up are the guest-facing instance of Module 12’s existing Follow-up layer and Client Debrief object (95.2). The feedback-quality guidance (“what felt particularly memorable” rather than “rate us 1–5”) is new and useful content for that existing object, not a new one. Critically: feedback “feeding into guest profiles, vendor evaluation, service standards, event design and training” is exactly the cross-event knowledge base Module 12 already identified as the specification’s single largest unbuilt layer (95.3, M12-D07) — Module 15 does not close that gap, it adds another source that will need to feed it once it exists.

# 117. Decisions supported by Module 15

Module 15 supplies: the invitation/RSVP/confirmation/reminder object set and its content standard; the concierge intelligence pack and the three-concierge-variant relationship; the Action/Time/Location/Context/ Detail message-drafting hierarchy; the Clarify sub-step and service- recovery message script folded into the canonical recovery playbook; and the requirement (not yet the answer) for a named family-authority decision owner.

## 117.1 Decisions outside Module 15 authority

WhatsApp Business API selection, data retention and consent policy for guest messaging; the exact response-time SLA per enquiry class; legal/ tact review of firm-boundary phrasing (e.g. “adults-only celebration”); and feedback-survey platform selection are operational, legal and vendor-selection matters outside this module’s authority.

# 118. Module 15 relationships, exclusions and gaps

## 118.1 Relationship to Modules 1–14

Module 15 is the most heavily reconciled module since Module 13: nearly every structural element it proposes already exists elsewhere in this specification (Communication/Touchpoint data model, VIP privacy and channel rules, pre-event cadence, service-language table, recovery playbook, escalation ladder, client-briefing doctrine, follow-up layer). Its lasting contribution is the guest correspondence lifecycle itself (invitation through RSVP through concierge through follow-up) as a named, first-class subject, plus the family-authority gap it correctly identifies but does not close.

## 118.2 Global and Lagos treatment

Globally reusable: the four qualities, the anticipate-the-next-question principle, personalisation-without-intrusion, the message hierarchy, and the concierge intelligence pack format. Lagos/Nigeria-context-dependent: the specific guidance that a guest “20 minutes away” may operationally mean much longer given traffic, and that journey communication should be built around real-world Lagos conditions rather than map-distance estimates.

## 118.3 Exclusions applied

The Module 15 CEO Master Assignment (250-person guest-communication architecture design) is excluded per the standing rule on CEO exercises and master exercises.

## 118.4 Explicit gaps identified

- (Resolved, M15-D04) No named decision authority was defined for family-hierarchy guest-experience conflicts. Resolved via Principal-designated Family Decision Owner with Event Director fallback (115.1).

- (Resolved, M15-D05) The logistics/cultural international-guest brief merge was proposed, not approved. Merged into one International Guest Brief (115.2).

- No WhatsApp Business API, data-retention or consent policy exists for guest-facing messaging (117.1) — a real operational gap given how central the channel is to Module 15’s own recommendation.

- No response-time SLA is defined by enquiry class or guest segment; Module 15 states the principle (“silence creates uncertainty”) but not a number, consistent with how other heuristics in this specification require event-specific calibration rather than a global default.

- Feedback captured post-event has no destination system — it is correctly routed toward the cross-event knowledge base (116.2), but that base does not yet exist (M12-D07 remains the specification’s most consequential open item).

# 119. Module 16 — canonical knowledge extraction and reconciliation

Source: “Event-Day Command, Control & the Maison Doclar Operations Room.” Status: approved foundation, subject to the CEO decision listed in Section 11.15. Module 16 is the most heavily reconciled module to date — more even than Module 13 or 15. Its command structure, control loop, look-ahead horizons, Command Centre concept, message contract, programme-resilience classification, and after-action/knowledge-base concepts are already canonical here via Modules 6, 8, 9, 10 and 11 (each cross-referenced inline above at 38.1, 42.0, 59.2 and 74.1). What follows is what remains after that reconciliation: genuinely new material, plus the one real conflict this module introduces.

**DEFINITION Maximum control. Minimum visible effort. Invisible

complexity, visible calm.**

## 119.1 Genuinely new content, adopted directly

- The CEO should not become the radio operator (16.6). A sharp, quotable statement of a principle that was previously only implicit in the CEO/Event Director decision split (37.3) — worth keeping in the CEO’s own words as a standing self-check.

- First guest, last guest (16.57-16.58). The first arrival deserves the same care as the most important arrival, and the event is not over when the programme ends — departure is still an experience. This sharpens the existing journey start/end boundary (13.1/13.2) and departure-as-hospitality doctrine (95.1) with a concrete attention rule: care does not ramp up gradually as the room fills, and does not switch off when the last programme item concludes.

- The 80% decision rule (16.50). Waiting for perfect information can cost more than acting on good information when risk is manageable; escalate only when consequences are significant. This pairs directly with the existing five-minute ownership rule (40.3) and decision-latency measures (78.3) as the judgment principle behind those mechanisms.

- Radio phrasing examples (16.15-16.16). Concrete worked examples (“Transport Lead to Command. Vehicle 4 is at Gate B with the international guest. Concierge required.”) for the existing WHO/ WHERE/WHAT/ACTION message contract (76.1) — illustration, not a new rule.

- The event-day decision matrix (16.48) — safety / VIP / client / guest experience / programme / can-we-absorb-it — is adopted as the quick operational checklist version of the fuller 76.3 consequence- prioritisation model, for use in the moment rather than during deliberate risk planning.

## 119.2 One conflict — resolved (M16-D01)

Module 16’s Incident Priority scale (16.25: Level 1 Minor/no guest impact, Level 2 Local/limited guest impact, Level 3 Major/significant guest impact, Level 4 Critical/safety-security-principal-reputational- event-threatening) was a fourth severity-labelling scheme alongside three that already existed: Module 11’s 1–5 probability x impact risk score (81.2), Module 11’s five-level Crisis Scale (86.2, itself already reconciled onto the 76.2 ladder), and Module 14’s staff escalation matrix (also reconciled onto 76.2).

Resolved. Incident Priority is retired as an independent scale. Event-day incident severity routes through the existing 86.2 Crisis Scale: Level 1 Minor now explicitly carries a “no guest impact” qualifier where applicable, and what Module 16 called Level 2/3/4 (Local/Major/ Critical) map onto Crisis Scale Levels 2/3/4-5 respectively, using 86.2’s existing owner column (Supervisor / Event Director / CEO- executive / CEO plus external authorities) rather than a separate ownership mapping. One severity scale remains canonical in this specification.

# 120. Module 17 — canonical knowledge extraction and reconciliation

Source: “Security, Safety, Privacy & Risk Management.” Status: approved foundation, subject to the CEO decisions listed in Section 11.16. Like Modules 13, 15 and 16, most of Module 17’s mechanics are already canonical elsewhere — risk registers and scoring (Module 11, 81.1-81.4), medical/photography/crowd protocols (Module 11, 83.1/85.1/11.19), guest- information minimisation and channel discipline (Module 5, 29.1-29.3), accessibility and dietary safety (Module 9, 66.2/67.2), vendor access control (Module 7, 50.2), and the Final Walk/five-metre inspection technique (Module 13, 51.1.1). What follows is what remains after that reconciliation.

**DEFINITION A guest can forgive an imperfect flower arrangement. They

will never forget feeling unsafe or exposed. The finest security is

the security the guest barely notices.**

## 120.1 Three dimensions, not one — genuinely new distinction

Safety (protection from accidental harm: fire, structural, medical, food), Security (protection from deliberate harm or unauthorised access: intrusion, theft, targeted threats) and Privacy (protection from information exposure: location, movements, personal data) are named here as three distinct, related concerns for the first time. Modules 5, 9 and 11 each already govern one or two of these individually, but nothing before this module stated that all three must be managed together as facets of the same protection function rather than as separate departmental concerns. Adopted directly as standing doctrine.

## 120.2 The four-part protection model — genuinely new organising frame

People, Place, Information, Reputation. This is a higher-level organising layer above the existing, more granular Module 11 risk categories (80.4: Guest, VIP, Venue, Production, Power, Weather, Transport, Catering, Security, Protocol, Reputation, Vendors, Technology, Programme) — every one of those fourteen categories maps onto one of these four layers (e.g. Weather/Power/Venue -> Place; Vendors/Catering -> People; Protocol/Reputation -> Reputation). Adopted as the top-level classification; the existing fourteen categories remain the working list beneath it.

## 120.3 Access zoning — genuinely new, complementary to the existing zone plan

Zone 1 (Public/Guest) through Zone 4 (Highly Restricted — Principal/VIP/ sensitive operations) classifies space by who may enter. This is a different axis from Module 9’s existing zone plan (65.1: Entrance/ Reception/Ballroom/Dining/VIP/Restrooms/Departure), which classifies space by what service capability is required there. The two overlap physically (the VIP zone in 65.1 sits inside Zone 4 here) but answer different questions and are both retained: 65.1 tells staff what to do in a space, this tells staff and security who may be in it. The principle of least access (17.13) is the physical-space instance of the data-minimisation principle already established for guest information (Module 5, 29.1) and vendor information-sharing (Module 7, 52.3) — one discipline, now applied to people as well as data.

## 120.4 Authority matrix and its boundary against the Family Decision Owner — resolved (M17-D01)

Module 17’s authority matrix (who can approve access, who can override, who cannot override) is new and valuable, but it must not be confused with the Family Decision Owner model resolved for Module 15 (115.1). These govern different things and use different authorities: the Family Decision Owner (or Event Director fallback) decides ordinary guest-experience matters — seating, social arrangements, family disputes over comfort or precedence. Security access is never within that person’s authority. “I’m family, let me through” at a restricted zone is answered by the Security Lead or Event Director per this module’s authority matrix, not by the Family Decision Owner, and not informally by the CEO (17.56: “your leadership message should be ‘follow the agreed protocol unless formally escalated’” — directly reinforcing the existing CEO-should-not-personally-intervene doctrine at 86.1 and 16.6/119.1).

Resolved. The default Security Override Authority is the Security Lead for the event, named on the Master Event File the same way a Family Decision Owner is named. If the Security Lead is unreachable, authority falls back to the Event Director (76.2 Level 4), never informally to family or the CEO. This closes M17-D01.

## 120.5 The lost child protocol, and the full child-safeguarding policy — resolved (M14-D07)

Module 9 (70.5) and Module 14 (107.2, M14-D07) both already flagged that child safeguarding was missing from this specification entirely. Module 17’s Lost Child Protocol (who receives the report, who searches, who controls exits, who contacts guardians, who communicates with security, who closes the incident — locate quickly without creating panic) is adopted directly as the incident-response half of the policy. The two pieces that were still missing — guardian-authority verification and photography-of-minors consent — are resolved here to close M14-D07 in full.

### 120.5.1 Guardian-authority verification

Every minor attending is linked to one named Responsible Adult (parent, guardian, or an adult the guardian has explicitly delegated to, e.g. a nanny or family member), captured at RSVP (Section 111) as part of the existing Minor guardianship record (Section 5). This is the child-specific instance of the one-accountable-owner doctrine already used for VIPs (30.1) and Family Decision Owner matters (115.1): a minor’s welfare on-site is never “everyone’s responsibility.” Two operational rules follow directly:

- Release rule: a minor is released only to their verified Responsible Adult (or a delegate with recorded evidence of delegation) — never to any other family member simply asserting a relationship, mirroring the discipline already established at 120.4 for security overrides generally.

- Two-person rule: no single member of staff is ever alone with an unaccompanied minor (during a lost-child search, in a designated children’s area, or otherwise); this is a hard operational control, not a judgement call, and applies regardless of how trusted the staff member is.

### 120.5.2 Photography and content consent for minors

Unlike the general adult guest photography position (85.1, where the default is contextual and event-specific), photography or publication of a minor defaults to no consent rather than implied consent: explicit guardian opt-in is required before a minor may be photographed beyond incidental, non-identifying background presence, and separately before any image is shared or published. This is captured on the Minor photography consent record (Section 5), linked to the same Responsible Adult who verified guardianship. Photographers and content vendors are briefed on which minors (if any) are cleared, at what scope, per the existing vendor-briefing discipline (Module 13, 48.5) — a photographer is not exempt from this because they hold professional equipment.

### 120.5.3 Scope of this closure

This closes M14-D07 as an operational safeguarding policy for private events where children attend as guests alongside family — the scope this specification has addressed throughout. It does not constitute, and should not be mistaken for, the separate legal/ regulatory undertaking required if Maison Doclar ever operates a standalone supervised childcare/creche service (background-checked dedicated staff, jurisdiction-specific child-protection licensing, mandatory reporting obligations) — that would be a new service line requiring its own legal review, not a gap in the policy closed here.

## 120.6 The security audit scorecard — new, distinct from the vendor scorecard

Module 17’s post-event security scorecard (access control, guest safety, VIP protection, medical readiness, fire readiness, vehicle management, privacy, vendor control, emergency response, communication — scored /10) assesses a different subject than the canonical Supplier scorecard (resolved at M13-D01): whole-event security posture, not one vendor’s performance. This does not conflict with that resolution and is adopted as a new object in its own right, feeding the same after-action review process already established at Module 11 (87.1).

## 120.7 Everything else — reconciled directly, no new object

The risk management cycle (17.4) is Module 11’s existing risk-and- recovery discipline (81.1-81.4, 87.4) under different labels. The risk register (17.6) and risk priority matrix (17.8) are the existing Risk register entry (Section 5) and 1–5 probability x impact score (81.2) at coarser resolution. The “what if” exercise (17.9) is the existing Risk Walk (81.1) reframed as rehearsal. The white-glove security language table (17.18) draws on the same canonical service-language table (64.2). The emergency command structure (17.22) is the existing Incident/Crisis Commander model (8.0.4, 8.0.5). Medical preparedness and the medical privacy principle (17.24-17.25) restate Module 11’s medical protocol (83.1) and crowd-around-a-medical-incident guidance (11.19) directly. Elderly/accessibility guidance (17.26-17.27) restates Module 9’s accessibility boundary (66.2). Catering/allergy safety (17.31-17.32) restates Module 9’s dietary chain (67.2). The security walk-through and 360-degree view (17.49-17.50) is Module 13’s Final Walk/five-metre test (51.1.1) applied to security specifically. Photography/privacy content (17.38-17.41) restates the existing photography policy (85.1), Module 13’s Partner Code (48.5) and Module 14’s staff social-media rule (105.3). The security incident communication chain (17.57-17.60) and “never speculate” discipline restate the one-voice principle (85.2) and verified-information standard already established. The three-questions- after-an-incident method (17.62) restates the existing Five Whys (87.2). None of these create new objects or new decisions.

# 121. Decisions supported by Module 17

Module 17 supplies: the safety/security/privacy three-dimension doctrine; the people/place/information/reputation organising frame; access zoning as a complement to the existing service zone plan; the authority-matrix boundary against the Family Decision Owner; the lost child protocol; and the security audit scorecard.

## 121.1 Decisions outside Module 17 authority

The operational child-safeguarding policy is now resolved (120.5, M14-D07). What remains outside this module’s (and this specification’s) authority is the separate legal/regulatory undertaking for a standalone childcare/creche service, should Maison Doclar ever operate one (120.5.3). Specific venue fire-code, electrical-safety and structural- hazard compliance require jurisdiction-appropriate qualified sign-off, not general hospitality judgement, consistent with the existing safety-override doctrine (82.3).

# 122. Module 17 relationships, exclusions and gaps

## 122.1 Relationship to Modules 1–16

Module 17 is the fourth consecutive heavily-reconciled module. Its lasting, genuinely new contributions are the three-dimension safety/security/privacy doctrine, the four-part protection organising frame, access zoning, the authority-matrix/Family-Decision-Owner boundary, the lost child protocol, and the security audit scorecard. Everything else in the module restates existing Module 5, 7, 9, 11 or 13 content and is reconciled rather than duplicated (120.7).

## 122.2 Exclusions applied

The Module 17 CEO Master Assignment (300-person Lagos chieftaincy celebration security and risk plan) is excluded per the standing rule.

## 122.3 Explicit gaps identified

- (Resolved, M14-D07) Child safeguarding remained only partially addressed. Closed via guardian-authority verification and minor photography consent (120.5); the separate legal undertaking for a standalone childcare service, if that ever becomes a Maison Doclar service line, remains a distinct future item (120.5.3).

- (Resolved, M17-D01) The Security Override Authority was not named for any specific event. Default is now the Security Lead, Event Director as fallback (120.4).

- No jurisdiction-specific fire-code, electrical-safety or structural sign-off process is defined (121.1) — consistent with how this specification consistently defers regulated-safety matters to qualified authority rather than generalist judgement.

# 123. The cross-event knowledge base — resolved (M12-D07)

Source: CEO-directed design, resolving the gap first identified at 95.3 and independently reinforced by Modules 15 (116.2) and 16 (16.63-16.65). This is not a new module; it is a cross-cutting architecture decision closing the specification’s single largest outstanding item.

**GOVERNING PRINCIPLE Privacy segregation is not a feature added to

the cross-event knowledge base. It is the constraint the architecture

is designed around.**

## 123.1 Two of five subjects already have this architecture

Cross-event knowledge accumulates around five subjects: Vendor, Guest/ VIP, Venue, Protocol Pattern, and Risk/Incident Type. Checking each against what already exists in this specification:

- Vendor — already built. The Supplier organisation record (Section 5) is a persistent identity, not event-scoped, and Supplier scorecards already accumulate against it event after event. What was missing is not the registry — it is the rule for whether one client’s scorecard evidence may inform a recommendation shown to a different client (123.3).

- Guest/VIP — already built, and deliberately excluded from cross-client sharing. The Reusable VIP memory model (29.4) is already a full cross-event knowledge lifecycle for guests — Event- only, Candidate, Approved reusable, Stale/disputed, Restricted archive, Deleted/anonymised. It exists to serve that guest better wherever they appear again, not to generate market intelligence about guests in general. Named or identifiable guest information stays out of the cross-client-queryable layer entirely; only fully de-identified, sufficiently-aggregated behavioural patterns (123.4) are eligible, and the identifiability bar for those is deliberately higher than for venue or vendor facts.

- Venue — not yet built. The existing Venue data entity (Section

  - captures physical facts, but nothing distinguishes “facts about this building, true across every event held there” from “facts about this one event.” A persistent Venue Identity record is introduced below (123.2) to close this.

- Protocol Pattern and Risk/Incident Type — not yet built. Neither has a persistent registry; recurring situations (a precedence conflict type, a recurring weather/power failure mode) currently live and die inside individual After-Action Reviews (87.1) with no mechanism to notice they have happened five times. A lightweight Pattern Library is introduced below (123.2) for both.

## 123.2 New registries

- Venue Identity record: venue name/location; physical facts stable across events (capacity, access points, power infrastructure, parking, accessible routes); accumulated evidence references (internal only); known limitations; last verified date. Distinct from the existing per-event Venue entity, which continues to record that event’s specific configuration.

- Pattern Library entry (Protocol Pattern or Risk/Incident Type): pattern name; subject type; description; triggering conditions; accumulated evidence references (internal only); recommended response/mitigation; confidence (rises with repeated observation); source After-Action Reviews.

Both follow the same Proposed/Approved/Provisional/Superseded/Rejected knowledge states as everything else in this specification (1.1) — neither is created from a single event’s evidence.

## 123.3 The cross-client sharing rule — the actual missing piece

Every existing per-subject mechanism (vendor scorecards, VIP memory, After-Action Reviews) already governs reuse within its own lane. None of them answers the one question that matters for a genuine knowledge base: may a fact learned on Client A’s event inform a recommendation made to Client B? This reuses the VIP three-level information model (29.2) as a general privacy-tier framework, applied to every subject:

| Tier | Meaning | Cross-client rule |
| --- | --- | --- |
| Level 1 — Service | An operational fact about a place, vendor or recurring pattern, not about a specific guest or the private character of an event (e.g. “generator undersized for 400 guests”) | Eligible for the cross-client-queryable index once approved |
| Level 2 — Confidential | Tied to a specific event’s private character even if it also touches a venue or vendor (e.g. what a family dispute revealed about a venue’s layout) | Never enters the cross-client index; remains inside its originating Master Event File |
| Level 3 — Restricted | High-sensitivity guest, security or personal circumstance information | Never enters the cross-client index |

A single event can produce facts at more than one tier about the same subject — a venue can generate both a Level 1 fact (“insufficient generator capacity”) and a Level 2 fact (“the family argued near the garden entrance”) in the same evening. Only the Level 1 fact is eligible for promotion; the Level 2 fact stays inside that Master Event File permanently.

## 123.4 The promotion path

No fact enters the cross-client-queryable layer automatically. The path mirrors the existing SOP promotion path (96.1): a candidate fact surfaces from an Outcome record, Supplier scorecard, or After-Action Review -> the Knowledge Base Curator (already named at 8.0.6) assesses privacy tier and evidentiary strength (a single event is a candidate, not a pattern; repeated corroborating evidence is required, per Module 11’s near-miss discipline at 87.1) -> approved entries enter the Venue Identity record, Pattern Library, or Vendor’s cross-client-visible summary -> entries remain versioned, reviewable and revocable, never silently rewritten.

For guest-behaviour patterns specifically (123.1), promotion additionally requires aggregation across enough distinct events/guests that no individual is identifiable — a materially higher bar than for venue or vendor facts, consistent with the Golden Privacy Rule already established for VIP data (29.1).

## 123.5 Query and access governance

Cross-client-visible knowledge (Venue Identity, Pattern Library, Vendor’s Level-1 summary) is queryable by role-appropriate staff across any event, following the same dashboard access-view discipline already established at 8.1. Anything still inside a single Master Event File (Level 2/3 facts, unapproved candidates) is visible only to that event’s authorised team, exactly as today. The Knowledge Base Curator holds sole authority to move a fact from one visibility state to the other.

## 123.6 Knowledge Base Curator — fully specified

Extending the role already named at 8.0.6: the Curator reviews candidate facts against the tier table (123.3), rejects or holds anything that could identify a guest, family or the private character of an event, requires corroborating evidence before treating a single incident as a pattern, and maintains the audit trail proving why each cross-client- visible entry was admitted. The Curator cannot be the same person who generated the evidence for a given event (an Event Director cannot approve their own event’s lesson into the cross-client layer) — a second-person review requirement, consistent with how this specification treats every other high-consequence approval.

## 123.7 What remains outside this specification

The actual database/technology implementation, specific data-retention periods, and — the one genuinely open legal question — whether existing or future client contracts need explicit language permitting Maison Doclar to derive de-identified operational learning from their event for use elsewhere. This specification sets the policy the implementation must satisfy; it is not the implementation, and the contract-language question should go to counsel before the Venue Identity registry or Pattern Library holds its first entry.

# 124. Module 19 — canonical knowledge extraction and reconciliation

Source: “Staffing, Service Culture & the Maison Doclar Guest Experience Team.” Status: approved foundation, subject to the CEO decisions listed in Section 11.18. Module 19 shares its title almost exactly with Module 14 and substantially overlaps it — team architecture, recruitment criteria, presence/language standards, escalation, empowerment and culture-building are already canonical via Sections 99–107. This extraction focuses on what genuinely closes gaps Module 14 itself flagged as blind spots (107.2), since that is where this module earns its place.

## 124.1 Reconciled directly, no new content

Team architecture and hierarchy (100.1); recruitment for character (101.1); presence, body language, voice and service-language standards (64.1-64.2, already reconciled three times over); the “no-wrong-door” warm handoff (103); staff briefing content and the five-minute huddle (102.1); the staffing/positioning grid and Floating Concierge (102.3); VIP one-owner staffing and VIP-Host-versus-Security boundary (30.1, 120.4); escalation solve-versus-escalate guidance (100.3, reconciled to 76.2); empowerment and discretionary authority (104.3); “never blame a colleague in front of the guest” and staff composure under pressure (64.1, 86.1); and the culture-building/recognition/accountability mechanism (104.1-104.2). Module 19’s four-step recovery sequence (Acknowledge -> Own -> Act -> Follow up) is the canonical 68.1 sequence with “Listen” implicit and “Act” meaning “Solve” — not a new model, on the same precedent as the Module 16 and Module 15 recovery-sequence reconciliations. Its “10-second rule” for noticing guest uncertainty is the same concern as the already-resolved 5-second acknowledgement target (64.1, M14-D01) and does not reopen that decision.

## 124.2 Small genuine enrichments, folded into existing sections

- The five staffing questions (what must happen, where, when, what judgement level, what if the person is unavailable) sharpen the existing “staffing follows function” principle (99.1) with a concrete checklist.

- The Staff Quality Triangle (Competence, Character, Composure) is adopted as a memorable hiring frame alongside the existing character-before-cosmetics doctrine (101.1) — not a new criterion, a better mnemonic for the same one.

- A fourth hiring diagnostic — “tell me about a time you noticed someone needed help before they asked” — is added to the three situational tests already at 101.2 (upset-guest, proactive-service, discretion) as a behavioural/past-experience question rather than a situational one; both formats have value and neither replaces the other.

- Task Staff / Service Staff / Hospitality Professional is a three-bucket compression of the existing five-level staff maturity model (104.4): Task Staff spans Instruction/Competence, Service Staff maps to Awareness, Hospitality Professional spans Anticipation/Judgement. Adopted as a simpler communication shorthand for the same model, not a second one.

- Reading the guest / personality matching (conversation, efficiency, privacy, or guidance — appropriate interaction, not maximum interaction) is genuinely new doctrine, not previously stated, and is adopted directly as a guest-facing behaviour standard alongside 64.1.

- Difficult-guest diagnostic questions (is this actually confusion, delay, embarrassment, lack of information, physical discomfort, or perceived disrespect) sharpen the existing complaint-type taxonomy (84.2) with concrete underlying-cause prompts.

- Staff-to-guest ratio is confirmed as explicitly not universal — a cocktail reception and a seated ceremonial dinner for the same headcount need different staffing — reinforcing rather than replacing the existing zone-plan/positioning-map approach (65.1, 102.3).

## 124.3 The relief principle and handover standard — new, partial progress on M11-D08

Every critical guest-facing position requires relief coverage, not just breaks in general — if someone needs to step away, the position, not just the person, must remain covered. Handovers between shift changes follow a Handover Standard: what happened, what is happening, what needs to happen next — covering important guests, outstanding requests, problems and pending arrivals. This is a genuinely new object (Handover record, Section 5) and gives the wellbeing gap first flagged at Module 11 (M11-D08: “no rotation, rest or supervision standard specified”) a real mechanism. It remains partial: relief and handover discipline is now defined, but numeric standards (shift length, break frequency, maximum consecutive hours) are still not set anywhere in this specification.

## 124.4 Training versus briefing, and rehearsal — new, partial progress on M14-D04

Module 19 draws a distinction Modules 1–18 had not made explicit: briefing communicates today’s requirements; training builds capability and cannot be substituted by a briefing, however good. Pre-event training content areas (guest service, protocol, security awareness, privacy, service recovery, venue, role, escalation, special sensitivities) and, more valuably, rehearsal by role-play — nine named scenarios (VIP early arrival, guest cannot find their table, dignitary seating conflict, angry guest, elder needing assistance, separated child, guest requesting restricted access, VIP requesting privacy, client changing a programme element) — are adopted directly. This is real progress on the training gap first flagged at Module 9 (70.5) and restated at Module 14 (M14-D04): it defines what training should cover and how to rehearse it. It does not fully close M14-D04: curriculum design (who builds the material, how often it is refreshed) and a certification/expiry tracking system remain undefined — though the Staff Talent Record introduced below (124.6) is the natural place that tracking would eventually live.

## 124.5 The Staff Performance Scorecard — new, distinct from the vendor and security scorecards

Module 19’s post-event staff assessment (presentation, warmth, composure, discretion, initiative, communication, protocol, guest awareness, reliability, overall — scored /10) is a genuinely new object: neither the existing per-standard competency states (69.1, pass/ fail against one behaviour) nor the recognition/accountability entry (104.2, incident-based) aggregate a person’s whole-event performance into one scored record. This does not conflict with the canonical Supplier scorecard (52.5) or the Security Audit scorecard (120.6) — three different subjects, three different instruments, each already flagged in the AI boundary (8.1) as not to be confused with one another. Adopted as a new data entity (Section 5).

## 124.6 The Staff Talent Record — new, partial progress on M14-D05

Module 19’s “Human Database” (skills, languages, experience, events worked, performance, strengths, training, availability, preferred deployment) is, for Maison Doclar’s own people, the same architectural pattern already built for venues and vendors at Section 123: a persistent identity that accumulates evidence across events, rather than each event starting from zero. This is adopted as the Staff Talent Record (Section 5) — a genuinely new object, not a restatement, and real progress on the M14-D05 gap (“ongoing performance management and career progression… neither addresses performance review cadence, promotion, retention or compensation growth over time”). Staff Performance Scorecards (124.5) accumulate against it event after event exactly as Supplier scorecards accumulate against a Supplier organisation record. It remains partial: the record now exists and can hold the evidence, but a defined review cadence (how often a formal review happens, independent of any one event), promotion criteria and compensation-progression policy are still not specified anywhere in this specification — those are HR-policy decisions, not data-architecture ones, and belong to M14-D05 as it now stands (124.7).

## 124.7 Updated status of the Module 14 blind-spot list

Of the eleven items at 107.2, this module makes genuine partial progress on three and leaves the remaining eight untouched — they still require HR, legal or regulatory ownership this specification cannot supply on its own, and are consolidated with clear status here so the CEO does not have to reconstruct this list from memory across five modules:

| Item * | *Status after the Staffing Policy Framework (142)** |
| --- | --- |
| Recruitment sourcing/ vetting (M14-D02) | Resolved in design (142.3, Provisional pending counsel sign-off). Vetting Record added. |
| Employment classification/ labour law (M14-D03) | Resolved (142.2). The control test is binding policy effective immediately, not contingent on counsel sign-off. |
| Training curriculum/ certification tracking (M14-D04) | Partial. Content areas and rehearsal method now defined (124.4); curriculum design and certification-expiry tracking still undefined |
| Performance cadence/career progression (M14-D05) | Partial. Persistent record now exists (124.6); review cadence, promotion and compensation-progression policy still undefined |
| HR disciplinary/grievance process (M14-D06) | Resolved in design (142.6, Provisional pending counsel sign-off). Disciplinary Record added. |
| Safeguarding for minors (M14-D07) | Resolved at Module 17 (120.5), not by this module — noted here only for a complete picture. |
| Staff personal-data privacy (M14-D08/M19-D01) | Resolved in design (142.5, Provisional pending counsel sign-off). Lawful basis, retention table, breach protocol now defined. |
| Compensation/payroll/ overtime (M14-D09) | Resolved in design (142.4, Provisional pending counsel sign-off and current-rate confirmation). |
| Staff insurance/liability (M14-D10) | Resolved in design (142.7, Provisional pending counsel sign-off). |
| Work authorisation for international deployment (M14-D11) | Resolved in design (142.7, Provisional pending counsel sign-off). |
| DEI in hiring (M14-D12) | Resolved in design (142.8, Provisional pending counsel sign-off). |

Direct recommendation, updated: seven of the eight items now have a designed policy rather than no policy — but “resolved in design” is not “resolved.” Every item marked Provisional above requires the same next step: qualified Nigerian employment counsel review and sign-off (142.9). Two items remain genuinely undesigned (training curriculum ownership and performance-review cadence) and still need HR ownership beyond what this specification can supply. Recommend engaging employment counsel this week for the Provisional items and treating the two Partial items as the next design task, rather than letting either wait for a future module to restate them again.

# 125. Module 20 — canonical knowledge extraction and reconciliation

Source: “The Maison Doclar Event Command Centre.” Status: approved foundation. This is the fourth command-centre module (after Modules 6, 10 and 16) and, like Modules 13/15/18/19 before it, is reconciled rather than duplicated. Its command hierarchy, Command Centre criteria, master timeline/live clock, event-status RAG, Command Board, issue/decision logging, radio format, VIP/vendor/transport/weather/power feeds, transitions, cascade effects and crisis sequence are all already canonical via Sections 37–45, 71–79, and 119. Four items are genuinely new and adopted directly:

- Information / Alert / Decision / Incident as an explicit message-priority taxonomy for anything entering the Command Centre — not previously named this way, and directly useful for the AI layer designed below (Section 127).

- Reversible versus irreversible decisions get different speed treatment — a reversible call (move a table) can be made fast; an irreversible one (cancel a ceremonial element) earns more deliberation. This is adopted as a genuine refinement to the “good-enough information” doctrine already at 119.1 (the Module 16 “80% decision rule”). Module 20 proposes “70%” for the same underlying idea — neither number is a measured target in either source module, so no new numeric conflict is created; the qualitative principle (act on sufficient information, calibrated by reversibility) is canonical and the percentage is illustrative rhetoric in both cases, not a value to reconcile.

- The client decision format (“we have X, our recommendation is Y because Z, please confirm”) sharpens the existing client-briefing formula (85.3) with an explicit rule: never present a problem to the client without a recommendation attached.

- Red-line moment countdown (T-60/T-30/T-15/T-5/T-0/T+5) is a tighter-grained version of the event-wide T-180…T-0 rhythm (42.0), scoped to one critical moment rather than the whole event. Adopted as a second, nested countdown for red-line moments specifically.

Module 20’s “Event Intelligence Database” and “Power of Patterns” (20.74-20.77) describe, independently, exactly the cross-event knowledge base already fully designed at Section 123 — the fourth module to converge on that same design from a different angle. No new gap; strong confirmation that Section 123 was worth building. Its AI sections (20.81-20.84) are the CEO’s own prompt for the design that follows.

# 126. The Maison Doclar AI Layer — operating philosophy

This section directly answers the CEO’s brief: incorporate AI as fully as is responsible, using the Anthropic API, grounded in this specification’s own knowledge base, never hallucinating, and without fanciful claims about 2026 capability.

## 126.1 Reframing “CEO-level decisions”

The brief asked for AI that makes CEO-level decisions. This is reframed, deliberately, to CEO-level situational synthesis and recommendation quality — not decision authority — and the reason is worth stating plainly rather than silently substituted. Every AI boundary rule already written into this specification (over sixty of them, Section 8.1) says the same thing in different contexts: AI may identify, rank, explain and recommend; a named, accountable human decides anything consequential. That pattern was not arbitrary caution accumulated by accident — it reflects what a language model actually is in 2026: a system that generates the statistically likely continuation of text, extremely capable at synthesis, extraction and drafting when grounded in real data, but with no ground-truth access to reality except what it is given, no legal or moral accountability, and a real, irreducible tendency to produce fluent, confident, wrong answers when it lacks grounding. Giving it CEO decision authority would not make Maison Doclar an “event intelligence company” — it would make it a company whose most consequential decisions are made by something that cannot be held responsible for them. The design below gives AI the largest responsible role this specification can support: full authorship of situational awareness, full authorship of draft recommendations and draft communications, and zero authority to commit Maison Doclar to anything without a named human’s confirmation. This is not a lesser ambition than “AI makes CEO decisions” — it is the version of that ambition that actually survives contact with a real event.

## 126.2 What “grounded in the knowledge base” means concretely

AI reasoning in the Command Centre draws only from: the Master Event File and its linked Section 5 data entities for the live event; the approved doctrine in Sections 1–124 of this specification; and the cross-event knowledge base (Section 123) at the privacy tier the querying role is entitled to see (8.1’s existing access-view discipline). It does not draw operational facts from general training knowledge, the open internet, or plausible-sounding inference presented as fact. If a fact is not in one of those three sources, the correct AI output is “not available in the knowledge base” — stated as such, not inferred, not estimated, not filled in from a similar-sounding pattern. This is the single most important mechanism against hallucination in this design, and everything in Section 128 elaborates it.

# 127. Where AI sits in the command loop

The existing command loop (Observe -> Interpret -> Decide -> Act -> Verify, 74.1, reconciled with Module 16’s version at 119.1) is the frame. AI’s role is mapped precisely onto it, stage by stage, rather than left ambiguous:

| Stage | AI role |
| --- | --- |
| Observe r c - V A r e r | Full authorship. Structured extraction from incoming eports (radio transcripts, WhatsApp messages, vendor heck-ins, guest requests) into the existing data entities – Issue, Incident, Risk register entry, Vendor status, IP board entry — classified by the new Information/ lert/Decision/Incident taxonomy (125). This is pattern ecognition and structured formatting of text that already xists; it is not judgement, and is where AI is most eliable |
| Interpret a c d c a ( s | Full authorship, with mandatory citation. Synthesis cross current data (“what does this mean”) — e.g. ombining a VIP-delay report with the master timeline and ependency graph (50.1) to identify a likely programme ollision. This is constraint-checking against data lready in the system, not prediction of the future 126.3 addresses this distinction explicitly). Every ynthesis output cites the records it drew from |
| Decide ( m d ( - d | Draft only. AI may propose options with reasoning structured against 76.3’s consequence-prioritisation odel) and a recommended option, exactly as it already rafts vendor recommendations (52.3) and client updates 85.3). It does not select the option that gets acted on – the named authority at the correct 76.2 ladder level oes |
| Act r a h b o s p | No authority. AI never sends an external message, eleases a payment, activates a contingency, overrides ccess, or commits Maison Doclar to anything without a uman confirming the specific action. This is the same oundary already established individually across dozens f rules in Section 8.1; this table is where they are hown as one consistent pattern rather than scattered oints |
| Verify ( s i r | Full authorship for confirming data-recorded completion e.g. “the delivery-milestone gate shows passed at 14:32, igned by X”) — it may not itself decide that something s actually resolved to the guest’s satisfaction, which emains a human judgement (68.1’s Follow-up step) |
| Learn n ( p p | Draft only, with second-person review. AI may propose a ear-miss, a learning candidate, or a cross-event pattern 123.4) for the Knowledge Base Curator to admit — never romotes one itself, consistent with the existing romotion-path rule |

## 127.1 Honest reframing of “predictive event management”

Module 20’s example (20.83: VIP delayed 18 minutes, system flags a programme collision) is real and valuable — but it is not prediction in the sense of forecasting an unknown future from statistical patterns. It is constraint-checking: the dependency graph (50.1), the critical path (50.4) and the master timeline already contain the facts (ceremony requires the VIP seated, procession requires protocol readiness, photography is scheduled at a fixed point); AI’s contribution is correctly computing that a known delay, propagated through already- known dependencies, produces a known collision. This is squarely within what a 2026 system grounded in structured data can do reliably. Calling it “prediction” invites the wrong mental model (a system guessing at an uncertain future) when the actual mechanism (arithmetic over declared dependencies) is more reliable and more inspectable than that framing suggests — and should be described accurately for that reason.

# 128. Grounding and hallucination-prevention mechanisms

Six concrete, named mechanisms, each mapped to something already established in this specification rather than invented fresh:

## 128.1 Retrieval grounding, no open-domain operational claims

Every operational fact AI states in a Command Centre output must trace to a specific record in the Master Event File, the approved knowledge base, or the cross-event index at the correct privacy tier. This extends the existing Data Rule (Section 5: “a fact without source, verification state, sensitivity and owner is not usable operational intelligence”) from human-entered data to AI-generated synthesis — the same standard, now applied to AI outputs specifically.

## 128.2 Absence is stated, never inferred

Consistent with the Known-Unknown discipline already established (96.3, 8.1): if the knowledge base does not contain a fact, AI states that plainly rather than estimating, assuming a typical value, or inferring from a similar past event. “Not available” is always an acceptable and correct AI output; a confident guess presented as fact is not, regardless of how plausible it sounds.

## 128.3 Three-tier confidence labelling

Every AI-surfaced fact carries one of three labels: Confirmed (directly recorded, source-verified, e.g. a signed readiness gate), Reported (single unverified source, e.g. one radio call not yet corroborated), or Inferred (AI-derived by combining confirmed/ reported facts, e.g. the programme-collision example at 127.1). AI must never present an Inferred conclusion with Confirmed-level confidence. This directly operationalises the “confidence” field already required throughout Section 5’s data entities.

## 128.4 No silent authority assumption

AI never assumes it holds authority it was not explicitly granted for a given output type. This is not a new rule — it is the existing pattern across all sixty-plus AI boundary rules (8.1) stated as a single governing meta-rule: when in doubt about whether an action requires human confirmation, AI treats it as requiring human confirmation.

## 128.5 Draft-then-approve gate

Nothing AI produces becomes an actioned record — a sent message, a logged decision, a released payment, a promoted knowledge-base entry — until a named human confirms it. This is the same second-person-review discipline already required of the Knowledge Base Curator (123.6) and the vendor/security/staff scorecard boundaries, generalised as the default for every AI output in the Command Centre.

## 128.6 Full audit trail

Every AI-drafted output is logged as AI-authored, together with the specific records it retrieved to produce it, so any output can be inspected after the fact against exactly what the AI saw. This extends the existing change-discipline and knowledge-state audit trail (1.1, 1.2) to AI outputs specifically — nothing AI produces is anonymous or unreconstructable.

# 129. AI-assisted Command Centre capabilities

Concrete, realistic capabilities the Anthropic API layer supports in 2026, each mapped to an existing Command Centre object rather than a new one:

- Structured extraction: incoming radio/WhatsApp/vendor-check-in text -> structured Issue, Incident, Risk register, or VIP board entries (Section 5), classified by Information/Alert/Decision/ Incident (125).

- Situation synthesis: on request or at defined intervals, a grounded summary of “what is happening / what is next / what is at risk” (20.0’s own three questions), citing the specific records behind each claim, formatted for the requesting role’s dashboard access level (8.1).

- Dependency/collision checking: constraint-checking against the dependency graph (50.1) and master timeline, surfaced as an Alert when a delay or change would violate a known dependency (127.1).

- Escalation drafting: pre-populating the WHO/WHERE/WHAT/WHEN/ACTION message format (76.1) from a structured Issue/Incident record, for a human to review and send — not composing an escalation from scratch under pressure.

- Decision-option drafting: structuring options against the consequence-prioritisation model (76.3) with a recommended option and reasoning, for the named ladder-level authority (76.2) to choose from.

- Client/executive reporting drafts: populating the STATUS/ISSUE/ ACTION/DECISION format (20.54) and the client decision format (“we have X, recommend Y because Z,” 125) from current Command Centre data, for the Client Communication Lead (8.0.5) to review and send — never sent directly by AI (already an existing rule, Section 8.1).

- Cross-event knowledge surfacing: querying the Venue Identity record, Pattern Library and Vendor cross-client summary (Section

  - to inform a live decision — e.g. surfacing an approved, Level-1 fact that this venue has a known generator-capacity limit — without itself promoting anything new into that layer.

- Post-event drafting: populating the After-Action Review (87.1), Client Debrief (95.2) and Staff/Supplier/Security scorecards (52.5, 120.6, 124.5) from the event’s logged data, for the accountable reviewer to complete and approve.

# 130. What this explicitly does not do in 2026

Stated plainly, because unrealistic claims are as damaging as under-claiming: the AI layer described here does not autonomously perceive the physical world (it has no camera, sensor or GPS access unless a specific integration is separately built and granted); does not make phone calls or take independent real-world action; does not have real-time knowledge of anything outside what this system records or retrieves for it; does not improve at judgement through use the way a person does — it applies the same grounded-synthesis approach consistently, and any apparent improvement over time comes from a better knowledge base (Section 123 accumulating more approved evidence), not from the model itself learning; and does not carry legal, moral or professional accountability for any decision — that remains, permanently, with the named human at the correct authority level. “Using the Anthropic API layer” means calling Claude models for text generation, extraction, synthesis and reasoning over data this system explicitly retrieves and provides — nothing more, and nothing should be represented to the client or the CEO as more than that.

# 131. Architecture and integration point

## 131.1 Placement, not a parallel system

The AI layer is not a separate application. It sits alongside the existing Command Board (38.4), CEO/Client dashboards (75.1-75.2) and Master Event File (92.1), with retrieval access scoped by the same role-based access-view discipline already governing those dashboards (8.1). AI-generated content appears inside those existing views, clearly labelled as AI-drafted with its confidence tier (128.3) and source citations — not as a separate feed a person must additionally monitor.

## 131.2 AI Systems Owner — new governance role

A named role, extending the pattern already established for every other governed capability in this specification (Master Event File Owner, SOP Custodian, Knowledge Base Curator, People/Culture Owner): the AI Systems Owner is accountable for what data and tools the Anthropic API integration can actually retrieve and call, reviews the audit trail (128.6) periodically for grounding failures or boundary violations, and is the only role authorised to change what the AI layer is permitted to access. This role does not gain any of the decision authority described in Section 127 — it governs the AI’s plumbing, not the event.

# 132. Decisions supported and outside authority

This design supplies: the Observe/Interpret/Decide/Act/Verify/Learn mapping of AI’s role (127); the six grounding mechanisms (128); the concrete capability list (129); the explicit 2026 capability boundary (130); and the architecture placement and AI Systems Owner role (131).

## 132.1 Outside this design’s authority

The actual technical implementation (which Anthropic model, context window management, tool-calling configuration, latency/availability requirements) is an engineering decision for whoever builds this system, not a specification-level one. Data-processing and AI-specific regulatory/compliance requirements (if any apply to Nigerian event operations specifically) are a legal question, consistent with how this specification has treated every other regulatory boundary (121.1, 82.3).

# 133. Relationships, exclusions and gaps

## 133.1 Relationship to Modules 1–19

This design does not introduce new event-operations doctrine — it formalises, as one coherent architecture, a pattern that has been built incrementally across every module since Section 8.1 was first written: AI synthesises and drafts, named humans decide and act. Section 123’s cross-event knowledge base and Section 127’s command-loop mapping are the two pieces of infrastructure this design depends on most directly, and both already existed before this section was written.

## 133.2 Exclusions applied

The Module 20 CEO Master Assignment (500-person command centre build, including the live five-minute crisis scenario) is excluded per the standing rule on CEO exercises and master exercises. It is a strong candidate for the AI shadow-mode evaluation capability already flagged as a gap since Module 10 (79) — once built, this scenario is close to ready-made test data for it.

## 133.3 Explicit gaps identified

- No AI shadow-mode/evaluation capability exists yet to test outputs like the one in the excluded CEO exercise against known-good human judgement before the AI layer is trusted in a live event — this gap was first identified at Module 10 (79) and remains open.

- No specific Anthropic API technical configuration (model selection, tool access list, context window strategy) is defined — deliberately left to implementation (132.1).

- No regulatory/compliance review has been conducted for AI use in Nigerian event operations specifically — flagged, not assumed (132.1).

- (Resolved, M20-D01) The AI Systems Owner role was newly created and not yet assigned. CEO named (8.0.9). Technical build timing (M20-D01’s remaining half) is still open.

# 134. The Consult capability — lead-initiated decision support

CEO-directed design, answering directly: can a functional lead put a problem to the system and get grounded advice? Yes — this is not a new authority beyond what Section 127 already established (AI drafts, humans decide); it is that capability given a name, an interface point, and one safeguard the general design did not yet make explicit: a recommendation must never let the person asking act beyond their own authority.

## 134.1 How a Consult works

Any named role (Event Director, functional lead, VIP Manager, Protocol Lead, Security Lead, concierge variants, and so on) may pose a described problem to the AI layer at any time — this is not limited to live incidents; it works equally for pre-event planning questions. The AI layer:

- Retrieves relevant grounded knowledge — applicable doctrine from this specification, the live Master Event File and its linked data (scoped to what that role’s dashboard access already permits, 8.1), and any relevant cross-event knowledge-base entries at the requester’s privacy tier (Section 123).

- Produces a structured Consult Response: a situation summary with citations, options with reasoning structured against the consequence-prioritisation model (76.3), a recommended option, and a confidence tier per fact used (128.3).

- Tags the response with who actually holds decision authority for this category of matter — the correct 76.2 ladder level, or a specifically named authority where one exists (Family Decision Owner 115.1, Security Override Authority 120.4, Knowledge Base Curator 123.6, Client Communication Lead 8.0.5, and so on).

## 134.2 The authority safeguard

If the requester is the authority holder for that matter, the Consult Response is framed as a ready-to-act recommendation. If the requester is not, the response is explicitly framed for escalation — “this decision sits with [named authority]; here is the recommendation to bring to them” — never phrased as an instruction the requester can execute themselves. This prevents a Consult from becoming a way to informally acquire authority a role was never given: a Protocol Lead asking whether a family member should be allowed past a restricted zone gets a recommendation addressed to the Security Lead, not permission to wave the person through. The AI layer holds no authority of its own to blur here — it is only ever reporting whose authority applies (127, Act row: no authority).

## 134.3 Honest handling of weak or absent precedent

Where the knowledge base has strong, directly applicable precedent (e.g. a Pattern Library entry, 123.2), the Consult Response says so and cites it. Where precedent is thin or absent, the response says that plainly — “the knowledge base has no strong precedent for this specific situation; the closest applicable doctrine is X, but this may need judgement beyond what is recorded” — consistent with the absence- handling rule (128.2). A confident-sounding answer manufactured to fill a genuine gap is exactly the failure mode this specification has been built to prevent; a Consult is not exempt from that discipline merely because a human explicitly asked for help.

## 134.4 Logging

Every Consult is recorded as an AI output record (Section 5, 128.6), extended with the query text, requesting role, and authority tag, so the AI Systems Owner (8.0.9) can review not just what the AI produced but what was asked and by whom — the same audit-trail discipline already applied to every other AI output.

# 135. Module 21 — canonical knowledge extraction and reconciliation

Source: “Event Day Execution — the Art of Making the Complex Look Effortless.” Status: approved foundation. This is a live-execution walkthrough covering ground already built across Sections 42, 51.1.1, 56, 59, 65, 95, and the Modules 9/13/16/20 reconciliations — staff/ vendor arrival control, the guest-ready checkpoint, ceremony readiness, transitions, departure-as-hospitality, and the command loop are all already canonical. Nine items are genuinely new and adopted directly; everything else is reconciled without new content.

## 135.1 Reconciled directly

The Event Day Command Cycle (Check -> Confirm -> Position -> Execute -> Observe -> Correct -> Reset) is the preparation-and-execution framing of the same command loop already canonical at 74.1/119.1 — not a fourth model, the same one applied to a scheduled component rather than an incoming signal. The five-minute response sequence (Stop the damage -> Establish facts -> Assign -> Act -> Verify) is the same pattern as the canonical recovery playbook (68.1) and the Module 11 recovery loop (87.4), on the now-familiar precedent of folding sequence-naming variants into the one canonical model rather than treating each as a new conflict. Staff/vendor arrival control, presentation inspection, back-of-house separation, VIP handoff discipline, ceremony readiness, the five-minute lock (the same mechanism as the existing red-line countdown’s T-5 “lock movement,” 125), seating as precedence-aware architecture, departure choreography, and venue close/vendor close-out are all already canonical (30.4, 50.2, 51.1–51.2, 56.2–56.3, 63.3, 95.1, 102.1). The Event Day Formula (Prepare -> Position -> Anticipate -> Execute -> Monitor -> Correct -> Transition -> Close -> Learn) is a restatement of the same operating rhythm under a ninth label, not a new one.

## 135.2 Genuine enrichments, adopted directly

- The four states (Planned -> Ready -> Live -> Complete) are adopted as a lightweight, universal status field usable for any event component that does not already have its own more detailed state machine (e.g. Vendor appointment’s eight-state model, 48.2, remains authoritative for vendors specifically; this is the simple default for everything else).

- T-24/T-12/T-3 discipline (discover problems at T-24, resolve by T-12, execute at T-3) is adopted as the operating rule behind the new T-24 readiness checkpoint (42.0).

- Guest arrival surge monitoring — distinguishing normal arrival pressure from operational overload by watching vehicle rate, queue length and reception capacity together — is adopted as an enrichment of the existing guest-flow monitoring discipline (13.4).

- “I have it,” then act is adopted as the approved first response when a client raises a problem directly during the event — a concrete script for the existing don’t-transfer-anxiety doctrine (85.4).

## 135.3 The Energy Curve and the Guest Experience Pulse — new

Nothing before this module named the emotional arc of an event as something to be deliberately designed and monitored, distinct from its operational status: arrival, anticipation, ceremony, celebration, peak, social relaxation, departure. This is adopted as new doctrine, complementing rather than replacing the experience-design work already done at Module 1 (the five-layer experience model) — that work designs the intended experience; the Energy Curve is the live check that it is actually landing. The operative question, asked periodically through the event, is “is the room alive?” — not loudness, but engagement, comfort and emotional connection. This is formalised as the Guest Experience Pulse: a periodic Green/Amber/Red assessment across arrival, comfort, information, flow, service, programme, dining, VIP experience and departure (measuring experience, not task completion — 21’s own distinction, “the room is ready” versus “the room feels right”), sitting alongside the existing Command Board (38.4) as the experience-specific counterpart to its operational status view.

## 135.4 The Three-Level Imperfection Test — new triage lens

Level 1 (Invisible — guest never notices, do not overreact), Level 2 (Noticeable but recoverable — correct discreetly), Level 3 (Material — immediate intervention). This is genuinely new and distinct from the existing severity scales (86.2 Crisis Scale, 81.2 risk score): those answer “how severe is this,” calibrated for escalation; this answers “is this even worth intervening on,” calibrated for triage during a live event where dozens of small imperfections may appear simultaneously and reacting to all of them is itself a failure mode. Adopted as a companion lens, not a competing scale — a Level 3 imperfection is where the Crisis Scale/risk model then takes over.

## 135.5 Lost property — new record

Item, location found, time, finder, storage, handover. Nothing before this module formalised lost property as a controlled record rather than informal handling; adopted as a new data entity (Section 5).

## 135.6 The Event Score — new, built as a roll-up

Module 21’s post-event score (Guest Experience, VIP Management, Protocol, Operations, Production, Vendor Performance, Staff Performance, Timing, Security, Client Satisfaction, Overall — /10) is adopted, but deliberately as an aggregate roll-up, not a fifth independent scoring exercise: its Vendor Performance figure is computed from that event’s actual Supplier scorecards (52.5), its Staff Performance figure from that event’s Staff Performance scorecards (124.5), and its Security figure from the Security Audit scorecard (120.6) for that event, rather than being separately eyeballed. Guest Experience, VIP Management, Protocol, Operations, Production, Timing and Client Satisfaction are new whole-event dimensions this scorecard family did not previously cover and are scored directly. This is the fourth /10 instrument in this specification (alongside Vendor, Security, Staff) and is explicitly distinguished from all three in the AI boundary (Section 8.1) on the same precedent as the earlier three-scorecard distinction.

# 136. Module 22 — Service Recovery & Guest Psychology — canonical extraction and reconciliation

Source note: the supplied document’s internal numbering labelled this “Module 21,” conflicting with the already-integrated Module 21 (Event Day Execution). It is treated here by delivery sequence, as Module 22, per the CEO’s request to review it carefully for overlap — which was well-founded: this module is heavily reconciled against the canonical recovery playbook (68.1), the angry-guest/complaint doctrine (84.2), Module 11’s Five Whys (87.2) and Service Recovery Ledger (87.3), and Module 15’s recovery messaging (114.4). Five items are genuinely new.

## 136.1 Reconciled directly

The five-step sequence (Acknowledge -> Own -> Stabilise -> Resolve -> Follow up) is the canonical playbook (68.1) with “Stabilise” folded in as the same concept as Module 11’s “stabilise first, diagnose second” (82.2) — not a sixth competing sequence, on the now-established precedent for these variants. The angry-guest framework, “never win the argument,” dignity-before-logistics, the VIP one-owner recovery principle, “never make the VIP repeat themselves,” the three-phase protocol recovery (Protect -> Correct -> Learn, the same shape as the existing precedence conflict-resolution sequence at 16.5), client recovery doctrine, the crisis-communication “facts before narratives” principle, and root-cause/Five Whys are all already canonical. The “five variables of recovery” (Time, Visibility, Dignity, Importance, Consequence) is the recovery-specific simplified subset of the fuller consequence-prioritisation model already at 76.3, not a new model.

## 136.2 Genuine enrichments, adopted directly

- Uncertainty is often worse than delay. A five-minute wait with clear communication (“we’re preparing your room now, ready in ten minutes, I’ll come back personally”) feels smaller than the same wait in silence. Adopted as explicit doctrine, sharpening the existing reassurance-message content (Module 15, 15.30) with the specific mechanism: manage uncertainty, not only time.

- “But” cancels the apology. “I’m sorry you waited, but the driver…” undoes the acknowledgement it follows; “I’m sorry you waited. Let me resolve the next step for you” preserves it. Adopted as a specific rule within the existing service-language table (64.2).

- The Recovery Pyramid — Recognition, Acknowledgement, Correction, Restoration, Delight — is genuinely new: not a sequence of steps (that is 68.1) but a depth scale for how far a given recovery should go. Not every problem needs Delight; every significant problem needs at least Recognition through Correction. This is adopted directly, with the existing overcompensation caveat (84.3: never manufacture a problem to justify a Delight-level recovery) carried forward unchanged — the source module makes the same point independently (“do not train guests to believe every complaint produces a reward”), which is corroborating, not new.

- Hidden complaint detection and neglect recovery. A guest who says “it’s fine” while their body language says otherwise, and — more dangerously — a VIP who simply concludes “they don’t value me” and never complains at all, is a genuinely distinct failure mode nothing before this addressed. The recovery technique matters as much as the detection: quietly assign a senior host to restore orientation, comfort and attention without making the guest feel “everyone suddenly knows I complained” (which would itself be a second, compounding failure). This connects directly to the Guest Experience Pulse (135.3) — periodic Green/Amber/Red assessment is precisely the mechanism that catches a guest who never says anything.

- The Recovery KPI set — time to acknowledge, time to assign, time to resolve, repeat complaints, VIP incidents, unresolved issues, guest recovery satisfaction, root causes — is adopted as the measurement framework for the existing Service Recovery Ledger (87.3), which already captures the underlying records but had no named set of metrics to compute from them.

## 136.3 Exclusions applied

The CEO Case Lab (the calm, credible VIP complaint with no corroborating service-log evidence) is excluded per the standing rule on CEO exercises and master exercises. It is a strong candidate for the AI shadow-mode evaluation capability (still open, M20-D02) — a case explicitly designed to have no clean answer is good test material.

# 137. Module 23 — Discretion, Privacy & Information Control — canonical extraction and reconciliation

Delivered in the same document as Module 22 and treated as Module 23 by sequence. Heavily reconciled against Module 5’s information-level model (29.1-29.3, resolved above at 29.2), Module 15’s personalisation-vs- intrusion doctrine (110.1-110.2), Module 17’s four-part protection frame (120.2), and the Family Decision Owner model (115.1). Six items are genuinely new.

## 137.1 Reconciled directly

Information minimisation, need-to-know, “the VIP file is not a gossip file,” never discussing a guest in front of the guest, neutral discretion language, photography-is-not-automatic-consent, the after-event confidentiality rule, the vendor confidentiality extension, and the photographer’s special position are all already canonical (29.1, 48.5, 85.1, 105.3). The “family politics rule” — verify who actually has authority to issue an instruction before acting on it — is not a new principle; it is exactly what the Family Decision Owner model (115.1, resolved at M15-D04) already solves, and its independent appearance here is confirmation that resolution was the right one, not a reason to build a second mechanism. The four-level “Discretion Scale” is reconciled onto the existing three-level information model at 29.2 (above), with General added as a genuine zero-th tier.

## 137.2 Genuine enrichments, adopted directly

- The four dimensions of discretion (Information -> Access -> Behaviour -> Retention) are adopted as a lifecycle frame for privacy specifically — what do we know, who needs to know it, how do we act on it, what do we keep afterward — distinct from Module 17’s four-part protection frame (People/Place/Information/ Reputation, 120.2), which organises risk categories rather than an information lifecycle. Both are retained; they answer different questions.

- Photography consent, distinguished by category, for any sensitive guest — official event photography, informal photography, and social-media publication are not the same permission, and a guest comfortable with one may not be comfortable with another. This sharpens the existing photography policy (85.1) with an explicit three-way distinction it did not previously make. This does not import the minors’ opt-in-by-default rule (120.5.2) — that remains specific to minors; for adult guests generally, 85.1’s contextual, event-specific policy remains the standard, now with clearer categories to apply it to.

- Never disclose a hotel room number or private route — guests should be connected through controlled hotel/protocol channels instead. Adopted as a concrete rule within the existing security- information-minimisation doctrine (17.15/22.26 source material).

- Driver-specific discretion boundary and staff curiosity discipline — a driver’s role is transportation, not intelligence gathering, and staff should not ask guests unprompted personal questions (“where are you staying,” “is it true that…”). Adopted as role-specific instances of the existing discretion doctrine.

- The “how did you know?” response script. When a guest asks how Maison Doclar anticipated something, the approved answer is “we wanted to make sure everything was prepared for you” — not an explanation of the information chain. Adopted directly as the approved phrasing for this specific, previously-unaddressed moment, alongside the existing personalisation-without-intrusion doctrine (110.1).

- Do not overuse the word “VIP.” If every guest is called VIP, the term loses meaning — and, more importantly, guests should not have to overhear their own relative importance being discussed at all. Adopted as a language discipline alongside the existing quiet- privilege doctrine.

## 137.2.1 Module 29 — further reconciliation and two small additions

Module 29 (“The Art of Discretion, Privacy & Confidentiality”) overlaps this section almost entirely. Its eight-part privacy breakdown (Information, Access, Location, Conversation, Images, Digital Data, Association, Behaviour) is not a fifth classification — Location, Conversation, Images, Digital Data and Association are specific instances of Information and Access within the four-dimension lifecycle frame above, not independent dimensions. Its “Four Levels of Information” (Public/Operational/Confidential/Highly Sensitive) is the same model as the Discretion Scale (29.2) under different labels. Its five-zone access model (Public/Controlled/VIP/Principal/Critical) is a finer subdivision of the canonical four-zone model (120.3) — VIP and Principal splitting the existing Restricted zone, Critical mapping to Highly Restricted — available as a subdivision, not a fifth zone model. Need-to-know, information minimisation, the VIP file access segmentation, staff conversation discipline, the photography protocol, vendor/driver/security confidentiality, and the incident-confidentiality Contain/Assess/Escalate/Protect/Document/Review sequence (the canonical recovery pattern again) are all already canonical.

Two points are genuinely useful and adopted directly:

- The Discretion Ladder as a preset bundle, not a new classification. Module 29’s five-level guest treatment scale (Normal/Enhanced/ Restricted Photography/Restricted Access/Highly Confidential Handling) is adopted not as a new data model but as a convenience label: assigning a guest one ladder tier bundles the corresponding settings that already exist separately (which information level applies by default, 29.2; whether photography is restricted, 85.1; which access zone applies, 120.3) into one tag, so a team briefing can say “Level 4” instead of listing three separate settings. It changes nothing about how those underlying mechanisms work.

- Family photograph management and the photo-line problem. Approved groupings, sequence, a named family wrangler and a time limit, decided before the moment arrives, are adopted as concrete content for this specific, previously-unaddressed scenario. Related: recognising when one guest’s photograph with a VIP is becoming a queue of guests waiting for the same, and gracefully transitioning the VIP onward before it does — the same “smallest effective intervention” and graceful-exit doctrine already established (25.21, 139.2) applied to this specific moment.

## 137.3 Exclusions applied

The CEO Case Lab (the guest avoiding another guest, tested against a direct question from the person being avoided) is excluded per the standing rule. Like the Module 22 case, it is a good candidate for eventual AI shadow-mode evaluation (M20-D02) precisely because it has no clean, comfortable answer — discretion tested against the edge of dishonesty is exactly the kind of judgement call this specification has consistently kept as human authority (127), and this scenario is well- suited to checking that an AI-drafted response respects that boundary rather than resolving it.

# 138. Module 24 — Protocol Conflict, Diplomatic Judgement & High-Status Interactions — canonical extraction and reconciliation

Source labelled this “Module 23” internally, conflicting with the already-integrated Module 23 (Discretion, Privacy & Information Control) — per the CEO’s explicit instruction, treated here as Module 24. This module is exceptionally heavily reconciled: Module 3’s protocol intelligence framework (Sections 16–18) is unusually thorough and already covers most of this module’s ground in more executable form — the five-dimensional precedence model, the three event authorities, the eight-step conflict-resolution sequence, title verification, arrival/receiving/escort controls, seating intelligence, speaking-order control, and institutional consultation rules are all already canonical. What follows is what remains after that reconciliation — including a direct, welcome closure of part of a gap Module 3 itself had already flagged as missing.

## 138.1 Reconciled directly

The “four sources of precedence” (Office, Rank, Tradition, Relationship) is a simplified subset of the existing five-dimensional model (16.2: Office, Rank, Institution, Relationship, Ceremonial role) — Tradition maps to traditional-authority instances of Institution, and the existing model additionally carries the Ceremonial-role dimension this one omits. 16.2 remains canonical. The Protocol Decision Tree (six questions), the Maison Doclar Protocol Formula (Know -> Interpret -> Design -> Brief -> Execute -> Adapt -> Protect), and “confidence without arrogance” are restatements of the existing eight-step conflict- resolution sequence (16.5) and its conflict principle, on the established precedent for these variants — 16.5 remains the one canonical sequence. The empty-chair problem, the late-arrival principle, the unexpected dignitary, incorrect-title handling, the receiving line, the name/pronunciation test, traditional-title verification, the palace environment, religious protocol, international-guest preparation and the cultural brief are all already canonical (17.1–17.7, 18.3, 24.1– 24.2) — several appear near-verbatim as existing rehearsal-test items (18.3) or protocol alerts (18.5), which is a strong confirmation those were the right things to have built rather than a new finding. The four-level protocol escalation matrix reconciles onto the 76.2 ladder directly, on the same precedent as every other escalation-matrix variant since Module 14.

## 138.2 Genuine enrichments, adopted directly

- Never make the client the event’s live protocol manual. Asking the principal a protocol question mid-event signals unpreparedness. Adopted as an explicit rule alongside the existing host-authority doctrine (16.3) — Maison Doclar translates host intention into workable protocol in advance; it does not query the host live.

- Co-honouring techniques for when two guests both expect prominent recognition — separate receiving moments, differentiated introductions, appropriate seating, host participation, private acknowledgements — are adopted as the concrete technique set behind the existing conflict principle (16.5: “recognise each form of authority appropriately without diminishing another guest”).

- Discreet identification channel for an unexpected or uncertain dignitary (confirm through host representative, protocol contact, security or the invitation record, never by asking the guest who they are) sharpens the existing title-verification chain (17.1) with the specific mechanism for the moment identity itself is uncertain.

- Unexpected-speaker response options (brief acknowledgement, inclusion at an appropriate programme point, host approval, time- controlled remarks) give the existing speaking-order control (17.5) a concrete menu for this specific live scenario rather than a binary yes/no.

## 138.3 The entourage model — new

Nothing before this module classified a high-status guest’s physical arrival party into principal guest, official entourage, personal entourage, security, and support staff — distinct categories with different access, seating, catering, transport and security implications, all needing to be known before arrival rather than discovered at the door. This is adopted as new content, extending the existing arrival-control framework (17.2, which records “entourage” as a single field without this internal structure). “The host knows me” as an access claim is handled by respectful verification, not confrontation — consistent with, and not a new mechanism beyond, the already-resolved Family Decision Owner boundary (115.1) and the Security Override Authority boundary (120.4): an entourage member’s claimed relationship to the host does not itself grant access any more than a family member’s claimed authority does elsewhere in this specification.

## 138.4 The Protocol Huddle — new

For difficult events, a small, named decision group — Event Director, Protocol Lead, host representative, and relevant cultural/traditional authority where necessary — resolves live protocol conflicts, with one person able to say “this is the arrangement.” This is adopted as the protocol-specific instance of the same small-group command principle already established for crises generally (86.3’s Crisis Command Centre, 20.7’s “small enough to think, large enough to know”): live protocol conflict is a variant of the same live-decision problem, not a different one, and reuses the same discipline — named participants, one decision owner, no committee of ten.

## 138.5 Closes part of an existing Module 3 gap

Module 3’s own gap list (19.5) already flagged: “protocol correction, dispute, refusal and live-deviation playbooks remain to be authored.” This module is substantially that playbook — the diplomatic-no script, the co-honouring techniques, the discreet-identification channel, the correction-severity judgement, and the Protocol Huddle together give live protocol conflict a real operating procedure that did not exist before. It is not complete: the gap list’s adjacent items (representative/spouse/former-officeholder/acting-office treatment, seating adjacency schema, receiving-line capacity standards) remain open, and this module does not address them. 19.5 is updated to reflect partial closure rather than left to imply nothing has changed since Module 3.

## 138.6 Exclusions applied

The CEO Case Lab (the eight-minute five-dignitary seating crisis) is excluded per the standing rule. It is strong material for the still-open AI shadow-mode evaluation capability (M20-D02): a live protocol conflict with five simultaneously arriving authority claims and an eight-minute clock is close to worst-case test data for whether an AI-drafted recommendation correctly defers the final call to the Protocol Huddle rather than resolving it unilaterally.

# 139. Module 25 — The Luxury Service Recovery Lab — canonical extraction and reconciliation

Source is explicitly a judgement module: fifteen worked cases, each with a stated lesson, synthesising Modules 22–24. Unlike the standard CEO exercises this specification excludes throughout, these fifteen cases come with their own answers already attached — they are teaching content in worked-example form, not open assignments, and are extracted accordingly. Only the closing CEO Challenge (24.45, five simultaneous incidents, genuinely open) is excluded per the standing rule. Twelve of the fifteen cases confirm doctrine already canonical; ten items across the module’s framing sections and three cases are genuinely new.

## 139.1 Cases that confirm existing doctrine — no new content

Case 1 (never investigate in front of the waiting guest) confirms Module 22’s uncertainty-vs-delay doctrine (136.2). Case 2 (reduce touchpoints for a privacy-seeking VIP) confirms the quiet-privilege doctrine. Case 3 (unexpected nine-person entourage against an invitation for two) confirms the entourage classification model built at Module 24 (138.3) — direct validation that addition was needed. Case 6 (guest looks dissatisfied though nothing is visibly wrong) confirms hidden-complaint detection (136.2) and the existing discretionary check-in phrasing (15.27). Case 7 (protocol officer disagrees) confirms the Protocol Huddle (138.4). Case 8 (family member claims unlimited authority) confirms the Family Decision Owner model (115.1) and the entourage “host knows me” handling (138.3). Case 10 (guest is factually wrong but disappointment is real) confirms the complaint-type taxonomy (84.2). Case 11 (photographer versus VIP privacy preference) confirms the photography-consent doctrine (137.2) — the source’s own phrase, “content is never more important than consent and discretion,” is close to identical to language already canonical there. Case 13 (emergency priority order) confirms the safety-overrides- schedule doctrine (82.3) and medical protocol (83.1). Case 14 (contain first, investigate second) confirms the stabilise-first doctrine (82.2) and staff social-media rule (105.3). Case 15 (vendor blame chain, solve first) confirms Module 18’s vendor-failure doctrine. The Decision Model (See -> Assess -> Prioritise -> Protect -> Act -> Verify) is the command-loop family (74.1) under another label, reconciled on the now-standard precedent.

## 139.2 Genuine enrichments, adopted directly

- The six-dimension consequence model (Guest, Host, Protocol, Operations, Reputation, Future) organises a decision by who is affected, complementing rather than duplicating the existing consequence-prioritisation model (76.3, organised by properties of the incident — urgency, severity, irreversibility) and Module 22’s five recovery variables (136.1, already a subset of 76.3). Adopted as a genuine second lens: 76.3 asks how serious this is, the six-dimension model asks whose experience or interest is in play. The accompanying Decision Matrix (eight yes/no questions) is adopted as its practical checklist form.

- Never defend the plan before understanding the guest’s information (Case 4): a guest insisting their seat is wrong may know something the seating plan does not — a late family instruction, a changed relationship to the host. Adopted as a specific instance of taking guest pushback as a possible signal rather than only an error to correct.

- Interpret intent, not merely the literal instruction (Case 5): when a principal asks for something operationally unrealistic (“greet all 400 guests personally in 25 minutes”), the professional response identifies what the client actually wants (guests feeling personally welcomed) and designs an achievable equivalent, rather than a flat “that’s impossible.” This is genuinely new and directly relevant to the AI Consult capability (134): a Consult response facing an unrealistic request should perform exactly this translation — surface the achievable options that serve the underlying intent — rather than only reporting infeasibility.

- Interpersonal-conflict seating techniques (Case 9: physical separation, different arrival routes, different holding areas, staggered photography, differentiated hosting) extend the co-honouring techniques already adopted at Module 24 (138.2) from simultaneous-precedence competition to personal/interpersonal conflict between guests specifically — a related but distinct scenario Module 24 did not cover.

- When the principal is the operational problem (Case 12): a frustrated host giving contradictory instructions to multiple staff needs a buffer, not correction — a senior representative consolidates the instructions (“let me coordinate that for you”) and returns the principal to host mode. Adopted as new doctrine, distinct from but adjacent to the existing “I have it” CEO/client-moment script (135.2) — that script covers the client raising a problem; this covers the client being the problem.

- The smallest effective intervention (24.34): do not deploy a ten-person response to a one-person problem, or disrupt an entire event to fix a minor inconvenience. This is a genuinely distinct proportionality principle from the existing Three-Level Imperfection Test (135.4, which asks whether to intervene) — this one governs how much intervention once the decision to act is made. Adopted directly, alongside its companion invisibility test (“would an uninvolved guest know something had gone wrong?”) as the live- incident-response analogue of the First Guest Test (51.1.1).

- The escalation test: “does this require someone more senior, or am I simply uncomfortable making the decision?” This is genuinely new — nothing before this addressed the psychology of over-escalation specifically. Adopted as a self-check staff apply before invoking the existing 76.2 ladder, distinguishing legitimate escalation from discomfort-driven escalation.

- The end-of-incident test — guest okay, environment stable, responsible team knows it is closed, client informed if appropriate, documented if significant, root cause reviewable — is adopted as an explicit five-point closure checklist for the existing Incident record and Crisis log (Section 5), which previously had a “Close” step in the recovery loop (87.4) without this compact a definition of what closure actually requires.

## 139.3 The Judgement Case Library — new knowledge type, deliberately distinguished from the Pattern Library

The fifteen worked cases in this module are illustrative precedent, not accumulated event evidence — and that distinction matters enough to name explicitly rather than blur. Section 123’s Pattern Library (123.2) holds patterns built from real, corroborated event evidence, requiring multiple actual occurrences before promotion (123.4) — a single hypothetical case, however well-reasoned, does not qualify under that discipline. These fifteen cases, and any future CEO-approved cases like them, are adopted instead as a new, separate knowledge type: the Judgement Case Library — CEO-authored worked examples with a stated lesson, holding the same authority as any other approved doctrine in this specification (subject to the Proposed/Approved/Provisional/ Superseded/Rejected states, 1.1), but never conflated with Pattern Library entries or presented as if backed by live-event evidence they do not have. Its primary use is exactly the one already anticipated at 134.3: when a Consult response checks the knowledge base for precedent, the Judgement Case Library is a legitimate source to cite — clearly labelled as illustrative doctrine, not as an observed pattern — and where no case applies, the existing honest-absence rule (128.2, 134.3) still governs.

## 139.4 Exclusions applied

The CEO Challenge (24.45, five simultaneous incidents at 7:15pm) is excluded per the standing rule — unlike the fifteen cases, it is genuinely open with no attached answer. It is strong material for the still-open AI shadow-mode evaluation capability (M20-D02): five concurrent, differently-authoritative incidents with a hard ten-minute window is close to a stress test for whether an AI-drafted triage correctly applies the escalation test (139.2) rather than either under- or over-escalating across all five at once.

# 140. Module 26 — The Art of Host Management — canonical extraction and reconciliation

Source turns the lens from guest to principal. It reconciles against the Family Decision Owner model (115.1), the Principal Profile (93.2), the client-briefing formula (85.3) and the client decision format (125), and against Module 25’s “the principal can be the operational problem” (139.2). Eleven items are genuinely new; the rest confirms or sharpens existing doctrine.

## 140.1 Reconciled directly

Information filtering to the CEO/principal, the RED/AMBER/GREEN interruption classification, the three-sentence brief (“what happened, what we’ve done, what we need from you”), and the Host Experience Model (Prepare -> Protect -> Guide -> Buffer -> Enable -> Recover -> Release) all restate existing doctrine: CEO dashboard filtering (75.1), the 76.2 escalation ladder (applied here specifically to whether to interrupt the principal, a legitimate specific instance rather than a new model), the client-briefing formula (85.3) and client decision format (125) almost verbatim, and the command-loop family (74.1) respectively. “Never bring the host a problem without a path” is the same discipline already established for client communication generally.

Folded in from a second host-management submission (per CEO instruction, not given its own module number): the Three Experiences — Public (what guests see), Private (what the host personally feels) and Operational (what the host has to deal with) — is adopted as a complementary lens to the existing Three Roles (Host/Principal/Human being, 25.3): Three Roles asks what functions the principal performs; Three Experiences asks what they perceive while performing them. Both are retained. The one-sentence brief (“dinner will begin at 8:20 rather than 8:10; no guest impact expected”) is adopted as an even more compressed option than the three-sentence brief, for matters simple enough to need only the outcome stated, not the full what-happened/ what-we-did/what-we-need structure.

## 140.2 The Authority Map — generalises the Family Decision Owner

The Family Decision Owner (115.1) was scoped specifically to guest-experience matters. Module 26’s Authority Map (person, relationship, authority domain, can-instruct-staff) is broader: it documents operational authority across the whole host inner circle — spouse, PA, family representative, security lead, Event Director, Protocol Lead — not only for guest-experience conflicts. Adopted as the general artifact; the Family Decision Owner is its guest-experience row, not a competing mechanism. This directly closes the “everyone speaks for the host” problem for every domain, not only seating disputes, extending 115.1’s resolution rather than duplicating it.

A second submission’s “Inner Circle Map” (Principal -> Principal’s Representative -> Family Lead -> Protocol Lead -> Event Director) is the same Authority Map at coarser resolution. Its one genuinely useful addition is naming Family Lead as a distinct position within the Authority Map’s family domain — the person who coordinates family matters specifically, as opposed to the Principal’s Representative who holds broader delegated authority. Adopted as a named row, not a new mechanism. The submission’s worked decision-authority matrix (guest experience -> Maison Doclar; operational timing -> Event Director; ceremonial matters -> family/protocol authority; major client decisions -> Principal) is a good illustrative instance of what an Authority Map should contain per domain, not a new structure.

## 140.3 Six new products and roles, adopted directly

- The Host Brief — who the host must personally receive/thank, who to avoid being trapped with, ceremonial duties, family dynamics, essential photographs, private preferences, rest windows, likely decisions, and fallback authority when the host is unavailable. This is the deliverable generated from the Principal Profile (93.2) and Authority Map (140.2), the same relationship the Vendor Brief (49.1) already has to the underlying Scope of Work — a new document, not new underlying data. Its “who to personally receive” content is structured into three greeting tiers — who the host must personally receive, who they should personally acknowledge, and who an authorised representative can warmly receive on their behalf — a distinction not previously made explicit and adopted directly.

- The Host Companion — a dedicated Maison Doclar representative staying close enough to the principal to manage cues, transitions, time, photography coordination, and graceful exits from conversations. New role, the principal-specific analogue of the existing VIP Host role.

- The Host Time Budget — arrival, receiving, ceremonial obligations, photography, meal, guest engagement, private time and departure preparation, planned in advance so the host’s day has structure without feeling like “an airport departure board” (25.19, a good specific caution worth preserving). New product, informing but distinct from the live Principal Movement Board (Module 16/20) which tracks the day as it actually unfolds. Extended (per a second submission) to cover the principal’s entire day, not only event hours — morning preparation and family commitments before arrival draw on the same energy the event itself will need, and the Time Budget should protect high-value moments (ceremony, key photographs) from being scheduled against a principal who is already depleted, the same energy-curve discipline already built for the room generally (135.3) applied here to one person specifically.

- Conversation-exit scripts — “Excuse me, Sir, may I borrow you for a moment?” / “Madam, may I bring you through? Your next engagement is ready.” Adopted as approved phrasing for a specific, previously-unaddressed moment: giving the host a socially acceptable way out of a conversation.

- The Principal Suite — a controlled sanctuary (seating, refreshments, wardrobe support, private communication, security coordination, emergency supplies) with explicit access rules (who may enter, who may knock, who may accompany, emergency handling, photography permission). Genuinely new: no prior module formalised a controlled principal-specific space with these rules, despite “VIP holding area” being mentioned in early source material — it was never actually built as an object until now. Extended: wardrobe transitions (attire, jewellery, footwear, ceremonial accessories for multi-part events) are planned and timed in advance rather than chased on the day, and the Suite’s private-moment function is given a concrete list worth protecting deliberately — time alone before guests arrive, a quiet pause before ceremony, a private family photograph, a short break after formal proceedings, and a private farewell.

- The Family Hierarchy Map (Principal family, Senior family, Elders, Immediate household, Extended family, Community representatives) gives the Principal Profile’s existing “family structure” field (93.2/Section 5) a structured six-category breakdown it did not previously have — adopted as an enrichment of that field, not a new entity.

- Physical care checklist: verify the principal actually eats — a host spending an entire dinner greeting guests can reach the end of the evening having barely eaten — and monitor hydration and basic comfort discreetly through the same Host Companion function (above), not as a visible or embarrassing check-in. Adopted as concrete, previously-unstated content for an otherwise-obvious gap.

- The Celebration Principle: where the event is a celebration, the host should be allowed to actually celebrate, not spend the whole evening performing operational obligations. This is adopted as an explicit value alongside the Host Journey’s “Enable” step (140.5) — Enable describes the mechanism (absorbing distractions so graciousness is possible); the Celebration Principle states the outcome that mechanism is for.

## 140.4 “Recommend, don’t present” — new, links to the AI Consult capability

“There are three options, which do you want?” is replaced by “we recommend Option B because it protects guest flow; unless you prefer otherwise, we’ll proceed.” This addresses decision fatigue specifically — a host who has made hundreds of planning decisions over months should not face open-ended choices again on the day. This connects directly to the AI Consult capability (134): a Consult response already produces a recommended option with reasoning, not merely a list of options (134.1’s structure) — this principle is the service-culture rationale for why that response shape is correct, independent of who or what is producing the recommendation.

## 140.5 The Host Journey — new, parallel to the Guest Journey

The Host Experience Model, while its steps reconcile to the command-loop family (140.1), is worth naming as what it actually is: a Host Journey, structurally parallel to but distinct from the canonical Guest Journey (13.1) and the MD-EOS Delivery Lifecycle (91) — a third named journey, this one describing what the principal personally experiences rather than what a guest experiences or what the organisation does. Adopted as a named object in its own right for clarity, not merely a restated loop.

## 140.6 The Host Debrief — new variant of the Client Debrief

Timing matters: do not ask “how did we do?” immediately — allow the host time to emotionally process before asking focused questions (what worked, what should never happen again, which guest experience mattered most, where did you feel unsupported, what should we have anticipated). Adopted as the host-specific, more personal counterpart to the existing Client Debrief object (95.2), which remains the operational/business debrief; the two are complementary, not competing.

The Host Experience Score (a second submission): did the host feel informed, protected, respected; did they enjoy the occasion; were they burdened with unnecessary decisions; did they ever feel abandoned or overwhelmed; did they have private time; did they trust the team — each answerable directly rather than open-ended. Adopted as a structured checklist alongside the open Host Debrief questions above, not a replacement for them: the Score gives a fast, comparable read across events, the open questions give the texture a checklist cannot.

## 140.7 Exclusions applied

The CEO Master Exercise (the ten-minute principal-departure sequencing problem) is excluded per the standing rule. A second host-management submission, folded into this module rather than given its own number per the CEO’s explicit instruction (140.1–140.3, 140.6 above), had its own CEO Master Exercise (the 6:30pm six-way principal demand conflict) excluded on the same rule.

Module 27 (“The Architecture of a White-Glove Event”) is not given its own section. On review it was found to contribute almost nothing beyond what Modules 6, 7, 10, 11, 13, 16 and 20–21 already established — one of its central points restated the existing Critical cue contract (56.2) almost exactly. Its two small genuine contributions are folded directly into their homes rather than held in a separate section: the WHEN field in the message contract (76.1) and the multi-flow overlay practice at the dependency graph (50.1). The full review and verdict remain on the record in Appendix B, which exists precisely for this case — a module that was read carefully and found to add little should be traceable as reviewed, not silently absent.

Module 28 (“Event Intelligence & Live Command,” internally labelled “Module 27” in its own source — see the numbering note in Appendix B) is treated the same way, and overlapped even more heavily than Module 27: its Sense-Interpret-Predict-Decide-Act-Verify-Learn loop restates the canonical command loop (74.1); its NOW/NEXT/RISK model, VIP tiers, escalation chain, single source of truth, version control, change log, Event Black Box and Five Whys are all already canonical; its proposed 15-/60-minute look-ahead windows already sat inside the existing horizon ranges (73.1) before this module arrived; and its “AI Opportunity” section describes, with near-identical examples (“VIP arriving in 12 minutes”), the AI Layer already fully designed at Sections 126–134. Three small genuine points were folded directly into their homes: concrete subtle-signal examples and the queue/empty-space interpretive framing, added to the warning-horizons section (82.1); and a finer-grained five-step Watch/Prepare/Intervene/Escalate progression, folded into the evidence-based RAG model (40.1) as an optional subdivision of Amber/Red rather than a fifth state. No new roles, data entities or decisions were required.

# 141. Module 30 — The Maison Doclar Standard — capstone extraction

Source: “Final Module — The Maison Doclar Standard.” This module is different in kind from every module before it. It proposes almost no new mechanism, data entity or role — and that is the correct outcome for a capstone module arriving after twenty-nine others, not a failure to contribute. Its value is integrative: it names the philosophy this entire specification has been operationalising piece by piece, and in several places its own list of what “the Maison Doclar Way” should contain is, point for point, a description of the document that already exists. That correspondence is treated below as confirmation, and five genuinely useful capstone artifacts are adopted from it.

## 141.1 The Ten Rules — confirmed, not new, and worth keeping as a named summary

Every one of the ten rules (30.7–30.16) restates doctrine already built: never create a problem while solving one (the smallest-effective- intervention and invisibility tests, 139.2); never make the guest carry an operational problem (the no-blame-in-front-of-the-guest doctrine established from Module 9 onward); luxury is often barely visible (the foundational philosophy of Module 1); never make the guest ask twice (Module 15’s “don’t make the VIP repeat themselves”); every detail has a named owner (the one-owner doctrine, present in nearly every module since Module 6); every important moment needs a trigger, not only a clock (the Critical cue contract, 56.2, now folded twice); the guest sees the result, not the struggle (the front-of-house/back-of-house divide); discretion is not optional (Module 23/29’s discretion doctrine); cultural intelligence is part of luxury (Module 4); never stop learning from the event (the After-Action Review and the cross-event knowledge base, Section 123). Adopted as the canonical Ten Rules — a deliberately memorable, citable summary of ten load-bearing principles from across the specification, useful precisely because it is short enough to actually be remembered without having read all thirty modules.

## 141.2 The Maison Doclar Playbook — the module describes this document

Module 30’s proposed operating library (Guest Journey Standards, VIP Intelligence Framework, Principal Management Framework, Protocol Manual, Cultural Intelligence Guide, Vendor Standards, Event Architecture Framework, Live Event Control System, Discretion Charter, Crisis & Contingency Procedures, Post-Event Review, Guest Feedback System, Training & Certification) maps, almost without gaps, onto modules already integrated: Module 2, Module 5, Module 26, Modules 3/24, Module 4, Modules 7/13/18, Modules 12/27, Modules 6/10/16/20/28, Modules 17/23/29, Module 11, Section 123/87, Module 15, and Modules 14/19 respectively. This is worth stating plainly rather than passing over: the specification this CEO has been building, module by module, is already substantially the playbook this final module calls for. That is the intended outcome of this entire exercise, and this module is where it becomes visible as a completed shape rather than an accumulating list.

## 141.3 The Event Readiness Declaration — new, an integration artifact

Module 30’s pre-declaration checklist (30.18: who is the principal, who are the critical guests, protocol/cultural/guest-flow risks, vendor dependencies, critical transitions, top five failure points, contingencies, function ownership, what the principal does/does not need to know) is genuinely useful as a top-level artifact, distinct from every individual domain readiness gate already built (the protocol readiness gate 18.4, the vendor readiness gate 51.2, the guest-ready checkpoint 51.1, system readiness 96.2). None of those gates alone answers “is the event, taken as a whole, ready” — each is scoped to its own domain. Adopted as the Event Readiness Declaration: a final, named, whole-event go/no-go check that references the individual gates rather than re-deriving their content, signed off by the Event Director before an event opens. This is a new object, not a restatement — the specification did not previously have a single artifact that sits above all the domain-specific gates and asks whether the event as a whole may proceed.

## 141.4 The CEO Charter — new, elevates scattered CEO doctrine into one statement

CEO-role guidance has appeared piecemeal throughout this specification (14.40, 16.6, 20.4, 24.40, 86.1, and the AI Systems Owner design at 131.2). Module 30 states, in one place, what all of those individual points were building toward: the CEO’s five responsibilities (set the standard, build the system, build the people, protect the brand, build the intelligence); the dangerous CEO trap (competence at every individual task becomes a constraint, not an asset, once the organisation depends on “let me handle it” rather than on the system); and the real goal (“this is how Maison Doclar does things,” not “this is how the CEO does things”). Adopted as the CEO Charter — the capstone statement the scattered individual CEO-role rules were always instances of. It directly explains, retroactively, why the AI Layer (126–134) and the Consult capability (134) were designed the way they were: an AI system that only ever drafted and recommended, never decided, was always in service of exactly this goal — making Maison Doclar’s judgement systematised and repeatable rather than concentrated in one person, human or otherwise.

## 141.5 The Maison Doclar Creed — adopted as this specification’s closing statement

The Final Lesson and the Maison Doclar Creed are adopted, unedited in substance, as the closing mission statement of this specification — the natural counterpart to the Purpose statement and Governing Rule this document opens with (Section 1). Where Section 1 states what this document is (the reconciled record of what the operating system should know, collect, infer, recommend and control), the Creed states why: the guest should never have to understand how difficult their experience was to create; they should simply remember how it felt.

**THE MAISON DOCLAR CREED We anticipate rather than react. We observe

before we intervene. We protect dignity. We respect culture. We value

time. We value discretion. We make the important feel important

without making the service intrusive. We solve problems quietly. We

never make the guest carry our operational burden. We learn from every

experience. And we leave people feeling that everything was

effortless.**

## 141.6 Minor confirmed restatements

The Maison Doclar Promise (30.1), the Five People Maison Doclar Serves (30.2, a stakeholder map complementary to but distinct from the six-dimension consequence model at 139.2), the Maison Doclar Equation (30.3, the capstone version of the several domain-specific “equations” already scattered through this specification — vendor, staff, command, security), the Four Levels of Mastery (30.4–30.5, a four-level compression of the existing five-level staff maturity model, 104.4), the Operating Philosophy (30.6, the command-loop family again), the Guest Experience Standard (30.17, a compressed, question-form version of the canonical Guest Journey, 13.1, suited to a one-page pre-event check), and the role philosophies for the Event Director, Guest Experience Professional, Protocol Professional and Vendor Manager (30.19–30.22) are all confirmed restatements of doctrine already built. None require new sections; their value is rhetorical crystallisation, which is exactly what a closing module should provide.

## 141.7 Exclusions applied

The Final CEO Exercise (the one-page Signature Event Standard writing assignment) is excluded per the standing rule, as with every CEO exercise before it.

## 141.8 Where this leaves the specification

Thirty modules in, source-numbering discrepancies notwithstanding, this specification now contains: the full guest, protocol, cultural, VIP, command, vendor, staffing, communication, security, staff-management, AI-layer, execution, recovery, discretion, and host-management doctrine those thirty modules described; a fully designed cross-event knowledge base (Section 123); a fully designed AI Layer with an explicit 2026 capability boundary and six grounding mechanisms (126–134); ten items resolved across four CEO-approved debt-fix cycles plus the M12-D07 architecture cycle and the M18-D01/M13-D03 cycle (fourteen items fully resolved, three partially resolved); and, as of this module, an explicit CEO Charter and Creed closing the loop back to Section 1’s own opening statement of purpose. The standing open items — the eight-item staffing-policy backlog (124.7), Module 3’s remaining precedence-dataset gaps (19.5), and the AI shadow-mode evaluation capability (M20-D02) — remain exactly as recorded, and are the natural next work now that the module sequence itself has reached its stated end.

# 142. Staffing Policy Framework — closing the staffing-policy backlog (124.7)

Source: CEO-supplied draft staffing policy (zero-hours contract framework), prepared for external employment-counsel review. Status: Provisional, not Approved — this framework resolves the design half of seven of the eight items on the staffing-policy backlog; it does not resolve the legal sign-off half, and the document is explicit about that limitation itself. This specification preserves that limitation rather than letting it quietly disappear once absorbed here.

## 142.1 What is adopted, and at what state

The classification test, vetting requirements, contract structure, compensation/statutory-deduction framework, data-privacy framework, disciplinary process, insurance coverage, international-deployment requirements and diversity commitments are adopted as Provisional knowledge (1.1) — usable as Maison Doclar’s working staffing policy, but not yet Approved, because Approved status for anything carrying statutory and tribunal exposure requires the qualified Nigerian employment counsel review the source document itself calls for and has not yet received. This specification is not a contract template (49.2’s existing rule, restated here because it applies with equal force to employment contracts): the full contract text supplied stays an external legal artifact Maison Doclar’s lawyer finalises, not canonical text reproduced and treated as settled.

## 142.2 Employment classification and the control test

Zero-hours workers are classified as employees, not independent contractors, whenever Maison Doclar controls what, when, where and how work is done — the Nigerian substance-over-form control test. This closes M14-D03: contract labels do not override this test, and no future scope document may relabel controlled workers as contractors to avoid statutory obligations. This determination is adopted as binding policy, not merely informative — it is the one piece of this framework that does not wait on counsel review, since misclassification risk begins at the first contract signed, not at the policy’s eventual approval date.

## 142.3 Recruitment sourcing and vetting — closes M14-D02

Approved sourcing channels (staff referrals with anti-nepotism controls, hospitality training institutions, the existing staff database, professional networks); prohibited channels (undocumented informal group hiring); and mandatory vetting before first shift (identity verification, right-to-work confirmation, minimum two references, a background check for VIP-facing roles, role-specific qualifications, medical fitness where the role demands it) are adopted directly. A new Vetting Record (Section 5) captures each check, its evidence and the Hiring Manager’s sign-off before a worker is added to the Approved Staff Register — itself the staffing-specific instance of the Approval State discipline already used for vendors (48.2).

## 142.4 Contract, compensation and statutory compliance

The written-contract-before-first-shift rule, the wage structure (base rate at or above National Minimum Wage, training pay, overtime, night and weekend/holiday differentials), and the statutory deduction table (PAYE, employee/employer pension contributions, NHF, NSITF) are adopted as Provisional policy. This closes the design half of M14-D09 (compensation/payroll): rules now exist; what remains is counsel confirming current statutory rates and the CEO setting Maison Doclar’s actual rate relative to the stated minimum, both operational follow-ups rather than open design questions.

## 142.5 Staff data privacy — closes M14-D08/M19-D01

Lawful-basis categories (contractual necessity, legal obligation, consent), the data-category/retention table, the mandatory Staff Privacy Notice at onboarding, security measures, and the data-breach protocol (contain, assess, notify the Data Protection Commission within 72 hours if high-risk, notify affected staff, document) are adopted directly, closing the staff personal-data-privacy gap the Staff Talent Record (124.6) made urgent. The AI boundary rule already requiring staff-data care (8.1, “no compiling or exposing a person’s performance history outside their management chain”) now has a full policy underneath it rather than a standalone principle.

## 142.6 Disciplinary process — closes M14-D06

The three misconduct tiers (minor, serious, gross) and the six-step procedure (informal discussion -> verbal warning -> written warning -> final written warning -> disciplinary hearing -> dismissal), each with defined validity periods, evidence and appeal rights (to the CEO within five days, with the worker retaining recourse to the National Industrial Court), are adopted directly. A new Disciplinary Record (Section 5) captures each stage. This gives the existing “there must be consequences” principle (104.2) the formal process it always lacked.

## 142.7 Insurance, liability and international deployment — closes M14-D10/M14-D11

Mandatory coverage (Employee Compensation/NSITF, public liability, professional indemnity, group life assurance, motor insurance where applicable) and the incident/claims process are adopted directly, closing M14-D10. International deployment requirements — valid passport, appropriate visa/CERPAC, travel insurance, vaccination certificates, and a pre-deployment briefing on local labour law and cultural norms, applied symmetrically to Nigerian staff travelling out and international staff travelling in — are adopted directly, closing M14-D11.

## 142.8 Diversity and inclusion — closes M14-D12

The equal-opportunity commitment, reasonable-accommodation practices (accessibility, flexible scheduling for religious observance, cultural sensitivity in role allocation) and anonymous monitoring at application stage are adopted directly, closing M14-D12.

## 142.9 What remains genuinely open

Only the legal sign-off remains outstanding, not the design. Employment counsel review and CEO/counsel signature are required before this framework moves from Provisional to Approved status (1.1). Current statutory rates (minimum wage, pension percentages, tax bands) require periodic confirmation against current legislation, not a one-time check — the framework’s own annual review cycle (its 1.11) is adopted as the mechanism for this. Until counsel sign-off is obtained, this framework should be treated internally as strong operational guidance, not as a warranted compliance position Maison Doclar can rely on if challenged.

# 143. Nigerian Protocol Register — closing Module 3’s precedence-dataset gap (19.5)

Source: CEO-supplied protocol register, explicitly labelled by its own author as “DRAFT FOR VERIFICATION — do not use for live events without event-specific verification.” Status: Provisional, verification-required-per-event — a status this register does not graduate out of the way a design decision would. Its own discipline (every entry marked [Verify], a standing verification checklist, and an explicit statement that officeholders and event-specific requirements must be reconfirmed every time) is adopted as part of what makes it usable, not stripped out for tidiness.

## 143.1 What is adopted

The register closes the first three items on Module 3’s gap list (19.5) directly: a Nigerian formal precedence dataset now exists (federal and state political protocol, with explicit precedence ranking); institution-specific protocol packs now exist for traditional (Yoruba/Southwest palace system and Northern emirate system, each explicitly flagged as institution-specific rather than generalisable), diplomatic, religious (Christian and Muslim clergy), military/security, and institutional (academic, judicial, corporate) categories; and forms of address are populated across every category with direct-address, introduction and formal-title variants, consolidated in a quick-reference register (this register’s own 2.12). This attaches to the existing multiple-authority model (16.1) and five-dimensional precedence model (16.2) as their first populated dataset rather than a competing structure — the register’s own protocol-conflict-resolution framework (its 2.15) is, point for point, the same sequence already canonical at 16.5, independent confirmation rather than new doctrine.

## 143.2 Edge cases — closes the representative/spouse/former-officeholder/acting-office gap

Spouse precedence (immediately after the officeholder for political and diplomatic ranks, per-palace for traditional rulers, never assumed to want joint seating without verification), former-officeholder treatment (honorary precedence immediately below the current holder of the adjacent rank, current officeholders always taking priority), and acting officials (full precedence for Acting President/Governor, one rank below substantive holder for Acting Minister/Commissioner) are adopted directly, closing the specific edge-case gap flagged at 19.5. This does not close the broader “boundary between advice, institutional authority and final Maison Doclar approval” gap (19.5, still open) — the edge cases now have rules; who has final sign-off authority when those rules are disputed live is answered separately by the existing Protocol Huddle (138.4), not by this register.

## 143.3 What remains genuinely open

Every [Verify] placeholder in the register (current officeholder names, which change independent of this document) remains exactly that — this specification does not invent names to fill them, consistent with the absence-handling rule (128.2). Seating algorithms/adjacency schema, receiving-line capacity standards, and national-symbol jurisdiction-specific requirements remain open per 19.5, unchanged by this register. The register’s own verification checklist (its 2.13) is adopted as the mandatory pre-event step converting this dataset from reference material into an event-specific, currently-accurate protocol plan — no event proceeds on this register’s entries without that checklist having been run.

# 144. AI Shadow-Mode Evaluation Harness — closing M20-D02

Source: CEO-commissioned advisory review of the three standing gaps. Status: design resolved, implementation not started — the document’s own framing is adopted without softening: this is the one gap of the three that is a genuine precondition, not a phased item, and the specification says so as plainly as the source did.

## 144.1 The harness architecture

Historical case (a real past event decision with known-good human judgement) -> AI Layer running in shadow mode (no production access, per the existing AI boundary discipline, 8.1) -> comparison engine (AI output against the human decision) -> divergence report -> root-cause analysis -> model adjustment or a new human-override rule. Adopted directly as the mechanism validating the AI Layer (126–134) before it is trusted with any live event, and as the natural downstream consumer of the Judgement Case Library (139.3) and the excluded CEO exercises this specification has been flagging as good test material since Module 10 (79) — both are now formally in scope as harness input.

## 144.2 Acceptance criteria — adopted as binding, not aspirational

Minimum 95% agreement with human experts on precedence matters; zero tolerance for critical divergence on seating, forms of address or protocol breaches; every divergence documented and explained; and human-in-the-loop required for every high-confidence recommendation regardless of the AI’s own confidence tier (128.3). These are adopted as launch-blocking criteria, consistent with the AI Layer’s existing design principle that AI drafts and humans decide (126.1, 127): the harness is how that principle gets verified rather than merely asserted.

## 144.3 Test case library

Minimum 20 test cases before any shadow-mode testing begins (government and traditional precedence, 100% agreement threshold), expanding to the full structure below:

| Category * | *Cases** * | *Acceptance threshold** |
| --- | --- | --- |
| Government precedence | 15 | 100% agreement |
| Traditional protocol | 15 | 100% agreement |
| Diplomatic protocol | 10 | 95% agreement |
| Religious protocol | 5 | 95% agreement |
| Mixed protocol conflicts | 5 a | Human review required (no utomated pass/fail) |
| Forms of address | 10 | 100% agreement |
| Seating decisions | 10 | 95% agreement |
| Edge cases | 10 | Documented and reviewed |

Sourced from the Judgement Case Library (139.3), the Protocol Register’s own worked examples (143), and the excluded CEO exercises across this specification, each converted into a historical-case format the harness can run.

## 144.4 Ownership — new role added

CTO is adopted as a new named role: primary owner of the shadow-mode test harness’s technical implementation. This is deliberately distinct from the AI Systems Owner (8.0.9, the CEO) — the AI Systems Owner governs what the AI layer may access and reviews its audit trail; the CTO builds and operates the specific validation harness that proves the AI layer is safe to grant that access to in the first place. Protocol Director is adopted as supporting owner (providing and validating test cases); an external protocol expert is adopted as independent validator of divergence analysis, consistent with the second-person-review discipline already required of the Knowledge Base Curator (123.6) and now extended to AI validation specifically.

## 144.5 Sequencing — what cannot wait versus what can be phased

Cannot wait: the test harness itself, and the first 20 high-priority cases (government and traditional precedence). Can be phased: the full 80-case library, automation of the testing pipeline (manual is acceptable initially), and validation cadence (quarterly is acceptable after initial launch, rather than continuous). Timeline adopted as guidance, not a hard deadline this specification enforces: 60 days for the initial harness and a 20-case library, 90 days for full validation against the complete test structure above.

## 144.6 The standing rule this closes

No AI-generated protocol, precedence, seating or address recommendation reaches a live event until it has passed this harness. This is adopted as an explicit, binding extension of the AI Layer’s existing boundary (Section 8.1, 126–134): the AI Layer was always designed to draft and recommend, never decide, but “recommend” for protocol matters specifically now requires harness validation first, not merely a human reviewer in the loop at the moment of use.

# Appendix A — Repeatable module extraction template

Complete this record for every incoming CEO knowledge module. Then reconcile approved items into the consolidated sections above.

## A1. Module identity

- Module number and title

- Source file/version/date

- Source owner

- Ingestion date

- Reviewer

- Extraction status

## A2. Executive summary

- What this module teaches

- Why it matters to the operating system

- Where it relates to existing knowledge

- What is genuinely new

## A3. Knowledge extracted

- Doctrine

- Definitions

- Principles

- Frameworks and taxonomies

- Standards and thresholds

- Rules and conditions

- Playbooks and response patterns

- Prohibitions and guardrails

## A4. Relationships

- Knowledge items reinforced

- Knowledge items modified

- Knowledge items superseded

- Dependencies on other modules

- Downstream system areas affected

## A5. Decisions supported

- Decision question

- Decision owner

- Inputs required

- Permitted system role: inform / recommend / decide / execute

- Approval boundary

## A6. Data requirements

- Entity and field

- Purpose

- Source

- Verification method

- Sensitivity

- Freshness/expiry

- Required versus optional

- Missing-data consequence

## A7. Application logic

- Trigger

- Preconditions

- Evaluation method

- Timing or lifecycle stage

- Context modifiers

- Exceptions

- Output

- Expiry/re-evaluation condition

## A8. Intelligence outputs

- Briefs

- Risks

- Recommendations

- Tasks

- Alerts

- Scores

- Explanations and evidence

## A9. Roles and governance

- Knowledge owner

- Data owner

- Decision owner

- Executor

- Approver

- Viewer permissions

- AI boundary

- Audit requirement

## A10. Geography and culture

- Globally reusable knowledge

- Country context

- City/local context

- Event-type context

- Evidence versus assumption

- Portability requirements

## A11. Conflicts and gaps

- Contradictions

- Ambiguous terms

- Missing thresholds

- Missing data

- Unsafe inference risks

- CEO decisions required

- Recommended resolution

## A12. Change impact

- Consolidated sections changed

- Schemas affected

- Rules affected

- Interfaces/workflows affected

- Migration required

- Tests/evaluations required

## A13. Acceptance

- Approved items

- Provisional items

- Rejected items

- Deferred items

- Approver and date

- Effective version

# Appendix B — Module change register

| Module | Specification version | Added | Modified / superseded | Open decisions | Approval status |
| --- | --- | --- | --- | --- | --- |
| 1 — White-Glove Hospitality | 0.1 | Doctrine; luxury dimensions; anticipation; five layers; friction foundation; intelligence and governance boundaries | Initial document — none | M1-D01 to M1-D10 | Foundation proposed for CEO confirmation |
| 2 — The Guest Journey | 0.2 | Journey ontology; 14 stages; touchpoints; transitions; emotional choreography; seven-question and never-ask tests; archetypes; friction scale | Expanded data model, decisions, outputs, roles, friction taxonomy, repository and lifecycle | M2-D01 to M2-D10 | Integrated; CEO decisions remain open |
| 3 — Nigerian Protocol & Precedence | 0.3 | Multiple-authority model; contextual precedence; verification; seating, arrival, ceremonial and conflict controls; protocol brief/master; readiness gate | Expanded data, roles, AI boundary, journey variants, outputs and repository; exercises/challenge excluded | M3-D01 to M3-D12 | Integrated; authoritative datasets and CEO decisions remain open |
| 4 — Nigerian Cultural & Ceremonial Intelligence | 0.4 | Five-question model; cultural authority; context packs; object controls; family/community, faith/interfaith and cultural-bridging frameworks; readiness gate | Resolved Module 3 ending; expanded data, roles, AI boundary, friction, products and repository; exercises/challenge excluded | M4-D01 to M4-D14 | Integrated; specialist packs and CEO decisions remain open |
| 5 — VIP & High-Net-Worth Guest Management | 0.5 | VIP handling dimensions; controlled file; field classification; ownership lifecycle; preferences/memory; variants; Control Desk/dashboard; recovery/readiness | Expanded data, roles, AI/privacy boundaries, seating, journey, products and repository; exercises/challenge excluded | M5-D01 to M5-D18 | Integrated; privacy/legal, security and CEO decisions remain open |
| 6 — Event Command & Control | 0.6 | Command authority; Command Centre; timelines/versioning; vendor/dependency control; RAG/priority/escalation; communications/handoffs; live loops; contingencies/recovery | Expanded data, roles, AI/specialist boundaries, journey/VIP/host protection, products and repository; master exercise excluded | M6-D01 to M6-D20 | Integrated; safety/specialist and CEO decisions remain open |
| 7 — Vendor & Supplier Management | 0.7 | Supplier intelligence; classifications/status; evidence-led due diligence; brief/code/scope/change control; dependencies; arrival/setup; inspection/readiness; failure/recovery; scorecards/network | Expanded data, decisions, command/vendor model, outputs and repository; follow-the-guest and master exercises excluded | M7-D01 to M7-D18 | Integrated; commercial, legal, specialist and CEO decisions remain open |
| 8 — Protocol, Ceremony & Run-of-Show | 0.8 | Ceremony architecture/spine; principal routes; contextual authority; movement matrix; Run of Show/cues/clock/GO-HOLD; arrivals/holding; speakers/MC/stage/photo; transitions/recovery | Integrated Modules 3–7 into ceremony state/control; expanded data, roles, AI boundaries, outputs and repository; master exercise excluded | M8-D01 to M8-D22 | Integrated; authority, safety, media and CEO decisions remain open |
| 9 — White-Glove Service Operations | 0.9 | Executable standards contract/lifecycle; CEO library; event plan; staff views; behaviour/language/privacy; zones/ownership; greeting/access; dining/dietary/restroom/comfort; recovery/final touch; competency/assurance | Turned principles/rules into event-applicable, owned and evidenced standards; expanded data, roles, AI boundaries, outputs and repository; CEO exercise excluded | M9-D01 to M9-D24 | Integrated; thresholds, safety, HR/privacy, legal and CEO decisions remain open |
| 10 — Event Command, Control & Live Operations | 0.10 | Canonical operational picture; command lenses; look-ahead/latest-safe action; signal/assertion/forecast/recommendation pipeline; CEO filter; five-level escalation; risk/incident intelligence; AI assurance/evaluation | Reconciled and refined Module 6 rather than duplicating it; expanded data, roles, AI boundaries, outputs and repository; CEO exercise excluded | M10-D01 to M10-D26 | Integrated; live data, specialist, security/privacy, validation and CEO decisions remain open |
| 11 — Event Risk, Crisis & Service Recovery | 0.11 | Risk philosophy; incident-vs-crisis test; risk categories/scoring/register; decision triggers; domain incident protocols (medical, security/VIP, weather, power, catering, vendor); service-recovery sequence; one-voice and client-briefing communication; crisis command/log; after-action/five-whys learning cycle | Reconciled crisis scale with existing 76.2 ladder rather than duplicating it; expanded data, roles, AI boundaries, outputs and repository; CEO Master Exercise excluded | M11-D01 to M11-D12 w e | Integrated; Lagos baselines, eather thresholds, xternal-authority, legal/regulatory and CEO decisions remain open |
| 12 — The Event Operating System | 0.12 | MD-EOS; Master Event File/Event ID; event-protection principles; Principal l Profile; guest segmentation/priority matrix; event-wide dependency map; SOP library; system-readiness aggregation; Known Unknowns register; client debrief/event report templates | Reconciled event ifecycle with Section 6 and control layers with Section 2; confirmed rather than duplicated existing programme, RAG, dependency and decision objects; identified cross- event knowledge base as unbuilt; expanded data, roles, AI boundaries and repository | M12-D01 to M12-D08 | Integrated; cross-event knowledge-base design/privacy segregation and remaining CEO decisions remain open; CEO Master Assignment excluded |
| 13 — Vendor & Supplier Mastery | 0.13 | Due-diligence diagnostic techniques I (portfolio test, interview protocol, M total-cost-of-failure); the Vendor 4 Partner Code (fills a previously r referenced but undefined object); t guest-ready inspection techniques b (Final Walk, five-metre test, guest-eye f test); critical path as a named s dependency-graph output; vendor t removal criteria v | ntegrated into odule 7 (Sections 7–53) as efinements rather han a new module lock; surfaced and lagged — not ilently resolved — hree competing endor-scorecard models and the Vendor Pyramid’s overlap with existing classification dimensions | M13-D01 to M13-D04 7; primary va w p u (partner code s u s | Substantially overlapped Module lue as filling reviously ndefined content ) and urfacing three nreconciled corecard models; CEO decisions remain open |
| 14 — Staffing, Service Culture & the White-Glove Team | 0.14 | Team architecture and RACI; G character-based hiring and interview b diagnostics; staff escalation matrix r (reconciled with 76.2); role cards/ M briefing/positioning map and Floating 1 Concierge; culture-building mechanism; d recognition/accountability doctrine; e staff maturity model; wellbeing, r communication and confidentiality d practice; canonical 5-second d acknowledgement target (M14-D01) b | uest-facing ehaviour content econciled with odule 9 (Section 03) rather than uplicated; staff scalation matrix eused 76.2 ladder irectly; expanded ata, roles, AI oundaries and repository; CEO Master Assignment excluded | M14-D01 N (resolved o — 5s l target) a to M14-D13 | ew rganisational/HR ayer genuinely dded; guest- facing content reconciled with Module 9; eleven explicit HR/legal blind spots catalogued and logged; the one conflict this module raised was resolved same-day |
| 15 — Guest Communication, Concierge & the Art of Personalisation | 0.15 | Invitation/RSVP/confirmation/reminder R object set; concierge intelligence va pack and three-concierge-variant ca relationship; message-drafting es hierarchy (Action/Time/Location/ ma Context/Detail); Clarify sub-step and di service-recovery message script; de family-authority gap identified; sa international-guest brief merge Mo recommended al | ecovery-sequence riant folded into nonical 68.1; calation matrix pped to 76.2 rectly (no new cision needed, me pattern as dule 14); nearly l other structure already existed (Comm/Touchpoint model, VIP privacy/ channel rules, pre-event cadence, service-language table, client- briefing doctrine); expanded data, roles, AI boundaries and repository | M15-D01 to M15-D06 | Most heavily reconciled module since Module 13; enuine ontribution is the nvitation/RSVP/ oncierge orrespondence ifecycle; family- uthority owner and brief-merge decisions remain open; CEO Master Assignment excluded |
| 16 — Event-Day Command, Control & the Operations Room | 0.16 | CEO-should-not-be-radio-operator C principle; first-guest/last-guest c attention; the 80% decision rule; a event-day decision matrix (quick C version of 76.3); radio phrasing m examples for 76.1; Incident Priority p scale retired in favour of the 86.2 m Crisis Scale c | ommand structure, ontrol loop, look- head horizons, ommand Centre, essage contract and rogramme-resilience odel all already anonical (Modules 6, 8, 9, 10, 11) | M16-D01 Mo (resolved r — Incident Priority s retired, 86.2 Crisis Scale canonical) | st heavily econciled module to date; genuine contributions were mall but sharp; independently reinforced M12-D07 as the specification’s top priority gap; CEO Master Assignment excluded |
| 17 — Security, Safety, Privacy & Risk Management | 0.17 | Safety/security/privacy three- R dimension doctrine; people/place/ m information/reputation frame; access c zoning (complementary to 65.1); g authority-matrix boundary against m Family Decision Owner; lost child protocol; guardian-authority s verification and minor photography W consent (M14-D07 closed in full); a security audit scorecard ( | isk registers, edical/photography/ rowd protocols, uest-info inimisation, accessibility/dietary afety and the Final alk technique all lready canonical Modules 5, 7, 9, 11, 13); lost child protocol extended to a full safeguarding policy | M17-D01 F resolved c (Security Lead default); M14-D07 resolved (full child- safe- guarding policy) | ourth onsecutive heavily reconciled module; lasting contributions are the three- dimension doctrine, access zoning, and a complete child- safeguarding policy; CEO Master Assignment excluded |
| 18 — Vendor Management, Supplier Control & the Delivery Standard (integrated into Module 7) | 0.18 | Mock-up/first-article production V gate; recovery ladder (elaborates M the Activate step of 51.3); Six-P A qualitative evaluation frame; no- M surprise/subcontractor principle n folded into change control (49.3); pr Supplier Intelligence File field re enrichments; commercial authority su ladder and payment-milestone vi structure (49.2.2-49.2.3) (5 | endor Maturity odel folded into pproval State on 13-D02 precedent; o-surprise inciple partially solves the bcontractor- sibility gap 3.4) | M18-D01 Al resolved r (three M fields s added, M /10 in scale); f M13-D03 r resolved in structure (49.2.2- 49.2.3) | most entirely a estatement of odule 7, on the ame pattern as odule 13; tegrated as urther efinements to Sections 47–53; genuine contributions are the production- gate, recovery- ladder, and commercial- authority/payment- milestone structure closing a gap restated across three modules; CEO Master Assignment excluded |
| 19 — Staffing, Service Culture & the Guest Experience Team (integrated into Module 14) | 0.19 | Relief principle and Handover Reco Standard (partial progress on enti M11-D08); training-vs-briefing exis distinction with nine rehearsal 99– scenarios (partial progress on Modu M14-D04); Staff Talent Record lis (partial progress on M14-D05); new stat Staff Performance Scorecard, tha distinct from vendor/security res scorecards wit | nciled almost M19 rely into M1 ting Sections ( 107; consolidated le 14 blind-spot t with current us (124.7) rather n letting it be tated again hout an owner | -D01 to Share 9-D03 with open) sub over 14; fur refi gen clo Mod | d its title , and stantially lapped, Module integrated as ther nements; uine value was sing gaps ule 14 itself flagged, not new domain content; eight staffing- policy items remain fully untouched and need HR/legal ownership; CEO Master Assignment excluded |
| 20 — The Event Command Centre (incl. the AI Layer design) | 0.20 | Information/Alert/Decision/Incident taxonomy; reversible-vs-irreversible decision speed; client decision format; red-line countdown; the Maison Doclar AI Layer — full architecture (command-loop role mapping, six grounding mechanisms, AI Systems Owner role, honest 2026 capability boundary) | Command-centre content reconciled into Sections 37–45, 71–79, 119; Event Intelligence Database independentl confirmed Section 123 already correct; “CEO-level decisions” reframed to CEO-level synthesis and drafting, explained not substituted | M20-D01, M20-D02 (open, sequen- cing, not y conflicts) | Fourth command- centre pass, reconciled into existing sections; central contribution was the CEO-directed AI Layer design, reframing decision authority into synthesis/drafting authority with an explicit rationale; CEO Master Assignment excluded (candidate for AI shadow-mode evaluation, still open since Module 10) |
| 21 — Event Day Execution | 0.21 | T-24 readiness checkpoint (7 P’s); four-state status model; First Guest Test; Energy Curve and Guest Experience Pulse; Three-Level Imperfection Test; Lost Property record; Event Score (roll-up of vendor/staff/security scorecards) | Live-execution content reconciled into Sections 42, 51.1.1, 56, 59, 65, 95 and the command-loop/ recovery-sequence family; no new conflicts introduced | None R (no e conflicts) c w c E th tr | econciled into xisting sections; genuine ontributions ere the T-24 heckpoint, the nergy Curve/Pulse, e imperfection iage lens, and the Event Score built as an explicit roll-up rather than a fourth independent scorecard; CEO Master Assignment excluded |
| 22 — Service Recovery & Guest Psychology | 0.22-0.23 | Uncertainty-vs-delay doctrine; R “but” cancels apology; Recovery c Pyramid (depth scale); hidden- p complaint detection tied to Guest a Experience Pulse; Recovery KPI set m | econciled into anonical recovery laybook, Five Whys nd consequence odel; source’s internal numbering conflicted with this spec’s own Module 21 and is noted, not silently resolved | None Del (no tog con- hea flicts) re su r n fl th re | ivered ether, both vily conciled as spected before eview; source umbering agged rather an silently numbered; CEO Case Lab excluded |
| 23 — Discretion Privacy & Information Control | , 0.22-0.23 | Four-dimension discretion Di lifecycle (Information/Access/ re Behaviour/Retention); photography- ex consent categories; hotel-room- mo number rule; driver/staff a discretion boundaries; “how did you t know?” script; VIP-word-overuse r caution a | scretion Scale conciled onto the isting three-level del with General as genuine zero-th ier; family politics ule confirmed as lready solved by the Family Decision Owner (115.1), not a new mechanism | None Deli (no toge con- Mod flicts) con tha the Dec mod La | vered ther with ule 22; firmed rather n duplicated Family ision Owner el; CEO Case b excluded |
| 24 — Protocol Conflict, Diplomatic Judgement & High-Status Interactions | 0.24 | Conflict classification, compromise ladder, entourage model, Protocol Huddle and diplomatic interaction refinements | Reconciled with Modules 3, 4, 5, 8 and 10; exercises excluded | No new standalone decision series | Integrated; event-specific authoritative verification remains mandatory |
| 25 — Luxury Service Recovery Lab | 0.25 | Judgement-case patterns, smallest-effective intervention, visibility and consequence reasoning; Judgement Case Library | Cases reconciled with canonical recovery, command and learning models; exercises excluded | No new standalone decision series | Integrated; case promotion and validation remain governed |
| 26 — Art of Host Management | 0.26 | Host Journey, Authority Map, host briefs/debrief, no-surprise control, decision filtering and Family Decision Owner generalisation | Reconciled with client, family, command, communication and AI Consult models; exercises excluded | No new standalone decision series | Integrated; event-specific authority approval remains required |
| 27 — Reviewed unnumbered submission | 0.27 | Event architecture refinements folded into dependency, critical-path and status models | Integrated into existing canonical sections rather than duplicated | No new standalone decision series | Integrated as reconciliation; source-numbering discrepancy retained for audit |
| 28 — Reviewed unnumbered submission | 0.28 | Live command refinements folded into look-ahead, message and early-warning models | Integrated into existing canonical sections rather than duplicated | No new standalone decision series | Integrated as reconciliation; source-numbering discrepancy retained for audit |
| 29 — Discretion/privacy continuation | 0.29 | Further privacy/discretion reconciliation and limited additions within Section 137 | Extended Module 23 without creating a competing privacy model; exercises excluded | No new standalone decision series | Integrated; legal/privacy validation remains external |
| 30 — The Maison Doclar Standard | 0.30 | Ten Rules, Event Readiness Declaration, CEO Charter, Creed and capstone integration | Confirmed and named existing doctrine; added whole-event readiness artifact; exercise excluded | Capstone — no unresolved module decisions added | Integrated; establishes the closing standard and transition to implementation |

24 — Protocol 0.24 Never make the client the live Four-source/five- None Exceptionally Conflict, protocol manual; co-honouring dimension precedence (no heavily Diplomatic techniques; discreet identification variant and four- con- reconciled; Judgement & channel; unexpected-speaker level escalation flicts) Module 3’s High-Status response options; entourage matrix both reconciled existing Interactions classification model (principal/ onto existing models; framework (integrated into official/personal/security/support); source’s internal already covered Module 3) the Protocol Huddle numbering conflicted most of this in with this spec’s own more executable Module 23 and was form; genuine renumbered to 24 on contributions CEO instruction substantially close a pre-flagged Module 3 gap (19.5, protocol dispute/live- deviation playbooks); CEO Case Lab excluded ————————————————————————————————————————————-

25 — The Luxury 0.25 Six-dimension consequence model Twelve of fifteen None Judgement module; Service Recovery (Guest/Host/Protocol/Operations/ worked cases (no fifteen worked Lab, incl. the Reputation/Future); “interpret confirmed existing con- cases extracted Judgement Case intent, not the literal instruction” doctrine (strong flicts) as teaching Library (feeds the AI Consult capability); validation signal); content since “the principal can be the three cases and each carries its operational problem”; smallest several framing own stated effective intervention; the sections were lesson; only the escalation test (authority vs genuinely new; closing CEO discomfort); end-of-incident closure Judgement Case Challenge checklist; the Judgement Case Library deliberately excluded, being Library, deliberately distinguished kept distinct from genuinely open from the evidence-based Pattern the Pattern Library with no attached Library (123.2) to prevent answer illustrative doctrine
being mistaken for
observed evidence
————————————————————————————————————————————-

26 — The Art of 0.26, updated Authority Map (generalises Family Reconciled against None Turns from guest Host Management 0.29 Decision Owner beyond guest- Family Decision Owner, (no to principal; experience matters); Host Brief; Principal Profile and con- central Host Companion role; Host Time both client- flicts) contribution Budget; Principal Suite (access communication formulas generalises the rules); Host Journey (parallel to already canonical Family Decision Guest Journey); Host Debrief Owner into a (distinct from Client Debrief). Later A second host- full Authority enriched (v0.29, per CEO instruction, management Map; Principal not a new module) with: Three submission was Suite finally Experiences lens, one-sentence brief, reconciled against built as a real Family Lead position, host greeting this module’s object after tiers, full-day Host Time Budget with existing content and being mentioned energy-curve protection, Principal folded in directly; unbuilt since Suite private-moment/wardrobe content, no new module early modules; physical-care checklist, the number issued both CEO Master Celebration Principle, and the Host Exercises Experience Score excluded ————————————————————————————————————————————-

27 — The 0.27 Multi-flow overlay mapping (folded Nearly the entire None CEO’s suspicion Architecture of a into 50.1, not a new object); WHEN module already (no of substantial White-Glove Event field folded into the message canonical across con- overlap (no standalone contract (76.1) Modules 6, 7, 10, 11, flicts) confirmed on section — see 50.1, 13, 16, 20–21; time- careful review; 76.1) plus-condition cues contributes restate the existing almost nothing Critical cue contract new. No (56.2) almost standalone exactly section created; its two real contributions were folded directly into existing sections instead of adding document weight; no new roles, data entities or decisions required; CEO Master Exercise excluded ————————————————————————————————————————————-

28 — Event 0.28 Concrete signal examples folded Even more heavily None Numbering Intelligence & into 82.1 (obvious/subtle signals, overlapped than (no mismatch Live Command (no queue/empty-space interpretation); Module 27: command con- flagged — source standalone optional finer-grained Watch/ loop, NOW/NEXT/RISK, flicts) labelled this section — see 40.1, Prepare/Intervene/Escalate VIP tiers, escalation “Module 27” and 73.1, 82.1) subdivision folded into 40.1 chain, single source its predecessor of truth, version “Module 26,” control, change log, both already Event Black Box and used in this Five Whys all specification; already canonical; treated as this proposed 15-/60- spec’s Module 28 minute windows per CEO already inside instruction. No existing horizon standalone ranges (73.1) section created; before this module no new roles, arrived; “AI data entities or Opportunity” section decisions describes the required; CEO already-built AI Master Exercise Layer (126–134) excluded with near-identical
examples
————————————————————————————————————————————-

29 — The Art of 0.29 Discretion Ladder (convenience label Overlaps Module 23 None No standalone Discretion, bundling existing settings, not a almost entirely, plus (no section; source Privacy & new data model); family-photograph/ Module 17’s con- numbering Confidentiality photo-line management; digital protection frame and flicts) matched this (no standalone writing discipline (“write as if it the recovery-loop spec’s own section — see 29.1, will be seen,” folded into 29.3) family; eight-part sequence this 29.3, 120.3, privacy breakdown, time (no 137.2.1) four-level info mismatch); two classification and genuine points five-zone access folded into model all fold as 137.2.1; no new finer subdivisions roles or data of models already entities beyond canonical (137.2, the writing- 29.2, 120.3) discipline note; CEO Master Exercise excluded ————————————————————————————————————————————-

30 — The Maison 0.30 Ten Rules (citable summary of Almost the entire None CAPSTONE. Module Doclar Standard CAPSTONE doctrine already built); Event module confirms (no proposed almost (capstone) Readiness Declaration (new whole- doctrine already con- no new event go/no-go artifact, above built across nearly flicts) mechanism — existing domain gates); CEO Charter every prior module; correctly, for a (five responsibilities, the CEO trap, its own proposed capstone arriving “how Maison Doclar does things”); “operating library” after twenty-nine the Maison Doclar Creed, adopted as is a near-exact others; its this specification’s closing mission description of this proposed statement paired with Section 1’s specification as it “operating opening Purpose already stood library” turned (141.2); Four out to describe Levels of Mastery this reconciled onto the specification five-level staff itself; five maturity model genuine capstone (104.4) artifacts adopted (141.1– 141.5); module sequence reaches its stated end; Final CEO Exercise excluded ————————————————————————————————————————————-

Post-capstone — 0.31 Staffing Policy Framework (142, Not module Nine Not a module — gap-closing Provisional pending counsel sign- overlap review; decisions three CEO- integration off); Nigerian Protocol Register these are CEO- resolved commissioned (Sections 142–144) (143, Provisional and commissioned in documents verification-required-per-event, gap-closing design closing exactly [Verify] placeholders preserved, documents, not (M14- the three gaps not populated); AI Shadow-Mode modules to reconcile D02, identified at Evaluation Harness design (144, against prior D03, Module 30’s own architecture/acceptance-criteria/ content D06, close (141.8); test-library defined, not yet built); D08/ “resolved in new CTO role; new data entities M19- design” is (Vetting Record, Disciplinary D01, explicitly not Record, Shadow-mode test case, D09, “resolved in Divergence report) D10, practice” — D11, legal sign-off, D12, verification M20- calls and D02) harness construction all remain as the actual next work ————————————————————————————————————————————-

# Executive finalisation and navigation

# Appendix C — Final review and implementation register

## C1. Review actions completed

- Confirmed all 30 modules are represented, including reconciled/unnumbered submissions and post-capstone gap-closing documents.

- Preserved canonical reconciliation rather than reintroducing duplicate command, recovery, vendor, staffing, privacy or protocol systems.

- Added final release truth, navigation, system spine, implementation gates and non-negotiable safeguards at the front of the document.

- Completed the module change register through Module 30.

- Updated document identity, metadata, header/footer and version to v1.0 Final Draft.

- Kept provisional, event-specific and specialist-validation limitations explicit rather than promoting them to Approved knowledge.

## C2. Production blockers

| Blocker | Release treatment |
| --- | --- |
| AI shadow-mode harness not built/passed | Blocks any live AI protocol, precedence, seating or address recommendation. |
| Employment-counsel review outstanding | Staffing Policy Framework remains Provisional; no claim of final legal compliance. |
| Protocol register requires event-specific verification | Every live event must confirm officeholders, institution/palace/mission requirements and unresolved edge cases. |
| No live-event validation dataset | Thresholds, staffing ratios, alerting, prediction and workflow usability remain provisional until tested. |
| Specialist plans not supplied by general specification | Security, medical, fire, crowd, electrical/structural, food-safety and emergency controls require competent owners and local requirements. |
| Privacy/security implementation not proven | Role/field access, redaction, exports, devices, offline cache, retention and breach controls must pass technical and operational tests. |

## C3. Final approval record

| Field | To be completed |
| --- | --- |
| Baseline approver | CEO, Maison Doclar |
| Approval decision | Approved / Approved with conditions / Returned for revision |
| Approved knowledge states | Reference the knowledge-state register and exceptions |
| Conditions | External validations, deferred decisions and pilot restrictions |
| Effective version | v1.0 |
| Approval date |  |
| Next review trigger | Material doctrine change, legal/protocol update, pilot evidence or six-month review—whichever occurs first |