## START HERE
MAISON DOCLAR — PRODUCTION GOVERNANCE REGISTER
Version 1.0 ¦ Canonical control record for build, acceptance, release and production operation
PURPOSE
Use this workbook to prove what was decided, tested, accepted, authorised, deployed and learned. It is the operational source of truth for production governance; it does not replace code, automated tests, monitoring or the Intelligence Specification.
NON-NEGOTIABLE CONTROL LAWS |  |  | HOW TO USE
1 | No candidate, no release | Every deployment decision is tied to one immutable release candidate and commit. | 1. Create | Add a RELEASE CANDIDATE before acceptance work begins.
2 | Evidence before assertion | A gate cannot pass without linked, reviewable evidence. | 2. Link | Use the same Candidate ID across gates, evidence, defects, risks and approvals.
3 | Scope is explicit | Authorisation states client, event, region, capability and environment. | 3. Prove | Attach durable evidence links; reviewers verify them in EVIDENCE.
4 | Blocking means stop | Critical defects, failed gates and unresolved major incidents stop release. | 4. Resolve | Close blockers or record a formally approved, time-limited exception.
5 | Exceptions expire | Every waiver has an owner, compensating control and expiry date. | 5. Review | Select the candidate on DASHBOARD and check the automatic release signal.
6 | Sensitive capabilities separate | AI, FaceGate and cross-event intelligence require explicit approvals. | 6. Decide | Record the CEO decision in CEO RELEASES with exact scope and conditions.
7 | CEO authority is bounded | CEO authorisation applies only to the named candidate and stated scope. | 7. Deploy | Record the deployment result and production version on the candidate row.
8 | Rollback is real | Rollback, support and incident ownership must be tested before production. | 8. Learn | Log incidents and feed material lessons into decisions and change control.
9 | Audit trail is permanent | Decisions, approvals and production changes are never silently rewritten.
ROLE BOUNDARIES
CEO | Owns final production authorisation and risk acceptance; may not self-verify technical evidence. |  | CTO / Engineering Lead | Owns technical readiness, candidate integrity, rollback and deployment execution.
Product / Operations | Owns workflow fitness, event readiness, service standards and operational evidence. |  | Security / Privacy | Owns security, privacy, biometrics, access and data-handling approvals.
Independent Reviewer | Verifies acceptance evidence and records pass/fail without changing implementation. |  | Release Manager | Reconciles candidate, gates, approvals and deployment record.
Incident Commander | Controls production incident response, communications and recovery. |  | Governance Administrator | Maintains register quality and vocabulary; cannot approve their own substantive record.
Control rule | Record preparer and approver must be different people for high-risk approvals. |  | Retention | Retain governance records according to the applicable legal and client schedule.

## DASHBOARD
PRODUCTION GOVERNANCE DASHBOARD
Select a Candidate ID. All signals below are calculated from the underlying registers.
Selected Candidate ID |  |  | Open control | Count
|  |  | Critical / major open defects | 0
AUTOMATIC RELEASE SIGNAL |  |  | Failed or incomplete G0–G6 gates | 0
SELECT A CANDIDATE |  |  | Critical / major open incidents | 0
|  |  | Expired active exceptions | 0
|  |  | Expired required approvals | 0
|  |  | Unverified or stale evidence | 0
Blocking control | Count | Required state | Candidate readiness failures | 0
Critical / major open defects | 0 | 0 | Blocking open questions | 0
Failed or incomplete G0–G6 gates | 0 | 0
Critical / major open incidents | 0 | 0
Expired active exceptions | 0 | 0
Expired required approvals | 0 | 0
Unverified or stale evidence | 0 | 0
Candidate readiness failures | 0 | 0
Blocking open questions | 0 | 0
Interpretation: READY FOR CEO DECISION is not production approval. Production is authorised only by a valid CEO RELEASES record for the exact candidate and scope.

## RELEASE CANDIDATES
RELEASE CANDIDATES
One immutable row per build proposed for staging or production. Do not reuse a Candidate ID.
Candidate ID* | Version* | Commit SHA* | Environment* | Created Date* | Owner* | Scope Summary* | Reconciled?* | Security Test* | Acceptance Test* | Migration Test* | Rollback Test* | Observability Ready* | Support Ready* | DR Ready* | Privacy Ready* | Required Approvals Complete?* | Deployment Status | Production Version | Deployed At | Deployment Record Link | Notes

## GATES
GATES
Required G0–G6 controls for each release candidate. A gate passes only after its evidence is independently verified.
Gate Record ID* | Candidate ID* | Gate* | Gate Name* | Status* | Owner* | Reviewer* | Evidence ID(s)* | Reviewed Date | Exception ID | Findings / Conditions | Next Action | Due Date | Last Updated*

## DECISIONS
DECISIONS
Canonical architecture, product, operational and policy decisions. Supersede records; do not overwrite history.
Decision ID* | Scope Type* | Scope ID | Candidate ID | Title* | Decision* | Rationale* | Alternatives Considered | Consequences | Owner* | Decision Status* | Approver* | Decision Date | Effective Date | Supersedes ID | Evidence IDs | Review Date | Confidentiality* | Last Updated*

## OPEN QUESTIONS
OPEN QUESTIONS
Unresolved matters that can change scope, design, safety or release readiness.
Question ID* | Candidate ID | Scope Type* | Scope ID | Question* | Why It Matters* | Priority* | Owner* | Raised Date* | Due Date* | Status* | Blocking?* | Decision ID | Answer / Resolution | Resolved Date | Escalated To | Last Updated* | Age (days) | Overdue?

## DEFECTS
DEFECTS
All acceptance and production defects. Severity is impact-based; closure requires retest evidence.
Defect ID* | Event ID | Candidate ID* | Found In* | Title* | Severity* | Status* | Owner* | Found Date* | Due Date | Affected Capability* | Guest / Operational Impact | Reproduction Steps* | Expected Result* | Actual Result* | Fix Commit | Retest Evidence ID | Retest Result | Closed Date | Exception ID | Last Updated* | Age (days) | Overdue?

## RISKS
RISKS
Known delivery, operational, security, privacy, commercial and reputational risks.
Risk ID* | Candidate ID | Event ID | Scope Type* | Scope ID | Risk Statement* | Category* | Likelihood* | Impact* | Rating* | Owner* | Treatment* | Mitigation / Controls* | Trigger / Indicator | Residual Rating* | Status* | Review Date* | Decision ID | Exception ID | Evidence IDs | Last Updated* | Overdue Review?

## APPROVALS
APPROVALS
Named, bounded approvals. Sensitive capabilities and production releases require explicit records.
Approval ID* | Candidate ID | Event ID | Scope Type* | Scope ID | Approval Type* | Capability | Required?* | Status* | Approver Role* | Approver Name* | Requested Date* | Decision Date | Effective From | Expiry Date | Conditions | Evidence IDs* | Related Decision ID | Revoked Date | Revocation Reason | Last Updated* | Expired?

## EXCEPTIONS
EXCEPTIONS
Time-limited waivers only. Every exception needs compensating controls, approval and expiry.
Exception ID* | Candidate ID | Event ID | Control / Requirement* | Reason* | Risk ID* | Compensating Controls* | Status* | Owner* | Approver* | Requested Date* | Approved Date | Expiry Date* | Closure Evidence ID | Closed Date | Renewal Exception ID | Last Updated* | Expired Active?

## INCIDENTS
INCIDENTS
Production and rehearsal incidents, from detection through recovery, review and corrective action.
Incident ID* | Candidate ID | Event ID | Environment* | Severity* | Status* | Title* | Detected At* | Reported By* | Incident Commander* | Affected Capability* | Guest / Business Impact* | Containment | Root Cause | Recovery At | Communications Owner | Client Notified? | Regulator Review? | Post-Incident Review Date | Corrective Change IDs | Evidence IDs | Closed At | Last Updated* | Duration (hours)

## EVIDENCE
EVIDENCE
Durable proof supporting acceptance, approval and release. Verification is separate from submission.
Evidence ID* | Candidate ID* | Event ID | Gate | Evidence Type* | Title* | Capability / Requirement* | Source / Tool* | Location / Link* | Captured At* | Submitted By* | Status* | Verified By | Verified At | Validity Ends | Contains Personal Data?* | Access Classification* | Related Record IDs | Notes | Last Updated* | Stale?

## CHANGE CONTROL
CHANGE CONTROL
All material production-bound changes, including emergency work, with impact, approval and rollback.
Change ID* | Candidate ID | Event ID | Change Type* | Title* | Description* | Reason* | Requested By* | Owner* | Priority* | Risk Rating* | Affected Components* | Data Migration?* | Security / Privacy Impact?* | Operational Impact* | Planned Window | Rollback Plan* | Test Evidence IDs* | Approval IDs* | Status* | Deployed At | Deployment Result | Post-Change Review | Decision ID | Last Updated*

## CEO RELEASES
CEO RELEASES
The final bounded production decision. General release never implies approval for AI, FaceGate, biometrics or cross-event intelligence.
CEO Release ID* | Candidate ID* | Decision* | Decision Date* | CEO Name* | Environment* | Client Scope* | Event Scope* | Region Scope* | Capabilities Authorised* | Capabilities Excluded* | AI Authorised?* | FaceGate / Biometrics Authorised?* | Cross-Event Intelligence Authorised?* | Conditions | Effective From* | Expiry Date | Rollback Owner* | Support Owner* | Incident Commander* | Approval IDs* | Evidence IDs* | Risk IDs | Exception IDs | Revoked Date | Revocation Reason | Production Version | Deployment Record | Last Updated*

## LOOKUPS
LOOKUPS
Controlled values used by dropdown fields. Governance administrator may extend these lists through a controlled change.
Priority | Generic Status | Gate Status | Decision Status | Approval Status | Release Decision | Severity | Risk Rating | Scope Type | Yes No | Evidence Status | Change Type | Environment | Confidentiality
Critical | Open | Not Run | Proposed | Pending | Not Authorised | Critical | Critical | Platform | Yes | Draft | Architecture | Local | Internal
High | In Progress | In Progress | Under Review | Approved | Conditional | Major | High | Client | No | Submitted | Data | Development | Restricted
Medium | Blocked | Passed | Approved | Conditional | Authorised | Moderate | Medium | Event |  | Verified | Security | Staging | Highly Restricted
Low | Pending | Failed | Rejected | Rejected | Revoked | Minor | Low | Release Candidate |  | Rejected | Frontend | Production
| Closed | Waived | Superseded | Expired | Expired |  |  | Capability |  | Stale | Backend
| Cancelled |  |  | Revoked |  |  |  | Region |  |  | Infrastructure
Operations
Policy
Emergency